## Slide 1: STIX/TAXII Plugfest Lessons Learned Jan 2018
Rev 1

## Slide 2: Lessons Learned Categories
Logistics/General
  What we need to repeat and make better
  Things to improve associated with planning, organization, meeting
STIX/TAXII Specifications
  Items that were not clear or incorrect in specifications
Interop Test Documents
  Items that were not clear or incorrect in test documents or procedures

## Slide 3: Logistics/General #1
Item | Notes
Organization/Agenda | - More organization and agenda defined the easier it will be to execute on the plan for the plugfest
Facility/Lunch/Room/Meeting | Ensure video/collaboration screen sharing Ensure wireless network availability Lunch and meeting room size sufficient for all participants to sit together or in close collaboration Ensure cross group conversations Ensure easy side-bars if necessary
Variety of data and implementations more than expected/good for exposure | - More variety of use cases and data helps expose products and vendors to different requirements
Right people (i.e. engineers) attended/collaborative | - Engineers able to change code/redeploy changes in real-time - Understanding of the specification and product use
Enforcement of coming in person and be ready with their products (concrete deliverable for the plugfest) | In-person collaboration is a must for good debugging/problem solving Having a fixed date helped bring focus to dev efforts

## Slide 4: Logistics/General #2
Issue | Action
Getting on conferencing facilities and sharing screens caused delay | - Ensure conferencing program to allow easy sharing without requiring explicit handover
Time spent on making sure everyone was in the plugfest room/slack to collaborate | - Ensure that everyone participating in the plugfest confirms access to the plugfest slack channel before the meeting
Need to encourage more upfront org self-testing before plugfest to help encourage better preparation | - Publish clear guidelines on minimum required self-verification before admitting plugfest participants (i.e. vendor X must verify tests X, Y, Z all work before being allowed into plugfest)
Need to plugfest more often (> 1 ), maybe coincident with F2F meetings | - Ensure future F2F and Plugfest cadence is published and managed actively
Should include time for out-of-scope testing as part of plugfest E.g. try new features if vendor X & Y support new feature | - Provide option for vendors to collaborate together during plugfest on new features if core plugfest tests are completed

## Slide 5: Logistics/General #3
Issue | Action
Lack of stable/validated schema and data sets that can be used for all clients and servers to verify against before plugfests would be good | Define and maintain package of downloadable JSON schema, test data and automated unit tests that all plugfest/interop participants can use before certification or plugfest Need common sets of data for all to use for testing Need unique/vendor sets of data that are unique to vendors or use cases that help provide more robust testing
Test data in test documents is not fully correct and duplicated UUIDs. | - Ensure test documents are correct
Need matrix for NxN conversations to order/specify to help keep track of what is going on during plugfest | - Helps plugfest participants focus and also keep track of what needs to be tested and what is being tested
Only 3 vendors support writing to collections | - Need increased number of vendors creating/pushing STIX content over TAXII

## Slide 6: STIX/TAXII Specifications #1
Issue | Action
Absolute Taxii URL problem can’t be used. Requires specification work to allow either discovery of URL or relative URLs for taxii | - Discuss in F2F
Different vendors implemented URLs and API roots differently due to confusion on whether to use /taxii or /taxii/api_root or other URLs | - Discuss spec cleanup to make it easier to follow and implement consistently
Different Media types on different endpoints is confusing and causes problems. Client could put both STIX and TAXII media types in requests accept header | - Update spec to include best practices
Max_content_length understandabiliy | Discuss in F2F should be considered per collection instead of per root. It’s not clear how max content length should really be implemented when content can’t be fitted into the response
HTTP status code in errors should be mandatory not optional (in the spec) | - Discuss in F2F

## Slide 7: STIX/TAXII Specifications #2
Issue | Action
Label property should not be mandatory (in spec). A vendor was expecting a mandatory field but it’s not included. | - Discuss in F2F on how to fix label spec text

## Slide 8: Interop Test Documents
Issue | Action
Fix maxcontentlength to add _ underscores in interop spec to match taxii spec | - Fix in next rev
Remove URL from 6. For API_Root as its not returned as part of the returned result | - Fix in next rev
Getting basic information of API Root and Server and verifying on client is not necessarily proving very much. Should test more semantic to check version compatibility instead of JSON parsing. | - Consider in Interop group
Make sure that content types match on responses | - Add test
MITRE libraries are not accepting self-signed certs and not accepting root certificates | - More MITRE focus
Make sure tests for both trailing / and not trailing / are handled correctly | - Add test
Version missing from accept header should be accepted and default to taxii-2 but its recommended that we include it. | - Add test