## EDXL-DE 2.0 Issues List
OASIS Emergency Management Technical Committee EDXL-DE 2.0 Issues List - GIS Related Subset | [9 empty] | Addition | Open
[10 empty] | Deletion | Closed
Editorial-Error
| NOTE: Status reflected in Section Title column: Grey=Draft Fix Done to DE 2.0 Draft Spec; Yellow=Issue to be resolved with geo-oasis:Where; Red=Needs Further Study; Green=Edit Approved | [5 empty] | NOTE: ACTION ITEM: GO THROUGH ENTIRE DOC AND ORDER THE DIAGRAM LIST SAME SEQUENCE AS THE TEXTUAL LIST. Text needs to reflect the diagram sequence rather than the other way around.
NOTE: Need to match up element to message matrix with all section changes to ensure they always match
ID | Date | Raised By | Status | Section Title | Short Description | Comment Description | 1st pass Resolution Description | Comments and/or Final Resolution | Resolution Notes. Added Requirements | Editorial-Substance
2 | 2010-04-30 | Don McGarry | Closed | polygon | Ring Orientation |  | Tabled for later discussion-Examine all of TargetArea | Use OASIS Where Profile of GML when available |  | [HJ] add left hand rule verbage | Closed
5 | 2010-04-30 | Doug Allport | Open | TargetArea – new elements recommended to distinguish DistributionTargetArea from SourceTargetArea | the Canadian FIPS like geocode values for area | These codes apply to geopolitical boundaries and are seen as very useful for jurisdictional routing, policy, etc. Hans was to have included them after the Philadelphia meetings. | Tabled for TargetArea discussion | Resolution: New Element: DistributionTargetArea: Area bounded by whatever criteria are being used for delivery of EDXL-DE package. New Element(s): SourceArea: Area bounded by observation of event such as HazMat. Not Closed. To be discussed further. |  | [Doug Allport] Need co-ordinates for putting points on a map. Target Area is not good enough as is because it is for destination area. Canadian system to use Atom, PubSubHubBub. Need to add some kind of <EventArea>, need Value Name approach. This is needed to put in the Canadian SGC (Standard Geographic Classification) codes or Marine locations - example shelter locations - event type needed for symbology [HJ] add <AreaOfInterest> with <keyword> to describe what kind of area it is "Event Location", "Source Location", "Display Location", etc. Possible to use ValueListURI.
13 | 2010-04-30 | Don McGarry | Open | targetArea | Move to GeoOASIS Where | Help me Carl Reed | Tabled for discussion with all TargetArea | OASIS:Where Profile of GML. Rex will present TSO--Need to follow up with Carl Reed on Schedule. Can use existing stopgap from HAVE and RM. |  | [HJ] Update to GeoOASIS Where 2009 schema provides methods to address published GIS requirements (i.e. altitude, points, etc.)
14 | 2010-04-30 | Don McGarry | Open | targetArea | Point | We need a point object | Tabled for discussion with all TargetArea | OASIS:Where Profile of GML. Rex will present TSO--Need to follow up with Carl Reed on Schedule. Can use existing stopgap from HAVE and RM. |  | [HJ] Possible to use <georss:point> rather than <gml:Point>...</gml:Point> to simplify. Concern is that there are 3 encoding for GeoRSS (see http://en.wikipedia.org/wiki/GeoRSS)
15 | 2010-04-30 | Hans Jespersen | Open | targetArea | Preference | How do we handle multiple area type preference | Tabled for discussion with all TargetArea-LoCodes for ascending order of precision | GeoGIS SC Issue. See above. |  | [HJ] Discussion of xml schema <sequence> vs <all> and effects on parsers. Need suggestions on how to allow an ordered list just for the <TargetArea> elements. For example, we could explicitly specify <PrimaryTargetArea> and <SecondaryTargetArea> as a <sequence>
16 | 2010-04-30 | Don McGarry | Open | Circle – will fix and do new examples when everything else done | Fix example | example shows lat,<space>lon<space>radius; should be lat,lon<space>radius | Tabled for discussion with all TargetArea | Fix example. OASIS:Where Profile of GML. Need to follow up with Carl Reed on Schedule. Can use existing stopgap from HAVE and RM. |  | [HJ] fixed spec to clarify existing use of <circle> in DE 1.0. Need GeoOasis Where 2009 schema for further review
31 | 2005-08-16 | Hans Jespersen | Closed | contentObject | Geo | Proposal to add a geospatial location for the originator within the <contentElement> structure | Add to TargetArea discussion as "SourceArea" for originator. | Resolution: See #5 above. |  | [HJ] we can do some preliminary work to add an <AreaOfInterest> or <ContentArea> in content object using existing <TargetArea> schemas and later update it to the GeoOasis Where 2009 schema
43 | 2010-06-24 | Tim Gilmore | Closed | circle | Clarify Format | lat,lon radius | Discuss with TargetArea. |  |  | [HJ] addressed in edits to spec v06+HJ
44 | 2010-06-24 | Tim Gilmore | Open | circle | Radius | Max value and unsigned | Discuss with TargetArea. | Can be addressed in OASIS:Where Profile of GML. We need to keep tracking Geospatial issues. |  | [HJ] not likely to be address in OGC spec. Need to have GIS SC address independent of OGC
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
c
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
5137
514
515
516
517
10/11/07--Issue #518: Done.
519
520
521
522
523
524
525
526
527
528
529
530
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
Note