## Sheet1
KMIP V1.2 schedule
Task | Lead | 2012-10-04 | 2012-10-11 | 2012-10-18 | 2012-10-25 | 2012-11-01 | 2012-11-08 | 2012-11-15 | (22-Nov) | 2012-11-29 | 2012-12-06 | 2012-12-13
Required for V1.2
Create proposal for key value in key block as optional and new “not here” attribute | John/Denis | 2012-10-04: Proposal review; 2012-10-18: Revised proposal; 2012-11-01: Ballot
Create proposal for Get Random operation based on Crypto Profile; also use case write-up | Tim/John/BobG | 2012-10-11: Proposal review; 2012-11-01: Revised proposal; 2012-11-15: Ballot
write new Usage Guide section on how to do attestation for Get, using Register and Get Random | Kelley/BobG | 2012-10-04: Draft text review; 2012-10-25: Revised text; 2012-11-08: Voice vote
write new Usage Guide section on how to do Metadata-only object | Denis/BobG | 2012-10-18: Draft text review; 2012-11-01: Revised text; 2012-11-15: Voice vote
complete proposal for encrypt etc, based on existing proposal; also write use cases | Tim/Denis/BobL | 2012-10-11: Proposal review; 2012-11-01: Revised proposal; 2012-11-15: Ballot
write new profiles and/or Usage Guide sections for 3 registration models | BobG/Gordon | 2012-10-18: Draft text review; 2012-11-08: Revised text | Voice vote
Possible for V1.2
proposal(s) on alternative protocol representations | Tim/BobG | 2012-10-25: Proposal review; 2012-11-15: Revised proposal |  | Ballot
investigate and return to committee with information to resolve decision on mutability of values, either as general issue or as template-specific | Bruce/Tim | 2012-10-04: Discussion; 2012-10-25: Proposal review; 2012-11-08: Revised proposal | Ballot
investigate and propose mapping PGP requirements including pgpuserid, ADK, object signature into existing/new KMIP capabilities, such as link types and obect name; new Usage Guide section. | Mike/BobG/Judy | 2012-10-11: Proposal review; 2012-11-08: Revised proposal | Ballot
write proposal for crypto-domain parameters in key block | Denis/BobL | 2012-11-01: Proposal review; 2012-11-15: Revised proposal |  | Ballot
write proposal for attribute-based grouping mechanism for tenant support | Gordon/BobG/Kiran | 2012-11-01: Proposal review; 2012-11-15: Revised proposal |  | Ballot
write proposal for client-specific usage limits, reporting back on what clients have used, and specifyencrypt/decrypt | BobL/BobG | 2012-11-01: Proposal review; 2012-11-15: Revised proposal |  | Ballot
investigate and report back to TC on whether any other query enhancements are needed | Tim/BobG | 2012-11-08: Proposal review | Revised proposal |  | Ballot
investigate and report back to TC on whether enhancements to notify/put are needed | JohnL | 2012-10-18: Discuss
investigate and report back to TC on whether “protected data” attribute is needed | Gordon | 2012-10-18: Discuss
investigate and report back to TC on whether we should support a mechanism for identifying the master when copying keys | Gordon/BobG | 2012-11-15: Discuss
investigate and report back to TC on group managed object in order to enable clients to identify other clients | JohnL | 2012-11-15: Discuss
define additional list of ECC algorithms and other enumerations | Denis | 2012-10-25: Proposal review; 2012-11-08: Revised proposal | Ballot
investigate and report back to TC on key versioning options | Saikat/Denis | 2012-10-18: Discuss
KMIP document re-structuring
proposal/example of Profile doc and library revision, based on f2f discussion (date tbd) | BobG/Subhash/BobL | 2012-11-15: Proposal review |  | Revised proposal |  | Ballot
review Usage Guide to determine whether to remove information, create new organization (assumptions / guidance on functionality / how to implementation attestation, etc) (date tbd) | Judy/Indra/BobG | 2012-11-01: Discuss
specify flow and test cases for asymmetric key wrapping of symmetric keys | Gordon/BobG/Bruce/Judy | 2012-11-15: Proposal review |  | Revised proposal |  | Ballot
determine whether to document the key escrow use case | Gordon/BobG | 2012-11-01: Discuss | Discuss