## PLCS templates
Tracker: PLCS templates
Export date: 2012-11-12 02:58:53
CCB Meeting: 2012-11-12
Row | Id | Category | Summary | Details | CCB decision | Priority | Status | Resolution | Release | Submitter | Assignee | Closer | Date raised | Date Closed
1 | 3581927 |  | OASIS:Organization - remove reference to Name class | Theproperty contextlessIdRole has an OWL class constraint An optional reference to the class used to define the role of the context free identifier (Organization.contextlessId) of the organization. For example CAGE code. The reference data used in Block: Ap239Ap233Psm:ClassSelect is restricted as follows: RDL constraint 1: The reference data for: ClassifiedByOwlClass.class is restricted to one of the following classes or a subclass of one of them: http://docs.oasis-open.org/plcs/ns/plcslib/v1.0/data/contexts/OASIS/refdata/plcs-rdl#Organization_identification_code http://docs.oasis-open.org/plcs/ns/plcslib/v1.0/data/contexts/OASIS/refdata/plcs-rdl#Organization_name The Organization_name class is not an identifier class | Accepted | 5 | Open | Remind |  | robbod | nobody | nobody | 2012-10-30 02:36 | 1970-01-01 12:00
2 | 3585041 |  | OASIS:ActualActivity - make planned activity optional | The planned activity should be optional | Accepted | 5 | Open | Remind |  | robbod | nobody | nobody | 2012-11-07 08:16 | 1970-01-01 12:00
3 | 3585150 |  | OASIS:ViewDefinitionContext not developed according to guide | There are a number of errors in the template. - Template block definition diagram out of date (the output port is of type ExternalViewDefinitionContext, but the parametric diagram shows it to be a ViewDefinitionContext) - The private properties apDomain, lifeCycle and viewDefinitionContext do not show their multiplicities. - The private properties apDomain and LifeCycle should both be reference properties not part properties as currently defined. - The public properties are not stereotyped as reference properties in the MagicDraw file. | Accepted | 5 | Open | Remind |  | philsp | nobody | nobody | 2012-11-07 01:40 | 1970-01-01 12:00
4 | 3586002 |  | OASIS: MeasuredProperty - create | Add a template representing a read property value. It should have the following characteristics: - name (read property name) - value (read property value) - unit (read property value unit) - dateRecorded : the date when the property value is read - recordedByEquipment: the equipment that performed the reading - recordedByPersOrg: the entity that read the value - typeOfValue: a class indicating if the property is an increment or an absolut value | Accepted | 5 | Open | Remind |  | phoubaux | phoubaux | nobody | 2012-11-10 10:46 | 1970-01-01 12:00
7 | 3581821 |  | OASIS: Catalog - add \"names\" property | Add a property "names" to the template | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 09:17 | 2012-10-31 08:09
8 | 3581823 |  | OASIS: CatalogItem - change binding of "names" property | Change the binding of the "names" property so that it binds to the BreakdownElement template "names" property. | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 09:21 | 2012-10-31 08:09
9 | 3581853 |  | OASIS: WorkRequest - add a "name" property | optional name property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:04 | 2012-10-31 08:26
10 | 3581854 |  | OASIS: WorkOrder - add "name" property | optional name property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:05 | 2012-10-31 08:36
11 | 3581855 |  | OASIS: DirectedActivity - add "names" property | optional names property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:06 | 2012-10-31 09:12
12 | 3581856 |  | OASIS: WorkDone - add "names" property | optional names property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:06 | 2012-10-31 08:55
13 | 3581857 |  | OASIS: PlannedActivity - add "names" property | optional names property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:08 | 2012-10-31 09:04
14 | 3581858 |  | OASIS: ActualActivity - add "names" property | optional names property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:08 | 2012-10-31 09:29
15 | 3581859 |  | OASIS: ActualProductUsage - add "names" property | optional names property missing | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-30 11:09 | 2012-10-31 09:20
16 | 3582172 |  | OASIS: EnvironmentDefinition - create - | Need a template for representing a type o environment. | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 09:44 | 2012-10-31 01:36
17 | 3582175 |  | OASIS: EnvironmentObserved - create - | Need a template to represent the observation of environmental conditions | Accepted observedOn property should be renamed to observedByEquipment to avoid confusing the equipment used to make the measurement. Eg a thermometer with equipment that is operating in an environment | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 09:46 | 2012-11-07 03:28
18 | 3582176 |  | OASIS: Fleet - create | Need a template to represent a fleet of products | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 09:47 | 2012-10-31 06:06
19 | 3582177 |  | OASIS: Mission - create | Need a template to represent a mission activity | This should be renamed "ActualMission" as there may well be a planned mission as well | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 09:48 | 2012-11-08 07:53
20 | 3582179 |  | OASIS: EventReport - create | Need a template to represent the report of events to manage the all the information exchanged between stakeholders before reaching the actual activity that closes the event. This will be represented as a collection containing potentially: - product (endproducts / serialized assets / function) - contract - observations - state observed - environments observed - the task method to be performed - the actual performed activitys - the resource orders - etc ... | Should this be a Message? Is it really an OASIS template? | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 09:58 | 2012-11-07 09:38
21 | 3582187 |  | OASIS: Applicability - remove reference to module Individual | The MD project is still using the module of the template Individual but it has been removed. | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 10:28 | 2012-10-31 10:30
22 | 3582200 |  | OASIS: FleetItem - create | Need a template to represent an item in a Fleet | Accepted The description should make it clear that the item is member of a fleet. I.e. "The FleetItem template describes how to represent an item (usually a product) that is a member of a fleet of items" | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 11:11 | 2012-10-31 06:41
23 | 3582264 |  | OASIS: Collection - add "names" | Add "names" property to template Collection | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-10-31 04:40 | 2012-10-31 04:56
24 | 3584953 |  | OASIS: MissionItem - Create | Need a template to represent an item in a mission to track when the item was in the mission and when it was not. Will be using ActivityAssignment with effectivity. | Accepted Change description to state that something has a role within a mission. I.e. "The MissionItem template describes how to represent an item that has a role in a mission. It enables the tracking of when as item was part of the mission and when it was not" | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-11-07 03:23 | 2012-11-07 05:27
25 | 3585352 |  | OASIS: PartAssembly - create | Need a template to represent: parent/child relationship (represented as a NextAssemblyUsage classified as "PartAssembly") of PartViewDefinition(s), with effectivity, quantity, locationIndicator properties | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-11-08 08:55 | 2012-11-10 10:40
26 | 3585353 |  | OASIS: RealizedPartAssembly - create | Need a template to represent a parent/child relationship (represented as a NextAssemblyUsage classified as "RealizedPartAssembly") where the parent is always ProductAsIndividualView, the child could be either a PartViewDefinition or a ProductAsIndividualView, with effectivity, quantity, locationIndicator properties NB: Potentially this template could also have an optional promisoryUsage property to represent the intend usage of the child in a upper RealizedPart - i.e. EndProduct - (but that last one could be a template in itself) | Accepted | 5 | Pending | Remind |  | phoubaux | phoubaux | phoubaux | 2012-11-08 08:57 | 2012-11-08 12:00
27 | 3585779 |  | OASIS:SystemElement - incorrect part property | Property sysBreakdown : SystemBreakdown is a Part property It should be a Reference property | Accepted | 5 | Pending | Remind |  | robbod | nobody | robbod | 2012-11-09 03:52 | 2012-11-09 04:23

## PLCS PSM
Tracker: PLCS PSMmodel
Export date: 2012-11-12 02:58:53
CCB Meeting: 2012-11-12
Row | Id | Category | Summary | Details | CCB decision | Priority | Status | Resolution | Release | Submitter | Assignee | Closer | Date raised | Date Closed
1 | 3586167 | PLCS PSM Model | ConditionRelationship not required | I do not think that ConditionRelationship is required. Its definition is: A ConditionRelationship is a relation between two conditions. NOTE The ConditionRelationship normally represents a logical combination of conditions. The logical type is identified by the classification of the ConditionRelationship by an ExternalOwlClass. EXAMPLE "If the engine has been running for 10000 hours AND the engine is fitted with a clog-up-quick Oil filter then change the oil filter" is an example of two conditions related by a logical AND. Right now the ConditionRelationship is used as condition parameters to a conditions It is not possible to have a Condition as a condition parameters to a condition So you have to use ConditionRelationship to represent complex logical conditions. It would be much simpler if a condition could be the input parameter to a Condition - not the ConditionRelationship This would make it more straightforward to represent boolean logic and remove ambiguity between Condition and ConditionRelationship In fact this would make Condition reflect standard programming If/Then Else constructs If I need to represent: IF A AND B THEN I can either represent this with one condition classified as an AND condition with A and B condition parameters OR I can either represent this with Three conditions. One condition with A as condition parameter and the other condition with B as condition pararmeter. These two conditions are related by a ConditionRelationship classified as an AND relationship, the ConditionRelationship is then the condition parameter to the third condition. I propose changing the definition of the ConditionRelationship to make it clear that is just a relationship. I.e. delete the NOTE Removing ConditionRelationship from ConditionParameterSelect and ConditionEvaluationParameterSelect Adding Condition to ConditionParameterSelect and ConditionEvaluationParameterSelect Changing the reference data so that the condition is classified NOT the ConditionRelationship | Accepted | 5 | Open | Remind |  | robbod | robbod | nobody | 2012-11-11 07:50 | 1970-01-01 12:00
2 | 3582235 |  | Missing characterization of Environment Assignments | The environment blocks have not been fully characterized in AP239ed2 The following Blocks: EnvironmentAssignment, EnvironmentViewDefinitionRelationship, ObservedEnvironmentAssignment, ObservedEnvironmentToDefinition, ObservedEnvironmentToDefinitionVersion, ObservedEnvironmentToDefinitionView, ObservedEnvironmentViewDefinitionRelationship, ObservationAssignment, should be added to the select below: ApprovalAssignmentSelect, CollectionMemberSelect, ConditionEvaluationAssignmentSelect ConditionEvaluationParameterSelect ConditionAssignmentSelect ConditionParameterSelect DateTimeAssignmentSelect DocumentAssignmentSelect EffectivityAssignmentSelect EvidenceSelect JustificationAssignmentSelect ObservationAssignmentSelect OrganizationOrPersonInOrganizationAssignmentSelect RequirementSourceSelect RiskPerceptionSourceAssignmentSelect SecurityClassificationAssignmentSelect TimeIntervalAssignmentSelect WorkRequestAssignmentSelect | Accepted | 5 | Pending | Remind |  | robbod | nobody | robbod | 2012-10-31 02:29 | 2012-11-12 06:43
3 | 3582248 | PLCS PSM Model | SecurityClassificationAssignmentSelect shoudl contain produc | SecurityClassificationAssignmentSelect should contain product, productversion, productviewdefnition, observation | Accepted | 5 | Pending | Remind |  | robbod | robbod | robbod | 2012-10-31 03:46 | 2012-11-12 06:42
4 | 3582287 | PLCS PSM Model | Extend Select: EffectivityAssignmentSelect | Add the following to EffecitivtyAssignmentSelect: - CollectionMembership - CollectionAssignment | Accepted | 5 | Pending | Remind |  | phoubaux | robbod | robbod | 2012-10-31 06:31 | 2012-11-12 06:42
Accepted