## OASIS TC
OASIS PLCS TC Work Programme and Resources
OASIS PLCS TC Tasks and Resources
PLCS Organization Entity | Membership | Major Responsibility | Subtasks for Major Responsibilities | Resources | Sponsor Company
OASIS TC |  |  |  | Chair Secretariat One voting member from each company Technical Lead Implementers Forum Lead DEX Lead reports to TC | BAESystems Det Norse Veritas Eurostep AB Lockheed-Martin LSC Group Ltd ManTech Enterprise Integration Center (e-IC) Norwegian Defence Logistics Organization Pennant International Group plc Rolls-Royce plc Saab AB Swedish Defence Materiel Administration The Boeing Company UK Ministry of Defence Technical Information US Department of Defense (DoD)
| Co-Chair |  |  | Howard Mason | BAESystems
| Co-Chair |  |  | Jerry Smith | US Department of Defense (DoD)
| Secretariat |  |  | Chris Kreiler | ManTech - Funded by US DoD
| Det Norse Veritas |  |  | Nils Sandsmark | Det Norse Veritas
| Eurostep AB |  |  | Nigel Shaw | Eurostep AB
| Lockheed-Martin |  |  | ?? | Lockheed-Martin
| LSC Group Ltd |  |  | Steve Foster? | LSC Group Ltd
| Norwegian Defence |  |  | Tor Arne Irgens | Norwegian Defense Logistics
| Pennant |  |  | John Spencer | Pennant International Group plc
| Rolls-Royce |  |  | Nigel Walker | Rolls-Royce plc
| Saab AB |  |  | Carl Johan Wilen | Saab AB
| Swedish Defense |  |  | Mats Elgh | Swedish Defence Materiel Administration
| Boeing |  |  | King Yee | The Boeing Company
| UK MOD |  |  | Phil Rutland | UK Ministry of Defence Technical Information
| Technical Lead Information Architect) |  |  | Tor Arne Irgens
| Implementers Forum Lead |  |  | Nigel Shaw Trine Hansen
| Quality Assurance Lead |  |  | Nigel Shaw Trine Hansen
Monitor and Maintain AP239
Implement change programme
|  |  | Monitor SC4 modules for input on AP239 | Tim King | LSC Group Ltd
Submission of change requirements to SC4
PLCS TC Administration
Meetings and conference calls
Identify potential future DEXs
OASIS exploders
OASIS PLCS TC Website
Administration of DEXs, capabilities, reference data, documentation tool through the ballot process
Balloting within PLCS TC
Rules for approval of methods
Agree process for review / ballot / update / maintenance of technical documentation
Review DEXs and Reference Data submitted for OASIS standards
PLCS TC balloting, OASIS balloting, publishing and regular reporting to OASIS members
Publishing within OASIS
Procedures for publishing - Agree with OASIS how the DEXs are to be published, i.e. what format - Agree with OASIS how to publish Reference data
Publish - DEXs as OASIS standards - Core PLCS Reference Data - Business domain extensions as standardized extensions to PLCS Reference Data
PLCS TC Work Programme Management
Agreed programme of work
Establish resource requirement
Agreed prioritization of tasks and resources
Agreed allocation of programme tasks
Establish and maintain a detailed project plan
Manage activities described in the project plan - Recommend additional activities - Identify actions relevant for the OASIS TC scope
Track progress
Communications
SC4 AP239 relevant working groups
OASIS PLCS Teams
Implementers Forum
Pilots/Projects
Marketing
Promotion
Maintain library of success stories
Maintain library of presentations for PLCS member reference
Outreach needed to spread word on PLCS value

## Technical
OASIS PLCS TC Work Programme and Resources V001
PLCS TC Technical Oversight, DEX Teams, and Infrastructure/Tool Team Tasks and Resources
PLCS Organization Entity | Membership | Major Responsibility | Subtasks for Major Responsibilities | Resources | Membership
Technical Oversight
| Information Architect |  |  | Tor Arne Irgens | Information Architect
| Tool Expert (Infrastructure) |  |  | Rob Bodington | Tool Expert (Infrastructure)
| Tool Expert |  |  | Mats Nilsson | Tool Expert
| Modeler |  |  | Tim Turner | Modeler
| Business Expert (Project Manager - Status tracking and reporting) |  |  | Chris Kreiler | Business Expert (Project Manager - Status tracking and reporting)
| Quality Leaders |  |  | Nigel Shaw Trine Hansen | Quality Leaders
| Implementers Forum Lead |  |  | Nigel Shaw Trine Hansen | Implementers Forum Lead
| Business Expert |  |  | Nigel Newling | Business Expert
| Business Expert |  |  | Phil Rutland | Business Expert
# | Activity | Main activities and Sub-activities [hours] | Comments | Resource Name | Sponsor Company
A1 | DEXLib infrastructure | 1412 | Support for development of Business Concepts High priority | Rob Bodington | Eurostep (360 hrs UK MOD funding, rest unfunded)
| Tool to manage configuration of DEXs and Capabilities |  | included in DEXLib infrastructure hours
Develop the DEXLib architecture and a framework explanation
Enhance user friendliness
Indexing mechanism - From the Business Concepts to DEX capabilities - From terminology dictionary to DEXLib
Extend existing DEXLib functionality to activate and complete scripts with information
A2 | Help files | 124
A2.1 | Add definition refined architecture to help/introduction | 10 |  | Trine Hansen | DNV
A2.1.1 | Descriptions on exchange contracts | 10 |  | Trine Hansen | DNV
A2.1.2 | Description of DEXs | 8 |  | Trine Hansen | DNV
A2.1.3 | Description of capabilities | 8 |  | Trine Hansen | DNV
A2.1.4 | Description on business concepts | 8 |  | Trine Hansen | DNV
A2.2 | Add general usage section | 4 |  | Rob Bodington | Eurostep (Eurostep funding)
A2.2.1 | Explaining use of classification | 16 |  | Rob Bodington | Eurostep (Eurostep funding)
A2.2.2 | Explaining use of identification | 20 |  | Rob Bodington | Eurostep (Eurostep funding)
A2.2.3 | Explaining use of IGNORE etc. as attribute values | 20 |  | Rob Bodington | Eurostep (Eurostep funding)
A2.2.4 | Add a select population matrix | 20 |  | Rob Bodington | Eurostep (Eurostep funding)
| Need Team Leader and resources for updating DEX Help and Guides |  |  | Mats Nilsson TBD UK MOD | FMV UKMOD
| Review structure of DEX Help |  |  | All members
| Ø Update on Development Guide. Include appropriate reference data guidance, format and content for documentation, rules, guidelines, Capabilities, Data Exchange Sets, mapping, testing, Business concepts, and Conformance Guidance/Requirements |  |  | Mats Nilsson | FMV
Ø Expand the introduction to DEXLib
| Ø Guidance on How to Start a DEX |  |  | Mats Nilsson Chris Kreiler Howard Mason | FMV
| Ø Guide on how to “Launch a DEX” |  |  | Mats Nilsson Chris Kreiler Howard Mason | FMV
| Ø Guide on how to write the XML for a DEX (dtds) |  |  | Tim Turner? | LSC Group, Ltd
| Ø Process for developing DEX and Capabilities |  |  | Tor Arne Irgens? | Norwegian Defense
| Ø Need review of Development Guide for Reference Data |  |  | All members for review; editor - DNV | All
| Ø FAQs |  |  | All members for review, editor - Mats Nilsson | All
| Ø Guides for review and test |  |  | Trine Hansen Tor Arne Irgens | DNV Norwegian Defense
| Ø Checklist for review of DEXs |  |  | Leif Gyllstrom Trine Hansen | FMV DNV
| Ø Update HTML |  |  | Rob Bodington Nik Barron | Eurostep (Eurostep funding) Pennant
| Ø Update Checklist for reference data review |  |  | DNV
Ø Develop templates for main rule types
Ø Develop scripts for business concepts, using rule templates
| Ø Update Capability Checklist for new architecture |  |  | Leif Gyllstrom | FMV
A3 | Test data | ???
A3.1 | Define the test data (exemplar) |  |  | Quality Assurance team
| Harmonize, update, and extend bike test data in S1000D format and compliance |  |  | Saab UKMOD Mike Day - RR?
| Need tool for test data development and viewing (create, review and validate part 21 and part 28 files) |  |  | Note: Eurostep to provide proposal for tool options
A4 | Content | 662
A4.1 | Review the core capabilities | 400 | High priority | Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | BAESystems LSC Group, Ltd Eurostep (UK MOD funding) FMV DNV
A4.2 | Develop missing core capabilities | 20 | High priority | Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | BAESystems LSC Group, Ltd Eurostep (UK MOD funding) FMV DNV
A4.3 | Develop an example business concept for the implementations to use | 10 | High priority | Leif Gyllstrom
A6 | Reference data | 96
A6.1 | Harmonize modelers ref data | 96 | 4 modelers 3 days workshop | Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | BAESystems LSC Group, Ltd Eurostep (no funding) FMV DNV
A6.2 | Review initial baseline of ref data | 40 |  | Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | BAESystems LSC Group, Ltd Eurostep (no funding) FMV DNV
A6.3 | Reuse Ref Data from 15926 |  | Future Convergence
Provide Technical Oversight for DEX, Capability, and Reference Data Development
Administer the Technical Development work programme
Establish API for PLCS
Establish mechanisms for approval and publication of business concepts reflecting business terms and mapping into DEXs
Agree how Reference Data will be published and maintained
Maintain development documentation guidance
Format and content
Rules
Guidelines
Capabilities, Data Exchange Sets, and Reference Data
Mapping
Testing and Test documentation
Business Concepts
Conformance Guidance/Requirements
Establish and maintain usage documentation guidance
Business user guidance
Software implementer guidance including translators
Contract managers guidance
Review DEXs, capabilities, and reference data
Reduce duplicate development and improve interoperability
Ensure submissions meet OASIS ballot requirements
Harmonization within PLCS TC of - Reference Data - Interpretations / mapping solutions - Translators - Mappings - Projects
Impact of SC4 module changes on DEXs
Harmonize with established SC4 and related standards
Harmonization with SC4 standards - 10303 STEP APs - 13584 PLIB - 15926 Oil & Gas
Harmonization with other standards - ASD (AECMA) 1000D and 2000M - MIP - OAGIS 9 - OMG - SCORM - UK MOD 00-60 - W3C
DEX Teams
Team Lead
Modeler
Business Expert
Other stakeholders
PLCS DEXs
No | ID | Name | Project Leader | Editor | Allocated Model Reviewer | Allocated Business Reviewer
D001 | product_breakdown_for_support | Product Breakdown for Support | Nigel Walker | Tim Turner | Trine Hansen (Norwegian Pilot) Eurostep Sweden (Eurostep funding ) | Gordon Robb
D002 | fault_states | Faults related to product structures | Adrian Blenkiron | Leif Gyllström | John Spencer | Mats Nilsson
D003 | task_set | Task Set | Phil Rutland | Sean Barker Leif Gyllstrom | Nigel Shaw (Eurostep funding) | Nigel Newling
D004 | work_package_definition | Work Package Definition | Nigel Newling | Tim King | Nigel Shaw (Eurostep funding) Rob Bodington | Carolyn Cox
D005 | maintenance_plan | Maintenance plan | Leif Gyllström | Leif Gyllström | Tom Hendrix? | BAESystems?
D007 | operational_feedback | Operational Feedback | Les Debenham or UKMOD? | Rob Bodington (limited Eurostep funding)
D008 | product_as_individual | Product as Individual | Robert "Mike" McBride | Tim Turner | Tim King? Tom Hendrix? | Nigel Newling? Mats Nilsson?
D009 | work_package_report | Work Package Report | Nigel Newling | Tim King | Nigel Shaw (Eurostep funding) Rob Bodington | Carolyn Cox
D010 | systems_requirements | System Requirements | Phil Spiby (Eurostep/VIVACE funded) | Phil Spiby (Eurostep/VIVACE funded) | Stefan Lindhal (Eurostep/VIVACE funded) | Mats Lindeblad (Volvo Aero)
PLCS Capabilities
No | ID | Project Leader | Editor | Allocated Model Reviewer | Allocated Business Reviewer |  | D001 : Product Breakdown for Support | D002 : Faults related to product structures | D003 : Task Set | D004 : Work Package Definition | D005 : Maintenance plan | D007 : Operational Feedback | D008 : Product as individual | D009 : Work Package Report | D010 : Equipment and Part list
C001 | assigning_identifiers | Nigel Walker | Tim Turner | Modelers CORE Team | Gordon Robb |  | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes
C002 | representing_parts | Nigel Walker | Tim Turner | Tom Hendrix Norwegian Pilot | Norwegian Pilot |  | Yes
C003 | representing_assembly_structure | Nigel Walker | Tim Turner | Tom Hendrix Norwegian Pilot | Gordon Robb Norwegian Pilot |  | Yes
C004 | representing_breakdown_structure | Nigel Walker | Tim Turner | Tom Hendrix Norwegian Pilot | Gordon Robb Norwegian Pilot |  | Yes | [5 empty] | Yes
C005 | representing_documents | Nigel Walker | Tim Turner | Tom Hendrix Norwegian Pilot | Gordon Robb Norwegian Pilot |  | Yes |  |  | Yes |  | Yes | Yes | Yes
C006 | assigning_effectivity | Nigel Walker | Tim Turner | Norwegian Pilot | Gordon Robb Norwegian Pilot |  | Yes |  |  |  |  | Yes | Yes
C007 | representing_state_type | Adrian Blenkiron | Leif Gyllström | Nigel Shaw (Eurostep funding) | Johan Carlson? |  |  | Yes |  | Yes | Yes | Yes | Yes
C008 | referencing_part_or_slot | Leif Gyllström | Leif Gyllström | Tom Hendrix | Les Debenham |  |  | Yes |  | Yes | Yes | Yes | Yes
C009 | referencing_product_breakdown_element | Adrian Blenkiron | Leif Gyllström | Swedish Pilot | Johan Carlson |  |  | Yes |  | Yes | Yes | Yes | Yes | Yes
C010 | assigning_reference_data | Adrian Blenkiron | Leif Gyllström | Modelers CORE Team | Norwegian Pilot |  | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes
C011 | representing_analysis_result | Adrian Blenkiron | Leif Gyllström | Rob Bodington (Eurostep funding) | Les Debenham |  |  | Yes |  |  | Yes | Yes
C012 | referencing_task | UKMOD TBD | Sean Barker | Leif Gyllström | Nigel Newling |  |  |  | Yes |  | Yes
C013 | representing_probability | UKMOD TBD | Sean Barker | Tom Hendrix | Adrian Blenkiron
C014 | messaging | UKMOD TBD | Sean Barker | Modelers CORE Team | Norwegian Pilot |  | Yes |  |  |  |  | Yes | Yes
C015 | representing_task | UKMOD TBD | Sean Barker | Nigel Shaw (Eurostep funding) | John Spencer |  |  |  | Yes | Yes
C016 | representing_person_organization | Nigel Newling | Trine Hansen | Modelers CORE Team | Norwegian Pilot |  | Yes |  |  | Yes |  |  | Yes | Yes
C019 | assigning_approvals | Nigel Newling | Mike Ward (no funding) | Tim Turner | Nigel Walker |  | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes
C020 | representing_life_cycle_opportunity | Nigel Newling | Nigel Newling | Nigel Shaw (Eurostep funding) | UKMOD TBD |  |  |  |  | Yes
C021 | requesting_and_ordering_work | Nigel Newling | Ian Hickman | - | -
C022 | representing_work_package | Nigel Newling | Nigel Newling | Rob Bodington (Eurostep funding) | UKMOD TBD | [8 empty] | Yes
C024 | report_activity_progress | Nigel Newling | Ian Hickman | - | - | [8 empty] | Yes
C025 | assigning_observation | Nigel Newling | Mike Ward | Sean Barker | Les Debenham | [6 empty] | Yes
C026 | representing_condition | Leif Gyllström | Leif Gyllström | Tom Hendrix | Swedish Pilot |  |  | Yes |  | Yes | Yes | Yes
C027 | representing_location | Nigel Newling | Nigel Newling | Rob Bodington (no funding) | Andy Burden (UKMOD) |  |  |  |  | Yes |  | Yes
C032 | representing_activity | UKMOD TBD | Rob Bodington (no longer funded) | Trine Hansen | Nigel Newling |  |  |  |  | Yes |  | Yes |  | Yes
C036 | assigning_date_time | Leif Gyllström | Trine Hansen | Modelers CORE Team | Nigel Newling |  | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes
C037 | referencing_documents | Leif Gyllström | Trine Hansen | Tim King | Carolyn Cox |  |  | Yes |  | Yes | Yes | Yes | Yes
C041 | representing_state_observed | UKMOD TBD | Rob Bodington (no longer funded) |  | Tor Arne Irgens |  |  |  |  | Yes |  | Yes | Yes | Yes
C043 | representing_environment_typical | UKMOD TBD | Rob Bodington (no longer funded) | Leif Gyllström | Swedish Pilot |  |  | Yes |  |  | Yes | Yes
C044 | representing_environment_actual | UKMOD TBD | Rob Bodington (no longer funded) | Leif Gyllström | Johan Carlson? | [6 empty] | Yes
C045 | representing_product_as_individual | UKMOD TBD | Rob Bodington (no longer funded) | Tom Hendrix | Nigel Newling
C046 | representing_variance | Nigel Newling | Rob Bodington (no longer funded) | Ian Hickman | Gordon Robb |  |  |  |  | Yes |  | Yes | Yes | Yes
C048 | representing_condition_evaluated | UKMOD TBD | Rob Bodington (no longer funded) | Tom Hendrix | Johan Carlson? | [6 empty] | Yes
C049 | representing_product_location | UKMOD TBD | Rob Bodington (no longer funded) | Nigel Newling | Johan Carlson? | [6 empty] | Yes
C050 | referencing_resource | UKMOD TBD | Mike Ward (no longer funded) | Sean Barker | John Spencer |  |  |  |  | Yes
C051 | representing_person_organization_typical | UKMOD TBD | Mike Ward (no longer funded) | Sean Barker | Swedish Pilot
C052 | representing_resource | UKMOD TBD | Mike Ward (no longer funded) | Sean Barker | John Spencer | [8 empty] | Yes
C053 | representing_periodicity | Adrian Blenkiron | Leif Gyllström | Tom Hendrix | Swedish Pilot | [5 empty] | Yes
C055 | representing_project_information | Adrian Blenkiron | Leif Gyllström | Nigel Newling | Tor Arne Irgens |  |  |  |  | Yes
C056 | representing_evolution_of_property_values | Robert "Mike" McBride | Tom Hendrix | Albert Leyson | Les Debenham
C057 | referencing_product_configuration | Leif Gyllström | Leif Gyllström | Tor Arne Irgens | Nigel Walker |  |  | Yes |  | Yes | Yes |  | Yes
C058 | representing_justification | UKMOD TBD | Rob Bodington (no longer funded) | Nigel Newling | Johan Carlson? |  |  |  |  | Yes |  | Yes |  | Yes
C059 | representing_work_output | Nigel Newling | Sean Barker | Rob Bodington (Eurostep funding) | Eurostep (Eurostep funding)
C060 | referencing_product_as_individual | UKMOD TBD | Rob Bodington (no longer funded) | Leif Gyllström | Gordon Robb | [6 empty] | Yes
C061 | referencing_scheme | Nigel Newling | Sean Barker | Nigel Shaw | Tor Arne Irgens
C062 | representing_scheme | Nigel Newling | Sean Barker | Nigel Shaw | Tor Arne Irgens |  |  |  |  | Yes
C063 | representing_product_configuration | UKMOD TBD | Rob Bodington (no longer funded) | Tim Turner | Trine Hansen Gordon Robb |  | Yes
C064 | representing_work_done | UKMOD TBD | Rob Bodington (no longer funded) | Tim King | Nigel Newling Norwegian Pilot | [6 empty] | Yes
C065 | representing_work_order | UKMOD TBD | Rob Bodington (no longer funded) | Tim King | Nigel Newling Norwegian Pilot |  |  |  |  | Yes |  | Yes
C066 | representing_work_request | UKMOD TBD | Rob Bodington (no longer funded) | Tim King | Nigel Newling Norwegian Pilot |  |  |  |  | Yes |  | Yes
C067 | representing_product_as_individual_configuration | UKMOD TBD | Rob Bodington (no longer funded) | Tom Hendrix | Nigel Newling
C068 | referencing_product_as_individual_configuration | UKMOD TBD | Rob Bodington (no longer funded) | Tom Hendrix | Nigel Newling | [6 empty] | Yes
C069 | referencing_activity | UKMOD TBD | Rob Bodington (no longer funded) | Trine Hansen | Nigel Newling |  |  | Yes
C070 | referencing_person_organization_typical | UKMOD TBD | Mike Ward (no longer funded) | Sean Barker | Swedish Pilot
C071 | referencing_work_order | UKMOD TBD | Rob Bodington (no longer funded) | Tim King | Nigel Newling Norwegian Pilot
C072 | referencing_work_request | UKMOD TBD | Rob Bodington (no longer funded) | Tim King | Nigel Newling Norwegian Pilot
C073 | representing_information_controls | Eurostep | Sean Barker | Tom Hendrix | Howard Mason
C074 | referencing_person_organization | Nigel Newling | Leif Gyllström | Tom Hendrix | Norwegian Pilot |  |  | Yes |  | Yes | Yes | Yes
C075 | referencing_project | Adrian Blenkiron | Leif Gyllström | Nigel Newling | Tor Arne Irgens |  |  | Yes |  |  | Yes
C076 | assigning_product_properties | UKMOD TBD | Mike Ward (no longer funded) | Tom Hendrix | Norwegian Pilot |  | Yes | Yes |  | Yes | Yes | Yes | Yes
C077 | assigning_process_properties | UKMOD TBD | Mike Ward (no longer funded) | Tom Hendrix | Norwegian Pilot |  |  |  |  | Yes | Yes | Yes
C078 | assigning_resource_properties | UKMOD TBD | Mike Ward (no longer funded) | Tom Hendrix | Norwegian Pilot | [6 empty] | Yes
C079 | representing_properties_numerically | UKMOD TBD | Mike Ward (no longer funded) | Tom Hendrix | Norwegian Pilot |  | Yes | Yes |  | Yes | Yes | Yes | Yes
C080 | representing_properties_textually | UKMOD TBD | Mike Ward (no longer funded) | Tom Hendrix | Norwegian Pilot |  | Yes | Yes |  | Yes | Yes | Yes | Yes
C081 | representing_product_as_realized_assembly | UKMOD TBD | Tom Hendrix | Tim King Tom Hendrix | Nigel Newling Mats Nilsson | [7 empty] | Yes
C082 | referencing_contract | Norwegian Pilot | Norwegian Pilot | Error 1: No contact provided for reviewer. | Tor Arne Irgens
C083 | representing_contract | Norwegian Pilot | Norwegian Pilot | Error 1: No contact provided for reviewer. | Tor Arne Irgens
C084 | representing_property_value_ranges | Nigel Walker | Tom Hendrix | Tim Turner | Les Debenham |  |  | Yes |  |  |  | Yes
C085 | representing_resource_as_realized | UKMOD TBD | Mike Ward (no longer funded) | Sean Barker | Swedish Pilot | [6 empty] | Yes
C086 | representing_slots | Nigel Walker | Tim Turner | Tom Hendrix | Gordon Robb
C087 | assigning_document_properties | Nigel Walker | Tim Turner | Tom Hendrix | Norwegian Pilot |  | Yes | [5 empty] | Yes
C088 | representing_task_structure | UKMOD TBD | Sean Barker | Nigel Shaw (Eurostep funding) | John Spencer
C089? | representing_task_and_state | UKMOD TBD | Sean Barker | Nigel Shaw (Eurostep funding) | John Spencer
C090 | representing_task_associations | UKMOD TBD | Sean Barker | Nigel Shaw (Eurostep funding) | John Spencer
C091 | representing_description | Modelers CORE Team | Modelers CORE Team | Modelers CORE Team | Norwegian Pilot
??? | representing_codes | Modelers CORE Team | Leif Gyllström | Modelers CORE Team | Norwegian Pilot
| representing_requirements | Phil Spiby (Eurostep funded) | Phil Spiby | Stefan Lindahl (Eurostep) | Mats Lindeblad (Volvo Aero)
Develop Capabilities
Develop new capabilities as required
Set up a review structure for capabilities
Develop DEX Packages
Develop DEX Documentation - Develop Implementation options - Capabilities - Business Concepts - DEX Documentation - Reference data - Prune long forms
Initial testing using DEX developed test data
Re-develop initial set of DEXs i.a.w. common agreements
Incorporate new Reference Data
Develop Reference Data
Develop reference data
Propose reference data from pilot sources
Publish reference data
Link with other standards
Develop a programme to monitor the resolution of ballot comments
Develop Rules
Infrastructure / Tool Team
Information Architect from Technical Oversight
Tool Expert (Infrastructure)
Maintain DEXLib Infrastructure
Continue to maintain DEXLib on Source Forge - Maintain an HTML mirror of DEXLib for non- developers - Allow an XML view facility in browsers (other than Internet Explorer) - Extend DEXLib to allow HTML publications - Extend DEXLib to allow individual (or sets of) DEXs to be published as a standalone package electronically and on paper
DEX specification template
Develop an agreed DEX template for acceptance by OASIS based on the example DEX “Assembly part list” to DEXLib
Reference Data Library Infrastructure
Establish and maintain a PLCS web server
Develop Pilot RDL service
Agree and standardize RDL services
Develop industrial strength RDL services
Define management of RDL services
Publish OWL files on the PLCS Web server
Establish PLCS RDL server accessed via APIs from translators
Establish a better development environment for reference data consolidation and management
User-friendly interface to reference data library from DEXLib
DEXLib Tools
|  |  | Tool plus processes for Work Progress tracking in DEXLib | Mats Nilsson
Tool for converting existing Part 28 file to/from Part 21 file
Note on C29: Rob Bodington: These hours are underestimates
Note on C34: Rob Bodington: These hours are overestimates
Note on C62: Rob Bodington: Increased
Note on E61: Rob Bodington: Assumed 10 days per modeler
Note on E129: Rob Bodington: Clarified funding)
Note on E142: Rob Bodington: Clarified funding)
Note on F22: Rob Bodington: Should be UK-MOD We are not providing all funding

## Quality_Implementers
OASIS PLCS TC Work Programme and Resources
PLCS TC Quality Assurance, Implementers Forum, and Pilots Organization, Tasks and Resources
PLCS Organization Entity | Membership | Major Responsibility | Subtasks for Major Responsibilities | Resources
Quality Assurance
| Lead |  |  | Nigel Shaw (no funding) Trine Hansen
| Testers |  |  | DEX Team Testers
Establish Quality Framework
Review Framework for Quality
Editing and approval of DEXs
Establish and Liaison with Implementers Forum
Ensure submissions meet requirements for OASIS Balloting
Verify and Validate DEX Team Testing
Implementers Forum
| Lead |  |  | Nigel Shaw (no funding) Trine Hansen
| Software Product Vendors |  |  | Pilot Project Representatives
| Implementers |  |  | Pilot Project Representatives
Integrators
Review and recommend changes
Capabilities, DEXs, and Reference Data
Business concepts
Harmonization • Establish guidelines for the implementers • Raise harmonization issues and recommend changes for – Capabilities, DEXs, and Reference Data – Interpretations / mapping solutions – Mappings – Projects/pilots – Translators
Pilots
Norwegian Pilot
UK MOD Pilot
Swedish Pilot
Others
Establish DEX Development Teams under Technical Oversight
Establish Pilot Test runs with Implementers Forum
Development of non-OASIS documentation
Capabilities, DEXs, and Reference Data
Guidelines
Share results and lessons learned
Implementers Forum
OASIS TC
Other DEX Development Teams
Quality Assurance
Technical Oversight

## DEXLib Work Estimate
Secretariat Note: Work breakdown with man-hour estimates from Rob Bodington. This is a slightly different view from the Technical Work sheet, but the hours and content are the same. This provides a more detailed view.
Rob Bodington (No Suggestions) V006
DEXLib infrastructure |  | A1 | DEXLib infrastructure
| Estimated total for DEXLib tool development |  |  |  |  | Note - not all the work has been estimated.
| Task | Funded Hours | Funded Hours per task | Total Hours | Hours per task | Comments | Sponsor company
|  |  |  | 1412 | 1412
1 | Business concepts |  |  | 120
1.1 | Specify the layout and content of the Business concept |  |  |  | 40 | This needs to be done collaboratively and will provide a specification. The content will include how the business concept maps to capabilities, how the reference data to be used with the business concept is specified | UK-MOD TAF 42
1.2 | Modify DTD |  |  |  | 8 |  | UK-MOD TAF 42
1.3 | Develop scripts to build template for BC |  |  |  | 8 |  | UK-MOD TAF 42
1.4 | Update XSL to display BC |  |  |  | 24 |  | UK-MOD TAF 42
1.5 | Update XSL to provide indices of BC |  |  |  | 16 | The index should show what capabilities uses a business concept Show what business concepts are used by a capability | UK-MOD TAF 42
1.6 | Provide support for links between BC, capabilities and Ref data |  |  |  | 16 | This means syntax + XSL to define +display the reference between the BC and the ref data etc (may be able to reuse existing code) | UK-MOD TAF 42
1.7 | Provide a search mechanism for BCs |  |  |  | 0 | This would require a significant investment, so no hours quoted. | ?
1.8 | Add tool for editors to list the links to BC in xml for pasting into text |  |  |  | 8 |  | UK-MOD TAF 42
1.9 | Contingency |  |  |  | 0
2 | Capabilities |  |  | 224
2.1 | Define capability macros |  |  |  | 120 | Specify how to represent a capability macro - a macro defining the set of entities to be instantiated, the associated reference data and values for attributes on the entities. This will be passed to the macro as parameters. The macro is in effect a representation of the instance diagrams in text - this may well be just the mapping syntax from Apes. This needs to be done collaboratively and will provide a specification. The macro syntax should be used in a business concept definition to show how the business concept is defined using the capability macros | UK-MOD TAF 40
2.2 | Document the macro language |  |  |  | 40 | Document how to write the macros and its usage | UK-MOD TAF 40
2.3 | Modify capability DTD to include macro in capability |  |  |  | 8 | This means syntax + XSL to define + display the reference between the business concept and a capability macro, and between capability macros | UK-MOD TAF 40
2.4 | Modify capability XSL to display macro |  |  |  | 40 | XSL shall display the macro in the capability XSL shall validate that the macros is defined using valid EXPRESS and other valid macros Index of macros should be provided. | UK-MOD TAF 40
2.5 | Update the mk_capability script to add macro section |  |  |  | 4 |  | UK-MOD TAF 40
2.6 | Provide support for linking to subsections of a capability |  |  |  | 8 | This means syntax + XSL to define + display the reference between the business concept and a capability macro, and between capability macros | UK-MOD TAF 40
2.7 | Update capability to handle example data |  |  |  | 4 | Currently example instance data is not presented in a consistent way. Some capabilities just use instance diagrams, some provide Part 21 file fragments, none provide Part 28 file fragments. The DTD needs to be extended to allow for both part21 and part 28 fragments. Need to extend the DTD and XSL to make the type of the type of test data explicit | UK-MOD TAF 40
2.9 | Contingency
3 | Instance diagramming tool |  |  | 400
[5 empty] | 400 | Provide facility for drawing instance diagrams that include capability macros. This may just be an agreed VISIO template or may be a tool. The hours estimate are for a tool. The tool will: - enable the drawing on instance diagrams that include capability macros - generate hyperlinks between EXPRESS entities defining the Capabilities - list a library of capability macros - instantiating a capability macro graphically from the library - facility to output a P28 and P21 file Note - this is a rough estimate of the whole job | ?
4 | Rules |  |  | 0
4.1 | Define rules for capabilities & DEXs |  |  |  | 0 | Define how to represent the rules, both text based and formal rules. This needs to be done collaboratively and will provide a specification NOTE - I am not sure that this is required once we have implemented the capability macros
4.2 | Modify capability & DEX DTD to include rules |  |  |  | 0
4.3 | Modify capability & DEX XSL to display rules |  |  |  | 0
4.4 | Update the mk_capability script to add rules section |  |  |  | 0
4.5 | Update the mk_dex script to add rules section |  |  |  | 0
5 | DEXS |  |  | 72
5.1 | Define Conformance classes |  |  |  | 16 | Define how to specify a conformance class. This needs to be done collaboratively and will provide a specification. Estimate assumes that the SC4 approach used in modular AP will be adopted.
5.2 | Update the mk_dex script to add conformance section |  |  |  | 4
5.3 | Define DTD to accommodate conformance classes |  |  |  | 4
5.4 | Create XSL to display conformance classes |  |  |  | 8
5.5 | DEX test data |  |  |  | 24 | Add a section in the DEX to list/index the test data for testing the compliance/conformance of the DEX and the exchange. Note, it is assumed that test data is available.
5.6 | Define DTD to accommodate test data |  |  |  | 4
5.7 | Create XSL to display test data |  |  |  | 8 | Assuming a simple display - hyperlinks from instantiated entities will be require more effort.
5.8 | Update the mk_dex script to add test data section |  |  |  | 4
6 | Exchange contracts |  |  | 120
6.1 | Requirements analysis |  |  |  | 120 | Establish requirements for exchange contract. This should identify potentially what is the content of the exchange contract and how it might build on DEXLib. This should refer to the baseline of the DEXs, capabilities, modules
6.2 | Define exchange contract |  |  |  | 0 | Define how to specify an exchange contract. This needs to be done collaboratively and will provide a specification.
6.3 | Define the DTD for the exchange contract |  |  |  | 0
6.4 | Define mk_exchange_contract script |  |  |  | 0 | Mechanism for generating the exchange contract XML template
6.5 | Create XSL to display exchange contract |  |  |  | 0 | Mechanism for linking to a DEX conformance classes. Mechanism for linking to business concepts
6.6 | Develop standard text for exchange contract |  |  |  | 0 | This will require legal wording
7 | Configuration management of DEXLib |  |  | 336
7.1 | Define how the baseline of the DEX, capabilities, modules, AP, reference data, and business concepts is managed, identified and represented in an exchange contract |  |  |  | 80 | Note - this should be picked up in the test document
7.2 | Implement simple to use tool to create and view baselines |  |  |  | 200
7.3 | Document tool and baselining process |  |  |  | 40
7.4 | Maintain a released version of the modular AP |  |  |  | 16 | We need to extract a released version of the modules into DEXLib to ensure that the DEXs use controlled versions of modules. (The modules will be continuing being developed in STEPmod)
8 | Publication |  |  | 40
8.1 | Maintain a mirror site of DEXLib that provides HTML access |  |  |  | 16 | Pennant already provide a site- the scripts need to be updated to ensure that a complete build is done.
8.2 | Install a mirror of capabilities for review |  |  |  | 4
8.3 | Release of capabilities for review |  |  |  | 4
8.4 | DEX publication approach |  |  |  | 0 | OASIS TC to agree on what is to be published. A DEX, A capability, a suite of DEXs? This is a prerequisite
8.5 | Generate a version of the DEXs for OASIS review |  |  |  | 16 | At this stage, we are not sure whether the current form of a DEX will be acceptable to OASIS for publication. So generate one and see.
8.6 | Modify DEX structure for publication by OASIS |  |  |  | 0 | Make the changes requested by OASIS. Not this dependent on 8.5 and no estimate effort can be made until the initial DEX has been reviewed.
9 | Ref Data |  |  | 4
9.1 | Collaborative Ref Data development environment |  |  |  |  | This is to replace Protégé. This would require significant effort. Hence no effort estimated. | 0
9.2 | Embed a link to the reference |  |  |  |  | Enable a link between the XSL displaying the reference data and the RDL server so allow the browsing of the reference data from DEXLib. This requires the support / maintenance of the RDL server. Hence no effort estimated. | 0
9.3 | Facility to identify extensible / non extensible reference data |  |  |  | 4 | Mark ref data classes as "non" extensible. I.e. can not be extended by subclasses in business concepts
10 | Activity model |  |  | 80
10.1 | Provide index, navigable activity model integrated into DEXLib |  |  |  | 80 | Each DEX shows the sub set of the activity model. The full activity model should be navigable from here.
11 | General |  |  | 16
11.1 | Maintain a decision site |  |  |  | 8 | A page on DEXLib listing the main decisions
11.2 | Maintain an action list on DEXLib |  |  |  | 8 | Create an action list in DEXLib
Note on E10: Rob Bodington: Modified hours
Note on H8: Rob Bodington: Added this column

## Resource Confirmation
OASIS PLCS TC Work Programme and Resources by Name
OASIS PLCS TC Tasks and Resources
OASIS PLCS Technical Oversight Tasks and Resources
OASIS PLCS Quality Assurance and Implementation Tasks and Resources
Resource | PLCS Organization Entity | Membership | Sponsor Company | Confirmation | Comments
Howard Mason | OASIS TC | Voting Member BAESystems, PLCS TC Co-Chair | BAESystems
Nils Sandsmark | OASIS TC | Voting Member Det Norse Veritas | Det Norse Veritas
Trine Hansen | Technical Oversight | Implementers Forum Lead | Det Norse Veritas
Trine Hansen | Technical Oversight | Quality Leaders | Det Norse Veritas
Trine Hansen | Implementers Forum | Lead | DNV
Trine Hansen | Quality Assurance | Lead | DNV
Nigel Shaw | Technical Oversight | Implementers Forum Lead | Eurostep
Nigel Shaw | Technical Oversight | Quality Leaders | Eurostep
Nigel Shaw | OASIS TC | Voting Member Eurostep | Eurostep
Nigel Shaw (no funding) | Implementers Forum | Lead | Eurostep
Nigel Shaw (no funding) | Quality Assurance | Lead | Eurostep
Rob Bodington | Technical Oversight | Tool Expert (Infrastructure) | Eurostep
TB D | OASIS TC | Voting Member Lockheed-Martin | Lockheed-Martin
Nigel Newling | Technical Oversight | Business Expert | LSC Group Ltd
Steve Foster? | OASIS TC | Voting Member LSC Group Ltd | LSC Group Ltd
Tim King | OASIS TC | Monitor SC4 modules for input on AP239 | LSC Group Ltd
Tim Turner | Technical Oversight | Modeler | LSC Group Ltd
Chris Kreiler | Technical Oversight | Business Expert (Project Manager - Status tracking and reporting) | ManTech - Funded by US DoD | Confirmed | Contracted under US DoD
Chris Kreiler | OASIS TC | Voting Member ManTech, Secretariat | ManTech - Funded by US DoD | Confirmed | Contracted under US DoD
Tor Arne Irgens | Technical Oversight | Information Architect | Norwegian Defense Logistics Logistics
Tor Arne Irgens | OASIS TC | Voting Member Norwegian Defence | Norwegian Defense Logistics Logistics
John Spencer | OASIS TC | Voting Member Pennant International Group plc | Pennant International Group plc International Group plc
Nigel Walker | OASIS TC | Voting Member Rolls-Royce | Rolls-Royce plc
Carl Johan Wilen | OASIS TC | Voting Member Saab AB | Saab AB
Mats Elgh | OASIS TC | Voting Member Swedish Defense | Swedish Defence Materiel Administration
Mats Nilsson | Technical Oversight | Tool Expert | Swedish Defence Materiel Administration
King Yee | OASIS TC | Voting Member Boeing | The Boeing Company
Phil Rutland | Technical Oversight | Business Expert | UK Ministry of Defence Technical Information
Phil Rutland | OASIS TC | Voting Member UK MOD | UK Ministry of Defence Technical Information
Jerry Smith | OASIS TC | Voting Member, USDOD, PLCS TC Co-Chair | US Department of Defense (DoD)
Resource Name | Number | Activity/Task | Sponsor Company | Task Description | Hours per task estimate | Confirmation | Comments
All members | A2 Help Files | Review structure of DEX Help | All
All members for review, editor - Mats Nilsson | A2 Help Files | Ø FAQs | All
All members for review; editor - DNV | A2 Help Files | Ø Need review of Development Guide for Reference Data | All
Sean Barker | C012 Referencing Task - Editor | Capability Set Editor | BAESystems
Sean Barker | C013 Representing Probability - Editor | Capability Set Editor | BAESystems
Sean Barker | C014 Messaging - Editor | Capability Set Editor | BAESystems
Sean Barker | C015 Representing Task - Editor | Capability Set Editor | BAESystems
Sean Barker | C025 Assigning Observation - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C050 referencing resource - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C051 representing person organization typical - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C052 representing resource - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C059 representing work output - Editor | Capability Set Editor | BAESystems
Sean Barker | C061 referencing scheme - Editor | Capability Set Editor | BAESystems
Sean Barker | C062 representing scheme - Editor | Capability Set Editor | BAESystems
Sean Barker | C070 referencing person organization typical - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C073 representing information controls - Editor | Capability Set Editor | BAESystems
Sean Barker | C085 representing resource as realized - Business Reviewer | Capability Set Business Reviewer | BAESystems
Sean Barker | C088 representing task structure - Editor | Capability Set Editor | BAESystems
Sean Barker | C089 representing task and state - Editor | Capability Set Editor | BAESystems
Sean Barker | C090 representing task associations - Editor | Capability Set Editor | BAESystems
BAESystems TBD | D005 Maintenance Plan - Business Reviewer | DEX Business Reviewer | BAESystems
Howard Mason | A2 Help Files | Ø Guidance on How to Start a DEX | BAESystems
Howard Mason | A2 Help Files | Ø Guide on how to “Launch a DEX” | BAESystems
Howard Mason | C073 representing information controls - Business Reviewer | Capability Set Business Reviewer | BAESystems
Sean Barker | A4 Content A4.1 | Review the core capabilities | BAESystems | Modelers CORE Team High priority | 400
Sean Barker | A4 Content A4.2 | Develop missing core capabilities | BAESystems | Modelers CORE Team High priority | 20
Sean Barker | A6 Reference Data A6.1 | Harmonize modelers ref data | BAESystems |  | 4 modelers 3 days workshop
Sean Barker | A6 Reference Data A6.2 | Review initial baseline of ref data | BAESystems |  | 40
Sean Barker | D003 Task Set - Editor | DEX Editor | BAESystems
Sean Barker Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Sean Barker - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | BAESystems
Tom Hendrix | C002 Representing Parts - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C003 Representing Assembly Structure - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C004 Representing Breakdown Structure - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C005 Representing Documents - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C008 Referencing Part or SLot - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C013 Representing Probability - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C026 Representing Condiiton - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C045 representing product as individual - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C048 representing condition evaluated - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C053 representing periodicity - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C056 representing evolution of property values - Editor | Capability Set Editor | Boeing
Tom Hendrix | C067 representing product as individual configuration - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C068 referencing product as individual configuration - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C073 representing information controls - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C074 referencing person organization - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C076 assigning product properties - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C077 assigning product properties - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C078 assigning resource properties - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C079 representing properties numerically - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C080 representing properties textually - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C081 representing product as realized assembly - Editor | Capability Set Editor | Boeing
Tom Hendrix | C081 representing product as realized assembly - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C084 representing property value ranges - Editor | Capability Set Editor | Boeing
Tom Hendrix | C086 representing slots - Business Reviewer | Capability Set Business Reviewer | Boeing
Tom Hendrix | C087 assigning document properties - Business Reviewer | Capability Set Business Reviewer | Boeing
Tom Hendrix | D005 Maintenance Plan - Model Reviewer | DEX Model Reviewer | Boeing
Tom Hendrix | D008 Product as Individual - Model Reviewer | DEX Model Reviewer | Boeing
Albert Leyson | C056 representing evolution of property values - Model Reviewer | Capability Set Model Reviewer | DNV
DNV TBD | A2 Help Files | Ø Update Checklist for reference data review | DNV
Norwegian Pilot TBD | C??? representing codes - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C002 Representing Parts - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C002 Representing Parts - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C003 Representing Assembly Structure - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C003 Representing Assembly Structure - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C004 Representing Breakdown Structure - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C004 Representing Breakdown Structure - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C005 Representing Documents - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C005 Representing Documents - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C006 Assigning Effectivity - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C006 Assigning Effectivity - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C010 Assigning Reference Data - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C014 Messaging - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C016 Representing Person Organization - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C064 representing work done - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C065 representing work order - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C066 representing work request - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C071 referencing work order - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C072 referencing work request - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C074 referencing person organization - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C076 assigning product properties - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C077 assigning product properties - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C078 assigning resource properties - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C079 representing properties numerically - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C080 representing properties textually - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C082 referencing contract - Editor | Capability Set Editor | DNV
Norwegian Pilot TBD | C082 referencing contract - Project Leader | Capability Set Project Leader | DNV
Norwegian Pilot TBD | C083 representing contract - Editor | Capability Set Editor | DNV
Norwegian Pilot TBD | C083 representing contract - Project Leader | Capability Set Project Leader | DNV
Norwegian Pilot TBD | C087 assigning document properties - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C091 representing description - Model Reviewer | Capability Set Model Reviewer | DNV
Trine Hanse - Quality Assurance Team | A3 Test Data A3.1 | Define the test data (exemplar) | DNV |  | ???
Trine Hansen | A2 Help Files | Ø Guides for review and test | DNV
Trine Hansen | A2 Help Files | Ø Checklist for review of DEXs | DNV
Trine Hansen | A2 Help Files A2.1 | Add definition refined architecture to help/introduction | DNV |  | 10
Trine Hansen | A2 Help Files A2.1.1 | Descriptions on exchange contracts | DNV |  | 10
Trine Hansen | A2 Help Files A2.1.2 | Description of DEXs | DNV |  | 8
Trine Hansen | A2 Help Files A2.1.3 | Description of capabilities | DNV |  | 8
Trine Hansen | A2 Help Files A2.1.4 | Description on business concepts | DNV |  | 8
Trine Hansen | A4 Content A4.1 | Review the core capabilities | DNV | Modelers CORE Team High priority | 400
Trine Hansen | A4 Content A4.2 | Develop missing core capabilities | DNV | Modelers CORE Team High priority | 20
Trine Hansen | A6 Reference Data A6.1 | Harmonize modelers ref data | DNV |  | 4 modelers 3 days workshop
Trine Hansen | A6 Reference Data A6.2 | Review initial baseline of ref data | DNV |  | 40
Trine Hansen | C016 Representing Person Organization - Editor | Capability Set Editor | DNV
Trine Hansen | C032 Representing Activity - Model Reviewer | Capability Set Model Reviewer | DNV
Trine Hansen | C036 assigning date time - Editor | Capability Set Editor | DNV
Trine Hansen | C037 referencing documents - Editor | Capability Set Editor | DNV
Trine Hansen | C063 representing product configuration - Business Reviewer | Capability Set Business Reviewer | DNV
Trine Hansen | C069 referencing activity - Model Reviewer | Capability Set Model Reviewer | DNV
Trine Hansen (Norwegian Pilot) | D001 Product Breakdown for Support - Model Reviewer | DEX Model Reviewer | DNV
Trine Hansen Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Trine Hansen - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | DNV
Eurostep Sweden TBD (Eurostep funding ) | D001 Product Breakdown for Support - Model Reviewer | DEX Model Reviewer | Eurostep
Eurostep TBD | C073 representing information controls - Project Leader | Capability Set Project Leader | Eurostep
Eurostep TBD (Eurostep funding) | C059 representing work output - Business Reviewer | Capability Set Business Reviewer | Eurostep
Eurostep to provide proposal for tool options | A3 Test Data | Need tool for test data development and viewing (create, review and validate part 21 and part 28 files) | Eurostep |  | ???
Ian Hickman | C046 representing variance - Model Reviewer | Capability Set Model Reviewer | Eurostep
Mats Lindeblad (Volvo Aero) | C??? representing requirements - Model Reviewer | Capability Set Model Reviewer | Eurostep |  |  |  | Eurostep Volvo Aero
Mats Lindeblad (Volvo Aero) | D010 System Requirements - Business Reviewer | DEX Business Reviewer | Eurostep |  |  |  | Eurostep Volvo Aero
Mike Ward (no longer funded) | C019 Assigning Approvals - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C025 Assigning Observation - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C050 referencing resource - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C051 representing person organization typical - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C052 representing resource - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C070 referencing person organization typical - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C076 assigning product properties - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C077 assigning product properties - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C078 assigning resource properties - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C079 representing properties numerically - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C080 representing properties textually - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C085 representing resource as realized - Editor | Capability Set Editor | Eurostep
Nigel Shaw (Eurostep funding) | D003 Task Set - Model Reviewer | DEX Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | D004 Work Package Definition - Model Reviewer | DEX Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | D009 Work Package Report - Model Reviewer | DEX Model Reviewer | Eurostep
Nigel Shaw - Quality Assurance Team | A3 Test Data A3.1 | Define the test data (exemplar) | Eurostep |  | ???
Nigel Shaw | C061 referencing scheme - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw | C062 representing scheme - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C007 Representing State Type - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C015 Representing Task - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C020 Representing Life Cycle Opportunity - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C088 representing task structure - Business Reviewer | Capability Set Business Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C089 representing task and state - Business Reviewer | Capability Set Business Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C090 representing task associations - Business Reviewer | Capability Set Business Reviewer | Eurostep
Phil Spiby (Eurostep funded) | C??? representing requirements - Editor | Capability Set Editor | Eurostep
Phil Spiby (Eurostep funded) | C??? representing requirements - Project Leader | Capability Set Project Leader | Eurostep
Phil Spiby (Eurostep/VIVACE funded) | D010 System Requirements - Editor | DEX Editor | Eurostep
Phil Spiby (Eurostep/VIVACE funded) | D010 System Requirements - Project Leader | DEX Project Leader | Eurostep
Rob Bodington | A1 | DEXLib infrastructure | Eurostep | Support for development of Business Concepts High priority |  |  | Eurostep (360 hrs UK MOD funding, rest unfunded)
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.1 | Specify the layout and content of the Business concept | Eurostep | This needs to be done collaboratively and will provide a specification. The content will include how the business concept maps to capabilities, how the reference data to be used with the business concept is specified | 40 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.2 | Modify DTD | Eurostep |  | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.3 | Develop scripts to build template for BC | Eurostep |  | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.4 | Update XSL to display BC | Eurostep |  | 24 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.5 | Update XSL to provide indices of BC | Eurostep | The index should show what capabilities uses a business concept Show what business concepts are used by a capability | 16 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.6 | Provide support for links between BC, capabilities and Ref data | Eurostep | This means syntax + XSL to define +display the reference between the BC and the ref data etc (may be able to reuse existing code) | 16 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.8 | Add tool for editors to list the links to BC in xml for pasting into text | Eurostep |  | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.1 | Define capability macros | Eurostep | Specify how to represent a capability macro - a macro defining the set of entities to be instantiated, the associated reference data and values for attributes on the entities. This will be passed to the macro as parameters. The macro is in effect a representation of the instance diagrams in text - this may well be just the mapping syntax from Apes. This needs to be done collaboratively and will provide a specification. The macro syntax should be used in a business concept definition to show how the business concept is defined using the capability macros | 120 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.2 | Document the macro language | Eurostep | Document how to write the macros and its usage | 40 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.3 | Modify capability DTD to include macro in capability | Eurostep | This means syntax + XSL to define + display the reference between the business concept and a capability macro, and between capability macros | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.4 | Modify capability XSL to display macro | Eurostep | XSL shall display the macro in the capability XSL shall validate that the macros is defined using valid EXPRESS and other valid macros Index of macros should be provided. | 40 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.5 | Update the mk_capability script to add macro section | Eurostep |  | 4 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.6 | Provide support for linking to subsections of a capability | Eurostep | This means syntax + XSL to define + display the reference between the business concept and a capability macro, and between capability macros | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.7 | Update capability to handle example data | Eurostep | Currently example instance data is not presented in a consistent way. Some capabilities just use instance diagrams, some provide Part 21 file fragments, none provide Part 28 file fragments. The DTD needs to be extended to allow for both part21 and part 28 fragments. Need to extend the DTD and XSL to make the type of the type of test data explicit | 4 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A2 Help Files | Ø Update HTML | Eurostep |  |  |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2 | Add general usage section | Eurostep |  | 4 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.1 | Explaining use of classification | Eurostep |  | 16 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.2 | Explaining use of identification | Eurostep |  | 20 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.3 | Explaining use of IGNORE etc. as attribute values | Eurostep |  | 20 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.4 | Add a select population matrix | Eurostep |  | 20 |  | Eurostep (Eurostep funding)
Rob Bodington | A4 Content A4.1 | Review the core capabilities | Eurostep | Modelers CORE Team High priority Eurostep (UK MOD funding) | 400
Rob Bodington | A4 Content A4.2 | Develop missing core capabilities | Eurostep | Modelers CORE Team High priority Eurostep (UK MOD funding) | 20
Rob Bodington | A6 Reference Data A6.1 | Harmonize modelers ref data | Eurostep |  | 4 modelers 3 days workshop |  | Eurostep (No funding)
Rob Bodington | A6 Reference Data A6.2 | Review initial baseline of ref data | Eurostep |  | 40 |  | Eurostep (No funding)
Rob Bodington | D004 Work Package Definition - Model Reviewer | DEX Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | C011 Representing Analysis Result - Model Reviewer | Capability Set Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | C022 Representing Work Package - Model Reviewer | Capability Set Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | C059 representing work output - Model Reviewer | Capability Set Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | D009 Work Package Report - Model Reviewer | DEX Model Reviewer | Eurostep
Rob Bodington (limited Eurostep funding) | D007 Operational Feedback - Editor | DEX Editor | Eurostep
Rob Bodington Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Rob Bodington - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | Eurostep
Rob Bodington (no longer funded) | C027 Representing Location - Model Reviewer | Capability Set Model Reviewer | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C032 Representing Activity - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C041 representing state observed - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C043 representing environment typical - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C044 representing environment actual - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C045 representing product as individual - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C046 representing variance - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C048 representing condition evaluated - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C049 representing product location - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C058 representing justification - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C060 referencing product as individual - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C063 representing product configuration - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C064 representing work done - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C065 representing work order - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C066 representing work request - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C067 representing product as individual configuration - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C068 referencing product as individual configuration - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C069 referencing activity - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C071 referencing work order - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C072 referencing work request - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Stefan Lindahl (Eurostep) | C??? representing requirements - Business Reviewer | Capability Set Business Reviewer | Eurostep
Stefan Lindhal (Eurostep/VIVACE funded) | D010 System Requirements - Model Reviewer | DEX Model Reviewer | Eurostep
All members for review, editor - Mats Nilsson | A2 Help Files | Ø FAQs | FMV
Leif Gyllström | A2 Help Files | Ø Checklist for review of DEXs | FMV
Leif Gyllström | A2 Help Files | Ø Update Capability Checklist for new architecture | FMV
Leif Gyllström | A4 Content A4.1 | Review the core capabilities | FMV | Modelers CORE Team High priority | 400
Leif Gyllström | A4 Content A4.2 | Develop missing core capabilities | FMV | Modelers CORE Team High priority | 20
Leif Gyllström | A4 Content A4.3 | Develop an example business concept for the implementations to use | FMV | High priority | 10
Leif Gyllström | A6 Reference Data A6.1 | Harmonize modelers ref data | FMV |  | 4 modelers 3 days workshop
Leif Gyllström | A6 Reference Data A6.2 | Review initial baseline of ref data | FMV |  | 40
Leif Gyllström | C??? representing codes - Editor | Capability Set Editor | FMV
Leif Gyllström | C007 Representing State Type - Editor | Capability Set Editor | FMV
Leif Gyllström | C008 Referencing Part or SLot - Editor | Capability Set Editor | FMV
Leif Gyllström | C008 Referencing Part or SLot - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C009 Referencing Product Breakdown Element - Editor | Capability Set Editor | FMV
Leif Gyllström | C010 Assigning Reference Data - Editor | Capability Set Editor | FMV
Leif Gyllström | C011 Representing Analysis Result - Editor | Capability Set Editor | FMV
Leif Gyllström | C012 Referencing Task - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C026 Representing Condiiton - Editor | Capability Set Editor | FMV
Leif Gyllström | C026 Representing Condiiton - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C036 assigning date time - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C037 referencing documents - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C043 representing environment typical - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C044 representing environment actual - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C053 representing periodicity - Editor | Capability Set Editor | FMV
Leif Gyllström | C055 representing project information - Editor | Capability Set Editor | FMV
Leif Gyllström | C057 referencing product configuration - Editor | Capability Set Editor | FMV
Leif Gyllström | C057 referencing product configuration - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C060 referencing product as individual - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C074 referencing person organization - Editor | Capability Set Editor | FMV
Leif Gyllström | C075 referencing project - Editor | Capability Set Editor | FMV
Leif Gyllström | D002 Fault States - Editor | DEX Editor | FMV
Leif Gyllström | D003 Task Set - Editor | DEX Editor | FMV
Leif Gyllström | D005 Maintenance Plan - Editor | DEX Editor | FMV
Leif Gyllström | D005 Maintenance Plan - Project Leader | DEX Project Leader | FMV
Leif Gyllström Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Leif Gyllstrom - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | FMV
Mats Nilsson | A2 Help Files | Need Team Leader and resources for updating DEX Help and Guides | FMV
Mats Nilsson | C081 representing product as realized assembly - Business Reviewer | Capability Set Business Reviewer | FMV
Mats Nilsson | D002 Fault States - Business Reviewer | DEX Business Reviewer | FMV
Mats Nilsson | D008 Product as Individual - Business Reviewer | DEX Business Reviewer | FMV
Mats Nilsson | DEXLib | DEXLib Tools - Tool plus processes for Work Progress tracking in DEXLib | FMV
Mats Nilsson | A2 Help Files | Ø Update on Development Guide. Include appropriate reference data guidance, format and content for documentation, rules, guidelines, Capabilities, Data Exchange Sets, mapping, testing, Business concepts, and Conformance Guidance/Requirements | FMV
Mats Nilsson | A2 Help Files | Ø Expand the introduction to DEXLib | FMV
Mats Nilsson | A2 Help Files | Ø Guidance on How to Start a DEX | FMV
Mats Nilsson | A2 Help Files | Ø Guide on how to “Launch a DEX” | FMV
Swedish Pilot TBD | C009 Referencing Product Breakdown Element - Model Reviewer | Capability Set Model Reviewer | FMV
Swedish Pilot TBD | C026 Representing Condiiton - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C043 representing environment typical - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C051 representing person organization typical - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C053 representing periodicity - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C070 referencing person organization typical - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C085 representing resource as realized - Model Reviewer | Capability Set Model Reviewer | FMV
Robert "Mike" McBride | C056 representing evolution of property values - Project Leader | Capability Set Project Leader | Lockheed-Martin
Robert "Mike" McBride | D008 Product as Individual - Project Leader | DEX Project Leader | Lockheed-Martin
Gordon Robb | C001 Assigning Identifiers - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C003 Representing Assembly Structure - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C004 Representing Breakdown Structure - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C005 Representing Documents - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C006 Assigning Effectivity - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C046 representing variance - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C060 referencing product as individual - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C063 representing product configuration - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C086 representing slots - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Gordon Robb | D001 Product Breakdown for Support - Business Reviewer | DEX Business Reviewer | LSC Group, Ltd
Les Debenham or UKMOD? | D007 Operational Feedback - Project Leader | DEX Project Leader | LSC Group, Ltd
Les Debenham | C008 Referencing Part or SLot - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C011 Representing Analysis Result - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C025 Assigning Observation - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C056 representing evolution of property values - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C084 representing property value ranges - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C036 assigning date time - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C049 representing product location - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C055 representing project information - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C058 representing justification - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C075 referencing project - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | D003 Task Set - Business Reviewer | DEX Business Reviewer | LSC Group, Ltd
Nigel Newling | D004 Work Package Definition - Project Leader | DEX Project Leader | LSC Group, Ltd
Nigel Newling | D008 Product as Individual - Business Reviewer | DEX Business Reviewer | LSC Group, Ltd
Nigel Newling | D009 Work Package Report - Project Leader | DEX Project Leader | LSC Group, Ltd
Nigel Newling | C012 Referencing Task - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C016 Representing Person Organization - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C019 Assigning Approvals - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C020 Representing Life Cycle Opportunity - Editor | Capability Set Editor | LSC Group, Ltd
Nigel Newling | C020 Representing Life Cycle Opportunity - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C022 Representing Work Package - Editor | Capability Set Editor | LSC Group, Ltd
Nigel Newling | C022 Representing Work Package - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C025 Assigning Observation - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C027 Representing Location - Editor | Capability Set Editor | LSC Group, Ltd
Nigel Newling | C027 Representing Location - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C032 Representing Activity - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C045 representing product as individual - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C046 representing variance - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C059 representing work output - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C061 referencing scheme - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C062 representing scheme - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C064 representing work done - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C065 representing work order - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C066 representing work request - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C067 representing product as individual configuration - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C068 referencing product as individual configuration - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C069 referencing activity - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C071 referencing work order - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C072 referencing work request - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C074 referencing person organization - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C081 representing product as realized assembly - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Tim King | C037 referencing documents - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C064 representing work done - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C065 representing work order - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C066 representing work request - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C071 referencing work order - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C072 referencing work request - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C081 representing product as realized assembly - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | D004 Work Package Definition - Editor | DEX Editor | LSC Group, Ltd
Tim King | D008 Product as Individual - Model Reviewer | DEX Model Reviewer | LSC Group, Ltd
Tim King | D009 Work Package Report - Editor | DEX Editor | LSC Group, Ltd
Tim Turner | A2 Help Files | Ø Guide on how to write the XML for a DEX (dtds) | LSC Group, Ltd
Tim Turner | A4 Content A4.1 | Review the core capabilities | LSC Group, Ltd | Modelers CORE Team High priority | 400
Tim Turner | A4 Content A4.2 | Develop missing core capabilities | LSC Group, Ltd | Modelers CORE Team High priority | 20
Tim Turner | A6 Reference Data A6.1 | Harmonize modelers ref data | LSC Group, Ltd |  | 4 modelers 3 days workshop
Tim Turner | A6 Reference Data A6.2 | Review initial baseline of ref data | LSC Group, Ltd |  | 40
Tim Turner | C001 Assigning Identifiers - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C002 Representing Parts - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C003 Representing Assembly Structure - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C004 Representing Breakdown Structure - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C005 Representing Documents - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C006 Assigning Effectivity - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C019 Assigning Approvals - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim Turner | C063 representing product configuration - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim Turner | C084 representing property value ranges - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Tim Turner | C086 representing slots - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C087 assigning document properties - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | D001 Product Breakdown for Support - Editor | DEX Editor | LSC Group, Ltd
Tim Turner | D008 Product as Individual - Editor | DEX Editor | LSC Group, Ltd
Tim Turner Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Tim Turner - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | LSC Group, Ltd
Chris Kreiler | A2 Help Files | Ø Guidance on How to Start a DEX | ManTech
Chris Kreiler | A2 Help Files | Ø Guide on how to “Launch a DEX” | ManTech
Tor Arne Irgens | A2 Help Files | Ø Process for developing DEX and Capabilities | Norwegian Defense Logistics
Tor Arne Irgens | A2 Help Files | Ø Guides for review and test | Norwegian Defense Logistics
Tor Arne Irgens | C041 representing state observed - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C055 representing project information - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C057 referencing product configuration - Model Reviewer | Capability Set Model Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C061 referencing scheme - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C062 representing scheme - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C075 referencing project - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C082 referencing contract - Model Reviewer | Capability Set Model Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C083 representing contract - Model Reviewer | Capability Set Model Reviewer | Norwegian Defense Logistics
John Spencer | C015 Representing Task - Business Reviewer | Capability Set Business Reviewer | Pennant International Group plc
John Spencer | C050 referencing resource - Business Reviewer | Capability Set Business Reviewer | Pennant International Group plc
John Spencer | C052 representing resource - Business Reviewer | Capability Set Business Reviewer | Pennant International Group plc
John Spencer | C088 representing task structure - Model Reviewer | Capability Set Model Reviewer | Pennant International Group plc
John Spencer | C089 representing task and state - Model Reviewer | Capability Set Model Reviewer | Pennant International Group plc
John Spencer | C090 representing task associations - Model Reviewer | Capability Set Model Reviewer | Pennant International Group plc
John Spencer | D002 Fault States - Model Reviewer | DEX Model Reviewer | Pennant International Group plc
Nik Barron | A2 Help Files | Ø Update HTML | Pennant International Group plc
Adrian Blenkiron | C007 Representing State Type - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C009 Referencing Product Breakdown Element - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C010 Assigning Reference Data - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C011 Representing Analysis Result - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C013 Representing Probability - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Adrian Blenkiron | C053 representing periodicity - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C055 representing project information - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C075 referencing project - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | D002 Fault States - Project Leader | DEX Project Leader | Rolls-Royce
Carolyn Cox | C037 referencing documents - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Carolyn Cox | D004 Work Package Definition - Business Reviewer | DEX Business Reviewer | Rolls-Royce
Carolyn Cox | D009 Work Package Report - Business Reviewer | DEX Business Reviewer | Rolls-Royce
Mike Day - RR? | A3 Test Data | Harmonize, update, and extend bike test data in S1000D format and compliance | Rolls-Royce |  | ???
Nigel Walker | C019 Assigning Approvals - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Nigel Walker | D001 Product Breakdown for Support - Project Leader | DEX Project Leader | Rolls-Royce
Nigel Walker | C001 Assigning Identifiers - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C002 Representing Parts - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C003 Representing Assembly Structure - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C004 Representing Breakdown Structure - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C005 Representing Documents - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C006 Assigning Effectivity - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C057 referencing product configuration - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Nigel Walker | C084 representing property value ranges - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C086 representing slots - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C087 assigning document properties - Project Leader | Capability Set Project Leader | Rolls-Royce
Johan Carlson | C007 Representing State Type - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C009 Referencing Product Breakdown Element - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C044 representing environment actual - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C048 representing condition evaluated - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C049 representing product location - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C058 representing justification - Business Reviewer | Capability Set Business Reviewer | Saab
Saab TBD | A3 Test Data | Harmonize, update, and extend bike test data in S1000D format and compliance | Saab |  | ???
Andy Burden (UKMOD) | C027 Representing Location - Business Reviewer | Capability Set Business Reviewer | UKMOD
Phil Rutland | D003 Task Set - Project Leader | DEX Project Leader | UKMOD
UKMOD or Les Debenham? | D007 Operational Feedback - Project Leader | DEX Project Leader | UKMOD
UKMOD TBD | A3 Test Data | Harmonize, update, and extend bike test data in S1000D format and compliance | UKMOD |  | ???
UKMOD TBD | C012 Referencing Task - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C013 Representing Probability - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C014 Messaging - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C015 Representing Task - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C020 Representing Life Cycle Opportunity - Business Reviewer | Capability Set Business Reviewer | UKMOD
UKMOD TBD | C022 Representing Work Package - Business Reviewer | Capability Set Business Reviewer | UKMOD
UKMOD TBD | C032 Representing Activity - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C041 representing state observed - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C043 representing environment typical - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C044 representing environment actual - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C045 representing product as individual - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C048 representing condition evaluated - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C049 representing product location - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C050 referencing resource - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C051 representing person organization typical - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C052 representing resource - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C058 representing justification - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C060 referencing product as individual - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C063 representing product configuration - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C064 representing work done - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C065 representing work order - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C066 representing work request - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C067 representing product as individual configuration - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C068 referencing product as individual configuration - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C069 referencing activity - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C070 referencing person organization typical - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C071 referencing work order - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C072 referencing work request - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C076 assigning product properties - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C077 assigning product properties - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C078 assigning resource properties - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C079 representing properties numerically - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C080 representing properties textually - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C081 representing product as realized assembly - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C085 representing resource as realized - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C088 representing task structure - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C089 representing task and state - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C090 representing task associations - Project Leader | Capability Set Project Leader | UKMOD
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C??? representing codes - Business Reviewer | Capability Set Business Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C??? representing codes - Project Leader | Capability Set Project Leader
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C001 Assigning Identifiers - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C010 Assigning Reference Data - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C014 Messaging - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C016 Representing Person Organization - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C036 assigning date time - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C091 representing description - Business Reviewer | Capability Set Business Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C091 representing description - Editor | Capability Set Editor
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C091 representing description - Project Leader | Capability Set Project Leader
TBD | A1-1 DEXLib Infrastructure (Business Concepts) 1.7 | Provide a search mechanism for BCs |  | This would require a significant investment, so no hours quoted. | 0
TBD | A1-1 DEXLib Infrastructure (Business Concepts) 1.9 | Contingency |  |  | 0
TBD | A1-10 DEXLib Infrastructure (Activity Model) 10.1 | Provide index, navigable activity model integrated into DEXLib |  | Each DEX shows the sub set of the activity model. The full activity model should be navigable from here. | 80
TBD | A1-11 DEXLib Infrastructure (General) 11.1 | Maintain a decision site |  | A page on DEXLib listing the main decisions | 8
TBD | A1-11 DEXLib Infrastructure (General) 11.2 | Maintain an action list on DEXLib |  | Create an action list in DEXLib | 8
TBD | A1-2 DEXLib Infrastructure (Capabilities) 2.9 | Contingency
TBD | A1-3 DEXLib Infrastructure (Instance Diagramming Tool) | Instance diagramming tool |  | Provide facility for drawing instance diagrams that include capability macros. This may just be an agreed VISIO template or may be a tool. The hours estimate are for a tool. The tool will: - enable the drawing on instance diagrams that include capability macros - generate hyperlinks between EXPRESS entities defining the Capabilities - list a library of capability macros - instantiating a capability macro graphically from the library - facility to output a P28 and P21 file Note - this is a rough estimate of the whole job | 400
TBD | A1-4 DEXLib Infrastructure (Rules) 4.1 | Define rules for capabilities & DEXs |  | Define how to represent the rules, both text based and formal rules. This needs to be done collaboratively and will provide a specification NOTE - I am not sure that this is required once we have implemented the capability macros | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.2 | Modify capability & DEX DTD to include rules |  |  | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.3 | Modify capability & DEX XSL to display rules |  |  | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.4 | Update the mk_capability script to add rules section |  |  | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.5 | Update the mk_dex script to add rules section |  |  | 0
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.1 | Define Conformance classes |  | Define how to specify a conformance class. This needs to be done collaboratively and will provide a specification. Estimate assumes that the SC4 approach used in modular AP will be adopted. | 16
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.2 | Update the mk_dex script to add conformance section |  |  | 4
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.3 | Define DTD to accommodate conformance classes |  |  | 4
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.4 | Create XSL to display conformance classes |  |  | 8
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.5 | DEX test data |  | Add a section in the DEX to list/index the test data for testing the compliance/conformance of the DEX and the exchange. Note, it is assumed that test data is available. | 24
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.6 | Define DTD to accommodate test data |  |  | 4
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.7 | Create XSL to display test data |  | Assuming a simple display - hyperlinks from instantiated entities will be require more effort. | 8
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.8 | Update the mk_dex script to add test data section |  |  | 4
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.1 | Requirements analysis |  | Establish requirements for exchange contract. This should identify potentially what is the content of the exchange contract and how it might build on DEXLib. This should refer to the baseline of the DEXs, capabilities, modules | 120
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.2 | Define exchange contract |  | Define how to specify an exchange contract. This needs to be done collaboratively and will provide a specification. | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.3 | Define the DTD for the exchange contract |  |  | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.4 | Define mk_exchange_contract script |  | Mechanism for generating the exchange contract XML template | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.5 | Create XSL to display exchange contract |  | Mechanism for linking to a DEX conformance classes. Mechanism for linking to business concepts | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.6 | Develop standard text for exchange contract |  | This will require legal wording | 0
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.1 | Define how the baseline of the DEX, capabilities, modules, AP, reference data, and business concepts is managed, identified and represented in an exchange contract |  | Note - this should be picked up in the test document | 80
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.2 | Implement simple to use tool to create and view baselines |  |  | 200
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.3 | Document tool and baselining process |  |  | 40
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.4 | Maintain a released version of the modular AP |  | We need to extract a released version of the modules into DEXLib to ensure that the DEXs use controlled versions of modules. (The modules will be continuing being developed in STEPmod) | 16
TBD | A1-8 DEXLib Infrastructure (Publication) 8.1 | Maintain a mirror site of DEXLib that provides HTML access |  | Pennant International Group plc already provide a site- the scripts need to be updated to ensure that a complete build is done. | 16
TBD | A1-8 DEXLib Infrastructure (Publication) 8.2 | Install a mirror of capabilities for review |  |  | 4
TBD | A1-8 DEXLib Infrastructure (Publication) 8.3 | Release of capabilities for review |  |  | 4
TBD | A1-8 DEXLib Infrastructure (Publication) 8.4 | DEX publication approach |  | OASIS TC to agree on what is to be published. A DEX, A capability, a suite of DEXs? This is a prerequisite | 0
TBD | A1-8 DEXLib Infrastructure (Publication) 8.5 | Generate a version of the DEXs for OASIS review |  | At this stage, we are not sure whether the current form of a DEX will be acceptable to OASIS for publication. So generate one and see. | 16
TBD | A1-8 DEXLib Infrastructure (Publication) 8.6 | Modify DEX structure for publication by OASIS |  | Make the changes requested by OASIS. Not this dependent on 8.5 and no estimate effort can be made until the initial DEX has been reviewed. | 0
TBD | A1-9 DEXLib Infrastructure (Ref Data) 9.1 | Collaborative Ref Data development environment |  | This is to replace Protégé. This would require significant effort. Hence no effort estimated.
TBD | A1-9 DEXLib Infrastructure (Ref Data) 9.2 | Embed a link to the reference |  | Enable a link between the XSL displaying the reference data and the RDL server so allow the browsing of the reference data from DEXLib. This requires the support / maintenance of the RDL server. Hence no effort estimated.
TBD | A1-9 DEXLib Infrastructure (Ref Data) 9.3 | Facility to identify extensible / non extensible reference data |  | Mark ref data classes as "non" extensible. I.e. can not be extended by subclasses in business concepts | 4
TBD | A2 Help Files | Ø Develop templates for main rule types
TBD | A2 Help Files | Ø Develop scripts for business concepts, using rule templates
TBD | A6 Reference Data A6.3 | Reuse Ref Data from 15926
TBD | C041 representing state observed - Model Reviewer | Capability Set Model Reviewer
TBD | C082 referencing contract - Business Reviewer | Capability Set Business Reviewer
TBD | C083 representing contract - Business Reviewer | Capability Set Business Reviewer
TBD | D007 Operational Feedback - Business Reviewer | DEX Business Reviewer
TBD | D007 Operational Feedback - Model Reviewer | DEX Model Reviewer
Note on B71: Rob Bodington: Assumed 10 days per modeler
Note on B73: Rob Bodington: Assumed 10 days per modeler
Note on B145: Rob Bodington: Assumed 10 days per modeler
Note on B147: Rob Bodington: Assumed 10 days per modeler
Note on B148: Rob Bodington: Assumed 10 days per modeler
Note on B213: Rob Bodington: Assumed 10 days per modeler
Note on B215: Rob Bodington: Assumed 10 days per modeler
Note on B216: Rob Bodington: Assumed 10 days per modeler
Note on B360: Rob Bodington: Assumed 10 days per modeler
Note on B362: Rob Bodington: Assumed 10 days per modeler
Note on B363: Rob Bodington: Assumed 10 days per modeler
Note on E192: Rob Bodington: Should be UK-MOD We are not providing all funding
Note on G72: Rob Bodington: Increased
Note on G140: Rob Bodington: These hours are underestimates
Note on G208: Rob Bodington: These hours are overestimates
Note on G214: Rob Bodington: Increased
Note on G250: Rob Bodington: Increased
Note on G361: Rob Bodington: Increased
Note on I192: Rob Bodington: Should be UK-MOD We are not providing all funding

## Res_conf_backup (hidden)
OASIS PLCS TC Work Programme and Resources by Name
OASIS PLCS TC Tasks and Resources
OASIS PLCS Technical Oversight Tasks and Resources
OASIS PLCS Quality Assurance and Implementation Tasks and Resources
Resource | PLCS Organization Entity | Membership | Sponsor Company | Confirmation | Comments
Howard Mason | OASIS TC | Voting Member BAESystems, PLCS TC Co-Chair | BAESystems
Nils Sandsmark | OASIS TC | Voting Member Det Norse Veritas | Det Norse Veritas
Trine Hansen | Technical Oversight | Implementers Forum Lead | Det Norse Veritas
Trine Hansen | Technical Oversight | Quality Leaders | Det Norse Veritas
Trine Hansen | Implementers Forum | Lead | DNV
Trine Hansen | Quality Assurance | Lead | DNV
Nigel Shaw | Technical Oversight | Implementers Forum Lead | Eurostep
Nigel Shaw | Technical Oversight | Quality Leaders | Eurostep
Nigel Shaw | OASIS TC | Voting Member Eurostep | Eurostep
Nigel Shaw (no funding) | Implementers Forum | Lead | Eurostep
Nigel Shaw (no funding) | Quality Assurance | Lead | Eurostep
Rob Bodington | Technical Oversight | Tool Expert (Infrastructure) | Eurostep
TB D | OASIS TC | Voting Member Lockheed-Martin | Lockheed-Martin
Nigel Newling | Technical Oversight | Business Expert | LSC Group Ltd
Steve Foster? | OASIS TC | Voting Member LSC Group Ltd | LSC Group Ltd
Tim King | OASIS TC | Monitor SC4 modules for input on AP239 | LSC Group Ltd
Tim Turner | Technical Oversight | Modeler | LSC Group Ltd
Chris Kreiler | Technical Oversight | Business Expert (Project Manager - Status tracking and reporting) | ManTech - Funded by US DoD | Confirmed | Contracted under US DoD
Chris Kreiler | OASIS TC | Voting Member ManTech, Secretariat | ManTech - Funded by US DoD | Confirmed | Contracted under US DoD
Tor Arne Irgens | Technical Oversight | Information Architect | Norwegian Defense Logistics Logistics
Tor Arne Irgens | OASIS TC | Voting Member Norwegian Defence | Norwegian Defense Logistics Logistics
John Spencer | OASIS TC | Voting Member Pennant International Group plc | Pennant International Group plc International Group plc
Nigel Walker | OASIS TC | Voting Member Rolls-Royce | Rolls-Royce plc
Carl Johan Wilen | OASIS TC | Voting Member Saab AB | Saab AB
Mats Elgh | OASIS TC | Voting Member Swedish Defense | Swedish Defence Materiel Administration
Mats Nilsson | Technical Oversight | Tool Expert | Swedish Defence Materiel Administration
King Yee | OASIS TC | Voting Member Boeing | The Boeing Company
Phil Rutland | Technical Oversight | Business Expert | UK Ministry of Defence Technical Information
Phil Rutland | OASIS TC | Voting Member UK MOD | UK Ministry of Defence Technical Information
Jerry Smith | OASIS TC | Voting Member, USDOD, PLCS TC Co-Chair | US Department of Defense (DoD)
Resource Name | Number | Activity/Task | Sponsor Company | Task Description | Hours per task estimate | Confirmation | Comments
All members | A2 Help Files | Review structure of DEX Help | All
All members for review, editor - Mats Nilsson | A2 Help Files | Ø FAQs | All
All members for review; editor - DNV | A2 Help Files | Ø Need review of Development Guide for Reference Data | All
Sean Barker | C012 Referencing Task - Editor | Capability Set Editor | BAESystems
Sean Barker | C013 Representing Probability - Editor | Capability Set Editor | BAESystems
Sean Barker | C014 Messaging - Editor | Capability Set Editor | BAESystems
Sean Barker | C015 Representing Task - Editor | Capability Set Editor | BAESystems
Sean Barker | C025 Assigning Observation - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C050 referencing resource - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C051 representing person organization typical - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C052 representing resource - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C059 representing work output - Editor | Capability Set Editor | BAESystems
Sean Barker | C061 referencing scheme - Editor | Capability Set Editor | BAESystems
Sean Barker | C062 representing scheme - Editor | Capability Set Editor | BAESystems
Sean Barker | C070 referencing person organization typical - Model Reviewer | Capability Set Model Reviewer | BAESystems
Sean Barker | C073 representing information controls - Editor | Capability Set Editor | BAESystems
Sean Barker | C085 representing resource as realized - Business Reviewer | Capability Set Business Reviewer | BAESystems
Sean Barker | C088 representing task structure - Editor | Capability Set Editor | BAESystems
Sean Barker | C089 representing task and state - Editor | Capability Set Editor | BAESystems
Sean Barker | C090 representing task associations - Editor | Capability Set Editor | BAESystems
BAESystems TBD | D005 Maintenance Plan - Business Reviewer | DEX Business Reviewer | BAESystems
Howard Mason | A2 Help Files | Ø Guidance on How to Start a DEX | BAESystems
Howard Mason | A2 Help Files | Ø Guide on how to “Launch a DEX” | BAESystems
Howard Mason | C073 representing information controls - Business Reviewer | Capability Set Business Reviewer | BAESystems
Sean Barker | A4 Content A4.1 | Review the core capabilities | BAESystems | Modelers CORE Team High priority | 400
Sean Barker | A4 Content A4.2 | Develop missing core capabilities | BAESystems | Modelers CORE Team High priority | 20
Sean Barker | A6 Reference Data A6.1 | Harmonize modelers ref data | BAESystems |  | 4 modelers 3 days workshop
Sean Barker | A6 Reference Data A6.2 | Review initial baseline of ref data | BAESystems |  | 40
Sean Barker | D003 Task Set - Editor | DEX Editor | BAESystems
Sean Barker Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Sean Barker - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | BAESystems
Tom Hendrix | C002 Representing Parts - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C003 Representing Assembly Structure - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C004 Representing Breakdown Structure - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C005 Representing Documents - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C008 Referencing Part or SLot - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C013 Representing Probability - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C026 Representing Condiiton - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C045 representing product as individual - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C048 representing condition evaluated - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C053 representing periodicity - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C056 representing evolution of property values - Editor | Capability Set Editor | Boeing
Tom Hendrix | C067 representing product as individual configuration - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C068 referencing product as individual configuration - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C073 representing information controls - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C074 referencing person organization - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C076 assigning product properties - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C077 assigning product properties - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C078 assigning resource properties - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C079 representing properties numerically - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C080 representing properties textually - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C081 representing product as realized assembly - Editor | Capability Set Editor | Boeing
Tom Hendrix | C081 representing product as realized assembly - Model Reviewer | Capability Set Model Reviewer | Boeing
Tom Hendrix | C084 representing property value ranges - Editor | Capability Set Editor | Boeing
Tom Hendrix | C086 representing slots - Business Reviewer | Capability Set Business Reviewer | Boeing
Tom Hendrix | C087 assigning document properties - Business Reviewer | Capability Set Business Reviewer | Boeing
Tom Hendrix | D005 Maintenance Plan - Model Reviewer | DEX Model Reviewer | Boeing
Tom Hendrix | D008 Product as Individual - Model Reviewer | DEX Model Reviewer | Boeing
Albert Leyson | C056 representing evolution of property values - Model Reviewer | Capability Set Model Reviewer | DNV
DNV TBD | A2 Help Files | Ø Update Checklist for reference data review | DNV
Norwegian Pilot TBD | C??? representing codes - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C002 Representing Parts - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C002 Representing Parts - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C003 Representing Assembly Structure - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C003 Representing Assembly Structure - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C004 Representing Breakdown Structure - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C004 Representing Breakdown Structure - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C005 Representing Documents - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C005 Representing Documents - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C006 Assigning Effectivity - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C006 Assigning Effectivity - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C010 Assigning Reference Data - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C014 Messaging - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C016 Representing Person Organization - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C064 representing work done - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C065 representing work order - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C066 representing work request - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C071 referencing work order - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C072 referencing work request - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C074 referencing person organization - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C076 assigning product properties - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C077 assigning product properties - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C078 assigning resource properties - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C079 representing properties numerically - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C080 representing properties textually - Business Reviewer | Capability Set Business Reviewer | DNV
Norwegian Pilot TBD | C082 referencing contract - Editor | Capability Set Editor | DNV
Norwegian Pilot TBD | C082 referencing contract - Project Leader | Capability Set Project Leader | DNV
Norwegian Pilot TBD | C083 representing contract - Editor | Capability Set Editor | DNV
Norwegian Pilot TBD | C083 representing contract - Project Leader | Capability Set Project Leader | DNV
Norwegian Pilot TBD | C087 assigning document properties - Model Reviewer | Capability Set Model Reviewer | DNV
Norwegian Pilot TBD | C091 representing description - Model Reviewer | Capability Set Model Reviewer | DNV
Trine Hanse - Quality Assurance Team | A3 Test Data A3.1 | Define the test data (exemplar) | DNV |  | ???
Trine Hansen | A2 Help Files | Ø Guides for review and test | DNV
Trine Hansen | A2 Help Files | Ø Checklist for review of DEXs | DNV
Trine Hansen | A2 Help Files A2.1 | Add definition refined architecture to help/introduction | DNV |  | 10
Trine Hansen | A2 Help Files A2.1.1 | Descriptions on exchange contracts | DNV |  | 10
Trine Hansen | A2 Help Files A2.1.2 | Description of DEXs | DNV |  | 8
Trine Hansen | A2 Help Files A2.1.3 | Description of capabilities | DNV |  | 8
Trine Hansen | A2 Help Files A2.1.4 | Description on business concepts | DNV |  | 8
Trine Hansen | A4 Content A4.1 | Review the core capabilities | DNV | Modelers CORE Team High priority | 400
Trine Hansen | A4 Content A4.2 | Develop missing core capabilities | DNV | Modelers CORE Team High priority | 20
Trine Hansen | A6 Reference Data A6.1 | Harmonize modelers ref data | DNV |  | 4 modelers 3 days workshop
Trine Hansen | A6 Reference Data A6.2 | Review initial baseline of ref data | DNV |  | 40
Trine Hansen | C016 Representing Person Organization - Editor | Capability Set Editor | DNV
Trine Hansen | C032 Representing Activity - Model Reviewer | Capability Set Model Reviewer | DNV
Trine Hansen | C036 assigning date time - Editor | Capability Set Editor | DNV
Trine Hansen | C037 referencing documents - Editor | Capability Set Editor | DNV
Trine Hansen | C063 representing product configuration - Business Reviewer | Capability Set Business Reviewer | DNV
Trine Hansen | C069 referencing activity - Model Reviewer | Capability Set Model Reviewer | DNV
Trine Hansen (Norwegian Pilot) | D001 Product Breakdown for Support - Model Reviewer | DEX Model Reviewer | DNV
Trine Hansen Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Trine Hansen - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | DNV
Eurostep Sweden TBD (Eurostep funding ) | D001 Product Breakdown for Support - Model Reviewer | DEX Model Reviewer | Eurostep
Eurostep TBD | C073 representing information controls - Project Leader | Capability Set Project Leader | Eurostep
Eurostep TBD (Eurostep funding) | C059 representing work output - Business Reviewer | Capability Set Business Reviewer | Eurostep
Eurostep to provide proposal for tool options | A3 Test Data | Need tool for test data development and viewing (create, review and validate part 21 and part 28 files) | Eurostep |  | ???
Ian Hickman | C046 representing variance - Model Reviewer | Capability Set Model Reviewer | Eurostep
Mats Lindeblad (Volvo Aero) | C??? representing requirements - Model Reviewer | Capability Set Model Reviewer | Eurostep |  |  |  | Eurostep Volvo Aero
Mats Lindeblad (Volvo Aero) | D010 System Requirements - Business Reviewer | DEX Business Reviewer | Eurostep |  |  |  | Eurostep Volvo Aero
Mike Ward (no longer funded) | C019 Assigning Approvals - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C025 Assigning Observation - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C050 referencing resource - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C051 representing person organization typical - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C052 representing resource - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C070 referencing person organization typical - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C076 assigning product properties - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C077 assigning product properties - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C078 assigning resource properties - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C079 representing properties numerically - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C080 representing properties textually - Editor | Capability Set Editor | Eurostep
Mike Ward (no longer funded) | C085 representing resource as realized - Editor | Capability Set Editor | Eurostep
Nigel Shaw (Eurostep funding) | D003 Task Set - Model Reviewer | DEX Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | D004 Work Package Definition - Model Reviewer | DEX Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | D009 Work Package Report - Model Reviewer | DEX Model Reviewer | Eurostep
Nigel Shaw - Quality Assurance Team | A3 Test Data A3.1 | Define the test data (exemplar) | Eurostep |  | ???
Nigel Shaw | C061 referencing scheme - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw | C062 representing scheme - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C007 Representing State Type - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C015 Representing Task - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C020 Representing Life Cycle Opportunity - Model Reviewer | Capability Set Model Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C088 representing task structure - Business Reviewer | Capability Set Business Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C089 representing task and state - Business Reviewer | Capability Set Business Reviewer | Eurostep
Nigel Shaw (Eurostep funding) | C090 representing task associations - Business Reviewer | Capability Set Business Reviewer | Eurostep
Phil Spiby (Eurostep funded) | C??? representing requirements - Editor | Capability Set Editor | Eurostep
Phil Spiby (Eurostep funded) | C??? representing requirements - Project Leader | Capability Set Project Leader | Eurostep
Phil Spiby (Eurostep/VIVACE funded) | D010 System Requirements - Editor | DEX Editor | Eurostep
Phil Spiby (Eurostep/VIVACE funded) | D010 System Requirements - Project Leader | DEX Project Leader | Eurostep
Rob Bodington | A1 | DEXLib infrastructure | Eurostep | Support for development of Business Concepts High priority |  |  | Eurostep (360 hrs UK MOD funding, rest unfunded)
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.1 | Specify the layout and content of the Business concept | Eurostep | This needs to be done collaboratively and will provide a specification. The content will include how the business concept maps to capabilities, how the reference data to be used with the business concept is specified | 40 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.2 | Modify DTD | Eurostep |  | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.3 | Develop scripts to build template for BC | Eurostep |  | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.4 | Update XSL to display BC | Eurostep |  | 24 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.5 | Update XSL to provide indices of BC | Eurostep | The index should show what capabilities uses a business concept Show what business concepts are used by a capability | 16 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.6 | Provide support for links between BC, capabilities and Ref data | Eurostep | This means syntax + XSL to define +display the reference between the BC and the ref data etc (may be able to reuse existing code) | 16 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-1 DEXLib Infrastructure (Business Concepts) 1.8 | Add tool for editors to list the links to BC in xml for pasting into text | Eurostep |  | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.1 | Define capability macros | Eurostep | Specify how to represent a capability macro - a macro defining the set of entities to be instantiated, the associated reference data and values for attributes on the entities. This will be passed to the macro as parameters. The macro is in effect a representation of the instance diagrams in text - this may well be just the mapping syntax from Apes. This needs to be done collaboratively and will provide a specification. The macro syntax should be used in a business concept definition to show how the business concept is defined using the capability macros | 120 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.2 | Document the macro language | Eurostep | Document how to write the macros and its usage | 40 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.3 | Modify capability DTD to include macro in capability | Eurostep | This means syntax + XSL to define + display the reference between the business concept and a capability macro, and between capability macros | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.4 | Modify capability XSL to display macro | Eurostep | XSL shall display the macro in the capability XSL shall validate that the macros is defined using valid EXPRESS and other valid macros Index of macros should be provided. | 40 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.5 | Update the mk_capability script to add macro section | Eurostep |  | 4 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.6 | Provide support for linking to subsections of a capability | Eurostep | This means syntax + XSL to define + display the reference between the business concept and a capability macro, and between capability macros | 8 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A1-2 DEXLib Infrastructure (Capabilities) 2.7 | Update capability to handle example data | Eurostep | Currently example instance data is not presented in a consistent way. Some capabilities just use instance diagrams, some provide Part 21 file fragments, none provide Part 28 file fragments. The DTD needs to be extended to allow for both part21 and part 28 fragments. Need to extend the DTD and XSL to make the type of the type of test data explicit | 4 |  | Eurostep UK-MOD TAF 40
Rob Bodington | A2 Help Files | Ø Update HTML | Eurostep |  |  |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2 | Add general usage section | Eurostep |  | 4 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.1 | Explaining use of classification | Eurostep |  | 16 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.2 | Explaining use of identification | Eurostep |  | 20 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.3 | Explaining use of IGNORE etc. as attribute values | Eurostep |  | 20 |  | Eurostep (Eurostep funding)
Rob Bodington | A2 Help Files A2.2.4 | Add a select population matrix | Eurostep |  | 20 |  | Eurostep (Eurostep funding)
Rob Bodington | A4 Content A4.1 | Review the core capabilities | Eurostep | Modelers CORE Team High priority Eurostep (UK MOD funding) | 400
Rob Bodington | A4 Content A4.2 | Develop missing core capabilities | Eurostep | Modelers CORE Team High priority Eurostep (UK MOD funding) | 20
Rob Bodington | A6 Reference Data A6.1 | Harmonize modelers ref data | Eurostep |  | 4 modelers 3 days workshop |  | Eurostep (No funding)
Rob Bodington | A6 Reference Data A6.2 | Review initial baseline of ref data | Eurostep |  | 40 |  | Eurostep (No funding)
Rob Bodington | D004 Work Package Definition - Model Reviewer | DEX Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | C011 Representing Analysis Result - Model Reviewer | Capability Set Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | C022 Representing Work Package - Model Reviewer | Capability Set Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | C059 representing work output - Model Reviewer | Capability Set Model Reviewer | Eurostep
Rob Bodington (Eurostep funding) | D009 Work Package Report - Model Reviewer | DEX Model Reviewer | Eurostep
Rob Bodington (limited Eurostep funding) | D007 Operational Feedback - Editor | DEX Editor | Eurostep
Rob Bodington Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Rob Bodington - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | Eurostep
Rob Bodington (no longer funded) | C027 Representing Location - Model Reviewer | Capability Set Model Reviewer | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C032 Representing Activity - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C041 representing state observed - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C043 representing environment typical - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C044 representing environment actual - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C045 representing product as individual - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C046 representing variance - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C048 representing condition evaluated - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C049 representing product location - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C058 representing justification - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C060 referencing product as individual - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C063 representing product configuration - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C064 representing work done - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C065 representing work order - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C066 representing work request - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C067 representing product as individual configuration - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C068 referencing product as individual configuration - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C069 referencing activity - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C071 referencing work order - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Rob Bodington (no longer funded) | C072 referencing work request - Editor | Capability Set Editor | Eurostep |  |  |  | Eurostep (No funding)
Stefan Lindahl (Eurostep) | C??? representing requirements - Business Reviewer | Capability Set Business Reviewer | Eurostep
Stefan Lindhal (Eurostep/VIVACE funded) | D010 System Requirements - Model Reviewer | DEX Model Reviewer | Eurostep
All members for review, editor - Mats Nilsson | A2 Help Files | Ø FAQs | FMV
Leif Gyllström | A2 Help Files | Ø Checklist for review of DEXs | FMV
Leif Gyllström | A2 Help Files | Ø Update Capability Checklist for new architecture | FMV
Leif Gyllström | A4 Content A4.1 | Review the core capabilities | FMV | Modelers CORE Team High priority | 400
Leif Gyllström | A4 Content A4.2 | Develop missing core capabilities | FMV | Modelers CORE Team High priority | 20
Leif Gyllström | A4 Content A4.3 | Develop an example business concept for the implementations to use | FMV | High priority | 10
Leif Gyllström | A6 Reference Data A6.1 | Harmonize modelers ref data | FMV |  | 4 modelers 3 days workshop
Leif Gyllström | A6 Reference Data A6.2 | Review initial baseline of ref data | FMV |  | 40
Leif Gyllström | C??? representing codes - Editor | Capability Set Editor | FMV
Leif Gyllström | C007 Representing State Type - Editor | Capability Set Editor | FMV
Leif Gyllström | C008 Referencing Part or SLot - Editor | Capability Set Editor | FMV
Leif Gyllström | C008 Referencing Part or SLot - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C009 Referencing Product Breakdown Element - Editor | Capability Set Editor | FMV
Leif Gyllström | C010 Assigning Reference Data - Editor | Capability Set Editor | FMV
Leif Gyllström | C011 Representing Analysis Result - Editor | Capability Set Editor | FMV
Leif Gyllström | C012 Referencing Task - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C026 Representing Condiiton - Editor | Capability Set Editor | FMV
Leif Gyllström | C026 Representing Condiiton - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C036 assigning date time - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C037 referencing documents - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C043 representing environment typical - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C044 representing environment actual - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C053 representing periodicity - Editor | Capability Set Editor | FMV
Leif Gyllström | C055 representing project information - Editor | Capability Set Editor | FMV
Leif Gyllström | C057 referencing product configuration - Editor | Capability Set Editor | FMV
Leif Gyllström | C057 referencing product configuration - Project Leader | Capability Set Project Leader | FMV
Leif Gyllström | C060 referencing product as individual - Model Reviewer | Capability Set Model Reviewer | FMV
Leif Gyllström | C074 referencing person organization - Editor | Capability Set Editor | FMV
Leif Gyllström | C075 referencing project - Editor | Capability Set Editor | FMV
Leif Gyllström | D002 Fault States - Editor | DEX Editor | FMV
Leif Gyllström | D003 Task Set - Editor | DEX Editor | FMV
Leif Gyllström | D005 Maintenance Plan - Editor | DEX Editor | FMV
Leif Gyllström | D005 Maintenance Plan - Project Leader | DEX Project Leader | FMV
Leif Gyllström Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Leif Gyllstrom - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | FMV
Mats Nilsson | A2 Help Files | Need Team Leader and resources for updating DEX Help and Guides | FMV
Mats Nilsson | C081 representing product as realized assembly - Business Reviewer | Capability Set Business Reviewer | FMV
Mats Nilsson | D002 Fault States - Business Reviewer | DEX Business Reviewer | FMV
Mats Nilsson | D008 Product as Individual - Business Reviewer | DEX Business Reviewer | FMV
Mats Nilsson | DEXLib | DEXLib Tools - Tool plus processes for Work Progress tracking in DEXLib | FMV
Mats Nilsson | A2 Help Files | Ø Update on Development Guide. Include appropriate reference data guidance, format and content for documentation, rules, guidelines, Capabilities, Data Exchange Sets, mapping, testing, Business concepts, and Conformance Guidance/Requirements | FMV
Mats Nilsson | A2 Help Files | Ø Expand the introduction to DEXLib | FMV
Mats Nilsson | A2 Help Files | Ø Guidance on How to Start a DEX | FMV
Mats Nilsson | A2 Help Files | Ø Guide on how to “Launch a DEX” | FMV
Swedish Pilot TBD | C009 Referencing Product Breakdown Element - Model Reviewer | Capability Set Model Reviewer | FMV
Swedish Pilot TBD | C026 Representing Condiiton - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C043 representing environment typical - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C051 representing person organization typical - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C053 representing periodicity - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C070 referencing person organization typical - Business Reviewer | Capability Set Business Reviewer | FMV
Swedish Pilot TBD | C085 representing resource as realized - Model Reviewer | Capability Set Model Reviewer | FMV
Robert "Mike" McBride | C056 representing evolution of property values - Project Leader | Capability Set Project Leader | Lockheed-Martin
Robert "Mike" McBride | D008 Product as Individual - Project Leader | DEX Project Leader | Lockheed-Martin
Gordon Robb | C001 Assigning Identifiers - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C003 Representing Assembly Structure - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C004 Representing Breakdown Structure - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C005 Representing Documents - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C006 Assigning Effectivity - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C046 representing variance - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C060 referencing product as individual - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C063 representing product configuration - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Gordon Robb | C086 representing slots - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Gordon Robb | D001 Product Breakdown for Support - Business Reviewer | DEX Business Reviewer | LSC Group, Ltd
Les Debenham or UKMOD? | D007 Operational Feedback - Project Leader | DEX Project Leader | LSC Group, Ltd
Les Debenham | C008 Referencing Part or SLot - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C011 Representing Analysis Result - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C025 Assigning Observation - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C056 representing evolution of property values - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Les Debenham | C084 representing property value ranges - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C036 assigning date time - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C049 representing product location - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C055 representing project information - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C058 representing justification - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | C075 referencing project - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Nigel Newling | D003 Task Set - Business Reviewer | DEX Business Reviewer | LSC Group, Ltd
Nigel Newling | D004 Work Package Definition - Project Leader | DEX Project Leader | LSC Group, Ltd
Nigel Newling | D008 Product as Individual - Business Reviewer | DEX Business Reviewer | LSC Group, Ltd
Nigel Newling | D009 Work Package Report - Project Leader | DEX Project Leader | LSC Group, Ltd
Nigel Newling | C012 Referencing Task - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C016 Representing Person Organization - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C019 Assigning Approvals - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C020 Representing Life Cycle Opportunity - Editor | Capability Set Editor | LSC Group, Ltd
Nigel Newling | C020 Representing Life Cycle Opportunity - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C022 Representing Work Package - Editor | Capability Set Editor | LSC Group, Ltd
Nigel Newling | C022 Representing Work Package - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C025 Assigning Observation - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C027 Representing Location - Editor | Capability Set Editor | LSC Group, Ltd
Nigel Newling | C027 Representing Location - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C032 Representing Activity - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C045 representing product as individual - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C046 representing variance - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C059 representing work output - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C061 referencing scheme - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C062 representing scheme - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C064 representing work done - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C065 representing work order - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C066 representing work request - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C067 representing product as individual configuration - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C068 referencing product as individual configuration - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C069 referencing activity - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C071 referencing work order - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C072 referencing work request - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Nigel Newling | C074 referencing person organization - Project Leader | Capability Set Project Leader | LSC Group, Ltd
Nigel Newling | C081 representing product as realized assembly - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Tim King | C037 referencing documents - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C064 representing work done - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C065 representing work order - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C066 representing work request - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C071 referencing work order - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C072 referencing work request - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | C081 representing product as realized assembly - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim King | D004 Work Package Definition - Editor | DEX Editor | LSC Group, Ltd
Tim King | D008 Product as Individual - Model Reviewer | DEX Model Reviewer | LSC Group, Ltd
Tim King | D009 Work Package Report - Editor | DEX Editor | LSC Group, Ltd
Tim Turner | A2 Help Files | Ø Guide on how to write the XML for a DEX (dtds) | LSC Group, Ltd
Tim Turner | A4 Content A4.1 | Review the core capabilities | LSC Group, Ltd | Modelers CORE Team High priority | 400
Tim Turner | A4 Content A4.2 | Develop missing core capabilities | LSC Group, Ltd | Modelers CORE Team High priority | 20
Tim Turner | A6 Reference Data A6.1 | Harmonize modelers ref data | LSC Group, Ltd |  | 4 modelers 3 days workshop
Tim Turner | A6 Reference Data A6.2 | Review initial baseline of ref data | LSC Group, Ltd |  | 40
Tim Turner | C001 Assigning Identifiers - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C002 Representing Parts - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C003 Representing Assembly Structure - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C004 Representing Breakdown Structure - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C005 Representing Documents - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C006 Assigning Effectivity - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C019 Assigning Approvals - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim Turner | C063 representing product configuration - Model Reviewer | Capability Set Model Reviewer | LSC Group, Ltd
Tim Turner | C084 representing property value ranges - Business Reviewer | Capability Set Business Reviewer | LSC Group, Ltd
Tim Turner | C086 representing slots - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | C087 assigning document properties - Editor | Capability Set Editor | LSC Group, Ltd
Tim Turner | D001 Product Breakdown for Support - Editor | DEX Editor | LSC Group, Ltd
Tim Turner | D008 Product as Individual - Editor | DEX Editor | LSC Group, Ltd
Tim Turner Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | Tim Turner - Participation as member of Modelers CORE Team | See Tasks Assigned to Modelers CORE Team | LSC Group, Ltd
Chris Kreiler | A2 Help Files | Ø Guidance on How to Start a DEX | ManTech
Chris Kreiler | A2 Help Files | Ø Guide on how to “Launch a DEX” | ManTech
Tor Arne Irgens | A2 Help Files | Ø Process for developing DEX and Capabilities | Norwegian Defense Logistics
Tor Arne Irgens | A2 Help Files | Ø Guides for review and test | Norwegian Defense Logistics
Tor Arne Irgens | C041 representing state observed - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C055 representing project information - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C057 referencing product configuration - Model Reviewer | Capability Set Model Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C061 referencing scheme - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C062 representing scheme - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C075 referencing project - Business Reviewer | Capability Set Business Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C082 referencing contract - Model Reviewer | Capability Set Model Reviewer | Norwegian Defense Logistics
Tor Arne Irgens | C083 representing contract - Model Reviewer | Capability Set Model Reviewer | Norwegian Defense Logistics
John Spencer | C015 Representing Task - Business Reviewer | Capability Set Business Reviewer | Pennant International Group plc
John Spencer | C050 referencing resource - Business Reviewer | Capability Set Business Reviewer | Pennant International Group plc
John Spencer | C052 representing resource - Business Reviewer | Capability Set Business Reviewer | Pennant International Group plc
John Spencer | C088 representing task structure - Model Reviewer | Capability Set Model Reviewer | Pennant International Group plc
John Spencer | C089 representing task and state - Model Reviewer | Capability Set Model Reviewer | Pennant International Group plc
John Spencer | C090 representing task associations - Model Reviewer | Capability Set Model Reviewer | Pennant International Group plc
John Spencer | D002 Fault States - Model Reviewer | DEX Model Reviewer | Pennant International Group plc
Nik Barron | A2 Help Files | Ø Update HTML | Pennant International Group plc
Adrian Blenkiron | C007 Representing State Type - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C009 Referencing Product Breakdown Element - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C010 Assigning Reference Data - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C011 Representing Analysis Result - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C013 Representing Probability - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Adrian Blenkiron | C053 representing periodicity - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C055 representing project information - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | C075 referencing project - Project Leader | Capability Set Project Leader | Rolls-Royce
Adrian Blenkiron | D002 Fault States - Project Leader | DEX Project Leader | Rolls-Royce
Carolyn Cox | C037 referencing documents - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Carolyn Cox | D004 Work Package Definition - Business Reviewer | DEX Business Reviewer | Rolls-Royce
Carolyn Cox | D009 Work Package Report - Business Reviewer | DEX Business Reviewer | Rolls-Royce
Mike Day - RR? | A3 Test Data | Harmonize, update, and extend bike test data in S1000D format and compliance | Rolls-Royce |  | ???
Nigel Walker | C019 Assigning Approvals - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Nigel Walker | D001 Product Breakdown for Support - Project Leader | DEX Project Leader | Rolls-Royce
Nigel Walker | C001 Assigning Identifiers - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C002 Representing Parts - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C003 Representing Assembly Structure - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C004 Representing Breakdown Structure - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C005 Representing Documents - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C006 Assigning Effectivity - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C057 referencing product configuration - Business Reviewer | Capability Set Business Reviewer | Rolls-Royce
Nigel Walker | C084 representing property value ranges - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C086 representing slots - Project Leader | Capability Set Project Leader | Rolls-Royce
Nigel Walker | C087 assigning document properties - Project Leader | Capability Set Project Leader | Rolls-Royce
Johan Carlson | C007 Representing State Type - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C009 Referencing Product Breakdown Element - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C044 representing environment actual - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C048 representing condition evaluated - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C049 representing product location - Business Reviewer | Capability Set Business Reviewer | Saab
Johan Carlson | C058 representing justification - Business Reviewer | Capability Set Business Reviewer | Saab
Saab TBD | A3 Test Data | Harmonize, update, and extend bike test data in S1000D format and compliance | Saab |  | ???
Andy Burden (UKMOD) | C027 Representing Location - Business Reviewer | Capability Set Business Reviewer | UKMOD
Phil Rutland | D003 Task Set - Project Leader | DEX Project Leader | UKMOD
UKMOD or Les Debenham? | D007 Operational Feedback - Project Leader | DEX Project Leader | UKMOD
UKMOD TBD | A3 Test Data | Harmonize, update, and extend bike test data in S1000D format and compliance | UKMOD |  | ???
UKMOD TBD | C012 Referencing Task - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C013 Representing Probability - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C014 Messaging - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C015 Representing Task - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C020 Representing Life Cycle Opportunity - Business Reviewer | Capability Set Business Reviewer | UKMOD
UKMOD TBD | C022 Representing Work Package - Business Reviewer | Capability Set Business Reviewer | UKMOD
UKMOD TBD | C032 Representing Activity - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C041 representing state observed - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C043 representing environment typical - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C044 representing environment actual - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C045 representing product as individual - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C048 representing condition evaluated - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C049 representing product location - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C050 referencing resource - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C051 representing person organization typical - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C052 representing resource - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C058 representing justification - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C060 referencing product as individual - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C063 representing product configuration - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C064 representing work done - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C065 representing work order - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C066 representing work request - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C067 representing product as individual configuration - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C068 referencing product as individual configuration - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C069 referencing activity - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C070 referencing person organization typical - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C071 referencing work order - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C072 referencing work request - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C076 assigning product properties - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C077 assigning product properties - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C078 assigning resource properties - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C079 representing properties numerically - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C080 representing properties textually - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C081 representing product as realized assembly - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C085 representing resource as realized - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C088 representing task structure - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C089 representing task and state - Project Leader | Capability Set Project Leader | UKMOD
UKMOD TBD | C090 representing task associations - Project Leader | Capability Set Project Leader | UKMOD
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C??? representing codes - Business Reviewer | Capability Set Business Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C??? representing codes - Project Leader | Capability Set Project Leader
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C001 Assigning Identifiers - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C010 Assigning Reference Data - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C014 Messaging - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C016 Representing Person Organization - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C036 assigning date time - Model Reviewer | Capability Set Model Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C091 representing description - Business Reviewer | Capability Set Business Reviewer
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C091 representing description - Editor | Capability Set Editor
Modelers CORE Team Sean Barker Tim Turner Rob Bodington Leif Gyllstrom Trine Hansen | C091 representing description - Project Leader | Capability Set Project Leader
TBD | A1-1 DEXLib Infrastructure (Business Concepts) 1.7 | Provide a search mechanism for BCs |  | This would require a significant investment, so no hours quoted. | 0
TBD | A1-1 DEXLib Infrastructure (Business Concepts) 1.9 | Contingency |  |  | 0
TBD | A1-10 DEXLib Infrastructure (Activity Model) 10.1 | Provide index, navigable activity model integrated into DEXLib |  | Each DEX shows the sub set of the activity model. The full activity model should be navigable from here. | 80
TBD | A1-11 DEXLib Infrastructure (General) 11.1 | Maintain a decision site |  | A page on DEXLib listing the main decisions | 8
TBD | A1-11 DEXLib Infrastructure (General) 11.2 | Maintain an action list on DEXLib |  | Create an action list in DEXLib | 8
TBD | A1-2 DEXLib Infrastructure (Capabilities) 2.9 | Contingency
TBD | A1-3 DEXLib Infrastructure (Instance Diagramming Tool) | Instance diagramming tool |  | Provide facility for drawing instance diagrams that include capability macros. This may just be an agreed VISIO template or may be a tool. The hours estimate are for a tool. The tool will: - enable the drawing on instance diagrams that include capability macros - generate hyperlinks between EXPRESS entities defining the Capabilities - list a library of capability macros - instantiating a capability macro graphically from the library - facility to output a P28 and P21 file Note - this is a rough estimate of the whole job | 400
TBD | A1-4 DEXLib Infrastructure (Rules) 4.1 | Define rules for capabilities & DEXs |  | Define how to represent the rules, both text based and formal rules. This needs to be done collaboratively and will provide a specification NOTE - I am not sure that this is required once we have implemented the capability macros | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.2 | Modify capability & DEX DTD to include rules |  |  | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.3 | Modify capability & DEX XSL to display rules |  |  | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.4 | Update the mk_capability script to add rules section |  |  | 0
TBD | A1-4 DEXLib Infrastructure (Rules) 4.5 | Update the mk_dex script to add rules section |  |  | 0
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.1 | Define Conformance classes |  | Define how to specify a conformance class. This needs to be done collaboratively and will provide a specification. Estimate assumes that the SC4 approach used in modular AP will be adopted. | 16
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.2 | Update the mk_dex script to add conformance section |  |  | 4
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.3 | Define DTD to accommodate conformance classes |  |  | 4
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.4 | Create XSL to display conformance classes |  |  | 8
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.5 | DEX test data |  | Add a section in the DEX to list/index the test data for testing the compliance/conformance of the DEX and the exchange. Note, it is assumed that test data is available. | 24
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.6 | Define DTD to accommodate test data |  |  | 4
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.7 | Create XSL to display test data |  | Assuming a simple display - hyperlinks from instantiated entities will be require more effort. | 8
TBD | A1-5 DEXLib Infrastructure (DEXs) 5.8 | Update the mk_dex script to add test data section |  |  | 4
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.1 | Requirements analysis |  | Establish requirements for exchange contract. This should identify potentially what is the content of the exchange contract and how it might build on DEXLib. This should refer to the baseline of the DEXs, capabilities, modules | 120
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.2 | Define exchange contract |  | Define how to specify an exchange contract. This needs to be done collaboratively and will provide a specification. | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.3 | Define the DTD for the exchange contract |  |  | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.4 | Define mk_exchange_contract script |  | Mechanism for generating the exchange contract XML template | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.5 | Create XSL to display exchange contract |  | Mechanism for linking to a DEX conformance classes. Mechanism for linking to business concepts | 0
TBD | A1-6 DEXLib Infrastructure (Exchange Contracts) 6.6 | Develop standard text for exchange contract |  | This will require legal wording | 0
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.1 | Define how the baseline of the DEX, capabilities, modules, AP, reference data, and business concepts is managed, identified and represented in an exchange contract |  | Note - this should be picked up in the test document | 80
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.2 | Implement simple to use tool to create and view baselines |  |  | 200
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.3 | Document tool and baselining process |  |  | 40
TBD | A1-7 DEXLib Infrastructure (Configuration Mgmt of DEXLib) 7.4 | Maintain a released version of the modular AP |  | We need to extract a released version of the modules into DEXLib to ensure that the DEXs use controlled versions of modules. (The modules will be continuing being developed in STEPmod) | 16
TBD | A1-8 DEXLib Infrastructure (Publication) 8.1 | Maintain a mirror site of DEXLib that provides HTML access |  | Pennant International Group plc already provide a site- the scripts need to be updated to ensure that a complete build is done. | 16
TBD | A1-8 DEXLib Infrastructure (Publication) 8.2 | Install a mirror of capabilities for review |  |  | 4
TBD | A1-8 DEXLib Infrastructure (Publication) 8.3 | Release of capabilities for review |  |  | 4
TBD | A1-8 DEXLib Infrastructure (Publication) 8.4 | DEX publication approach |  | OASIS TC to agree on what is to be published. A DEX, A capability, a suite of DEXs? This is a prerequisite | 0
TBD | A1-8 DEXLib Infrastructure (Publication) 8.5 | Generate a version of the DEXs for OASIS review |  | At this stage, we are not sure whether the current form of a DEX will be acceptable to OASIS for publication. So generate one and see. | 16
TBD | A1-8 DEXLib Infrastructure (Publication) 8.6 | Modify DEX structure for publication by OASIS |  | Make the changes requested by OASIS. Not this dependent on 8.5 and no estimate effort can be made until the initial DEX has been reviewed. | 0
TBD | A1-9 DEXLib Infrastructure (Ref Data) 9.1 | Collaborative Ref Data development environment |  | This is to replace Protégé. This would require significant effort. Hence no effort estimated.
TBD | A1-9 DEXLib Infrastructure (Ref Data) 9.2 | Embed a link to the reference |  | Enable a link between the XSL displaying the reference data and the RDL server so allow the browsing of the reference data from DEXLib. This requires the support / maintenance of the RDL server. Hence no effort estimated.
TBD | A1-9 DEXLib Infrastructure (Ref Data) 9.3 | Facility to identify extensible / non extensible reference data |  | Mark ref data classes as "non" extensible. I.e. can not be extended by subclasses in business concepts | 4
TBD | A2 Help Files | Ø Develop templates for main rule types
TBD | A2 Help Files | Ø Develop scripts for business concepts, using rule templates
TBD | A6 Reference Data A6.3 | Reuse Ref Data from 15926
TBD | C041 representing state observed - Model Reviewer | Capability Set Model Reviewer
TBD | C082 referencing contract - Business Reviewer | Capability Set Business Reviewer
TBD | C083 representing contract - Business Reviewer | Capability Set Business Reviewer
TBD | D007 Operational Feedback - Business Reviewer | DEX Business Reviewer
TBD | D007 Operational Feedback - Model Reviewer | DEX Model Reviewer
Note on B71: Rob Bodington: Assumed 10 days per modeler
Note on B73: Rob Bodington: Assumed 10 days per modeler
Note on B145: Rob Bodington: Assumed 10 days per modeler
Note on B147: Rob Bodington: Assumed 10 days per modeler
Note on B148: Rob Bodington: Assumed 10 days per modeler
Note on B213: Rob Bodington: Assumed 10 days per modeler
Note on B215: Rob Bodington: Assumed 10 days per modeler
Note on B216: Rob Bodington: Assumed 10 days per modeler
Note on B360: Rob Bodington: Assumed 10 days per modeler
Note on B362: Rob Bodington: Assumed 10 days per modeler
Note on B363: Rob Bodington: Assumed 10 days per modeler
Note on E192: Rob Bodington: Should be UK-MOD We are not providing all funding
Note on G72: Rob Bodington: Increased
Note on G140: Rob Bodington: These hours are underestimates
Note on G208: Rob Bodington: These hours are overestimates
Note on G214: Rob Bodington: Increased
Note on G250: Rob Bodington: Increased
Note on G361: Rob Bodington: Increased
Note on I192: Rob Bodington: Should be UK-MOD We are not providing all funding