DEX Publication Project

Status Report #3

24 AUGUST 2007

| Date of first issue: | Project No: |  |
| --- | --- | --- |
| 24.08.2007 |  |  |
| Prepared by: | Organisational unit: |  |
| Trine Hansen |  |  |
| Approved by: Tor Arne Irgens |  |  |
| Client: | Client ref.: |  |
| Steering Group for ‘DEX Publication Project’ |  |  |
| Summary: |
| This report covers the progress for the project “DEX Publication Project” for the period 1 June 07 to 24 August 07. The report refers to Project Plan version 20070423. The project has made good progress in several activities last period. The financial situation is still critical for some activities. Progress In total the project is estimated to be approximately 6-7 weeks behind schedule. Without any further delay and sufficient access to resources the project may be completed by middle of October 07. The main reason are limited access to responsible editors of templates for resolving issues and overlaps prior to review activities limited access to responsible editors of templates that have to be updated prior to review activities limited access to editor of Help section limited access to editors of checklists Resource situation There is an urgent need to have a final commitment from all contributors of the projects with respect to available resources for the project Clarification about funding for resources for the following activities are needed: Responsible editors of templates for update according to resolved issues prior to review activities Responsible editors of templates (and capabilities) for updating according to review comments/issues Documentation of the DEXLib ‘Help’ section Updates of the Aviation Maintenance DEX as a follow-up of the harmonization activity Reference data checklist How to reduce/stop the delay Access to committed resources |
| Report No: | Subject Group: | Date of this revision: | Revision No: | Number of pages: |
|  |  | 24.08.2007 | 01 | 3+11 |
| Report title: |
| DEX Publication Project - Status Report #3 |

Table of Contents	Page

1	Project plan	1

2	Status	2

2.1	Management	2

2.2	Core Team Activities	2

2.3	TOG Support Management	3

2.4	Check lists and Processes	3

2.5	DEXLib infrastructure	3

2.5.1	Sub-activity ‘Templates’	3

2.5.2	Sub-activity ‘Acceptance test plan’	4

2.5.3	Sub-activity ‘Long form generation’	4

2.5.4	Sub-activity ‘Part 28 generation’	4

2.5.5	Sub-activity ‘Business DEX’	4

2.5.6	Sub-activity ‘Business Objects’	4

2.5.7	Sub-activity ‘Release environment’	4

2.5.8	Sub-activity ‘Usage reporting tool’	4

2.5.9	Sub-activity ‘General maintenance’	4

2.5.10	Sub-activity ‘Configuration change management’	4

2.5.11	Sub-activity ‘Configuration management of reference data’	4

2.5.12	Sub-activity ‘Publication as standard’	4

2.5.13	Sub-activity ‘Normalized form of OWL’	4

2.5.14	Sub-activity ‘Graphical Express’	4

2.5.15	Sub-activity ‘Graphical Instance’	4

2.5.16	Sub-activity ‘Test data’	4

2.6	DEXlib Help section	5

2.7	Develop, review and update templates	6

2.8	Develop, review and update capabilities	8

2.9	Develop and harmonize DEXs	8

2.10	Review and update DEXs	8

2.11	Preparations for establishing Implementers Forum	8

2.12	Final report	8

3	Progress	9

3.1	Estimated progress per 24 August 07	9

3.2	Comments to Progress	10

4	Used Hours and direct costs	11

# Project plan

Reference should be made to detailed project plan ‘DEX_Publication_Project_Plan_version_20070423.doc’.

The Figure below shows the project activities and schedule.

The vertical red line represents the date of this report.

# Status

This status report refers to the period 1 June 07 to 24 August 07.

The project has made good progress in several activities the last period, although funding for some activities are still not clear.

In the last status report a delay of approximately 4 weeks was reported. During the last period, the financial issues have not changed and the accumulated delay is per 24 August approximately 6-7 weeks. The estimate of 6-7 weeks delay is very uncertain due to availability resources if the financial issues are solved.

To stop the delay it is important to have all requested resources available for the project.

## Management

In this period the focus has been on

- Day-to-day management of the project

- Request review activities

- Arrange Core Team workshops and telecons

- Reports to Steering Group (total 3 Steering Group meetings in the period)

The following ‘events’ have been performed in the period:

- 1 June 07: Core Team telecon (Status)

- 4-5 June 07: Task DEX workshop in Stockholm (mapping scope, mapping solutions, documentation). Minutes not sent out yet

- 7 June 07: Core Team telecon (Comments to document ‘Introduction to PLCS components’)

- 7 June 07: Core Team telecon (Configuration management of reference data)

- 7 June 07: Steering Group telecon (#6)

- 12 June 07: OASIS TC telecon (Status report)

- 18 June 07: Core team face-to-face meeting in London (Reference data process)

- 20 June 07: Review request for ‘Help’ document ‘Short Introduction to components of PLCS’ sent out

- 21 June 07: Steering group telecon (#7)

- 21 June 07: Core Team telecon (Template status)

- 21 June 07: TOG issue resolution meeting (Check list issue)

- 26 June 07: Review request for Templates sent out

- 3 July 07: Core team face-to-face meeting in London (Template issues, DEX layout)

- 4-5 July 07: DEX 3 harmonization workshop in Oslo

- 4 July 07: Steering Group telecon (#8)

- 5 July 07: Review request for ‘Help’ document ‘PLCS-Why_should_I_care’

- 23 July 07: Telecon with OASIS to clarify publication requirements from OASIS

- 13 August 07: DEX 3 harmonization in Veksjø (Sweeden). Minutes not sent out yet (one Minute for all three workshops will be written)

- 20-23 August 07: Daily Core Team telecons. Templates and DEX structure

## Core Team Activities

The Core Team has been very active during the period, even if only 50% of the core team members have been involved.

The following activities have been performed in this period:

- Resolved several template issues (such as representation of properties, resources and codes)

- Reference data process has been discussed, tested and updated according to test results

- Help documents have been reviewed and commented before they were sent out for ‘formal’ review

- Establishing a review checklist for reference data and DEX is on-going

- Completed the review checklist for Templates

- Alternative grouping of capabilities have been discussed, recommendation will be presented for the Steering Group

- Several telecons and face-to-face meetings have been arranged

## TOG Support Management

For clarification of OASIS requirements a telecon was arranged 23 July with representatives from OASIS (Ram Kumar and Mary McRae).

The main conclusion from the meeting was:

- Subsets of DEXLib can be published with minor efforts (like OASIS copyrights on all HTML pages)

- Establish a ‘Cover page’ for the publications

A proposal for a ‘Cover page’ has been established and will be sent to OASIS for review/comments.

A tool has been developed to automatically extract subsets of DEXLib for publications. The tool development is reported under activity ‘Configuration Change Management’.

## Check lists and Processes

Review checklist for Templates

Review checklist for templates has been established.

Review checklist for Capabilities

Status: Established, but have to be updated according to the concluded DEX framework.

Review checklist for Reference data

Status: On-going

Review checklist for DEXs

Status: Started

Review checklist for DEXLib Help section

Status: Completed

Reference data process

Status: A process is agreed in the Core Team group

DEX publication process

Status: First proposal was drafted in the first Core Team workshop in Britol in February 07. The process was updated to meet the OASIS requirements in the Core Team workshop in London 18 June 07.

## DEXLib infrastructure

### Sub-activity ‘Templates’

Status: Completed

### Sub-activity ‘Acceptance test plan’

Status: Specification written as part of the revised detailed plan. Test plan activity not started.

### Sub-activity ‘Long form generation’

Status: Completed.

### Sub-activity ‘Part 28 generation’

Status: Completed.

### Sub-activity ‘Business DEX’

Status: Completed. The Business DEXs now have a similar structure to the DEXs. This means that a long form can be generated for a Business DEXs

### Sub-activity ‘Business Objects’

Status: Started.

### Sub-activity ‘Release environment’

Status: On-going. First draft expected ready for comments from OASIS by 3-4 weeks.

### Sub-activity ‘Usage reporting tool’

Status: Started.

### Sub-activity ‘General maintenance’

Status: On-going.

### Sub-activity ‘Configuration change management’

Status: On-going. Requirements agreed and implementation goes on.

### Sub-activity ‘Configuration management of reference data’

Status: Requirements agreed. Implementation goes on.

### Sub-activity ‘Publication as standard’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Normalized form of OWL’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Graphical Express’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Graphical Instance’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Test data’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

## DEXlib Help section

Two documents have been drafted, commented by the Core Team, updated and then sent out for formal review. Review comments have been received, but not forwarded to editors (will be done shortly).

The two documents are ‘Introduction to PLCS’ and ‘PLCS – Why should I care’.

A draft document of the process for handling reference data classes is also established. Practical tests have identified some issues which imply a need for a revised version of the document.

There is a challenge to have satisfactorily access to committed resources for this activity.

Review of ‘Introduction to PLCS’

Request for review was sent out 20 June 07 with a feedback date by 29 June 07. The review status is illustrated in table below.

| # | Request sent to | Received comments from |
| --- | --- | --- |
| 1 | Core Team | Core Team’s comments were included before review request was sent out |
| 2 | RollsRoyce | X |
| 3 | Mantech | X |
| 4 | Steering Group |  |
| 4-1 | NDLO | No |
| 4-2 | FMV | Comments provided through e-mails and discussed directly with editor |
| 4-3 | UK MOD | No |
| 4-4 | LOGSA | X |
| 4-5 | EPMT | General comments received, but should be further detailed |
| 4-6 | Eurostep | Incorporated in document before it was sent out for review. |
| 4-7 | BAESystems | X |
| 4-8 | DNV | No |

Status review of document ‘Introduction to PLCS’

Review of ‘PLCS – Why should I care?’

Request for review was sent out 5 July 07 with a feedback date by 27 July 07. The review status is illustrated in table below.

| # | Request sent to | Received comments from |
| --- | --- | --- |
| 1 | Core Team | X |
| 2 | RollsRoyce | X |
| 3 | Mantech | No |
| 4 | Steering Group |  |
| 4-1 | NDLO | No |
| 4-2 | FMV | No |
| 4-3 | UK MOD | No |
| 4-4 | LOGSA | No |
| 4-5 | EPMT | No |
| 4-6 | Eurostep | Comments were included before the document was sent out for review |
| 4-7 | BAESystems | X |
| 4-8 | DNV | No |

Status review of document ‘PLCS – Why should I care?’

## Develop, review and update templates

The previous status report reported that several issues had to be resolved prior to review of templates. Most of these issues are now resolved, but due to lack of funding, several templates are not updated according to agreement and therefore not ready for review. This is considered as a high priority issue.

104 templates are scope for this project (out of 129 recorded in DEXLib today). All are uploaded to DEXLib.

Request for review of 41 templates were sent out 26 June 07. Feedback by 3 August 07 was requested. Per 24 August 07 review of 25 templates have been reported completed. Table below illustrates the status.

20-25 additional templates are now ready for review and a new review request will shortly be sent out.

It is still a funding issue having templates issues resolved and updated. It is strongly recommended to use responsible editor for this work.

Table below illustrated status of the 41 templates requested for review 26 June.

| # | Template name | Sent out for review | Review completed |
| --- | --- | --- | --- |
| 1 | assigning_activity | EPMT | OK |
| 2 | assigning_calendar_date | EPMT | OK |
| 3 | assigning_contract | EPMT | OK |
| 4 | assigning_descriptor | DNV | OK |
| 5 | assigning_document | DNV, LOGSA | OK |
| 6 | assigning_location | DNV | OK |
| 7 | assigning_organization | DNV, LOGSA | OK |
| 8 | assigning_process_property | FMV | No |
| 9 | assigning_product_property | FMV | No |
| 10 | assigning_reference_data | DNV, LOGSA | OK |
| 11 | assigning_resource_property | FMV | No |
| 12 | assigning_time | EPMT | OK |
| 13 | assigning_work_output | EPMT | OK |
| 14 | property_value_relationship | FMV | No |
| 15 | representing_activity_actual | EPMT | OK |
| 16 | representing_breakdown | DNV | OK |
| 17 | representing_breakdown_element | DNV | OK |
| 18 | representing_breakdown_structure | DNV | OK |
| 19 | representing_contract | EPMT | OK |
| 20 | representing_count | FMV | No |
| 21 | representing_date_time | EPMT | OK |
| 22 | representing_geographical_location | EPMT | No |
| 23 | representing_message | FMV | No |
| 24 | representing_numerical_item | FMV | No |
| 25 | representing_organizational_location | EPMT | No |
| 26 | representing_part | DNV, LOGSA | OK |
| 27 | representing_physical_element | DNV | OK |
| 28 | representing_physical_structure | DNV | OK |
| 29 | representing_planned_activity | EPMT | OK |
| 30 | representing_product_as_realized | DNV | OK |
| 31 | representing_product_usage | EPMT | OK |
| 32 | representing_quantity | FMV | No |
| 33 | representing_typical_activity | EPMT | OK |
| 34 | representing_value_limit | FMV | No |
| 35 | representing_value_range | FMV | No |
| 36 | representing_value_w_tolerances | FMV | No |
| 37 | representing_value_with_unit | FMV | No |
| 38 | representing_work_order | DNV | OK |
| 39 | representing_zone_breakdown | DNV | OK |
| 40 | representing_zone_element | DNV | OK |
| 41 | representing_zone_structure | DNV | OK |

Status – Templates requested for review 26 June

## Develop, review and update capabilities

The Core Team has recommended prioritizing templates before the capabilities. The main reason for this is that DEX longforms will be generated from the templates.

The core team recommend re-structuring the capabilities. This will be presented for the Steering group in the next period.

## Develop and harmonize DEXs

‘Harmonization’ between the two Task DEXs is in progress.

Two face-to-face workshops have been performed in the last period.

Next workshop is planned 4-5 September.

## Review and update DEXs

Review of the Task DEXs is in progress as part of the activity ‘Develop and harmonize DEXs’.

Updates have not started.

## Preparations for establishing Implementers Forum

This activity is not started.

## Final report

This activity is not started.

# Progress

## Estimated progress per 24 August 07

The Figure below illustrates the estimated completed progress per activity.

Estimated progress per activity per 24 August 07

## Comments to Progress

This chapter describes the work done in the period since the previous Status Report.

| # | Main activity | Comments to progress |
| --- | --- | --- |
| 1 | Management | This activity runs according to plan. |
| 2 | Core Team activities | Core team workshops and meetings have been arranged according to plan. |
| 3 | TOG support management | Sub-activity ‘Identify OASIS requirements for having the DEXs (and related concepts) through ballot’ This activity is almost completed. Cover page and test publication set to be accepted by OASIS remains. Sub-activity ‘Identify requirements for tool support of future TOG management activities’ This activity has started as part of other activities in this project. Sub-activity ‘Propose procedures for handling request for external support such as training and consultancy services’ This activity is not started. |
| 4 | Check lists and processes | This activity has made progress in the last period, but is still behind original plan. Main reason is lack of access to resources. According to plan the deliverables from this activity should have been finished first week of June 07. The following checklists are not completed: Reference data, capabilities, DEX. |
| 5 | DEXLib infrastructure | This activity was started last period and has made good progress. Several sub-activities are reported completed (95% completion is reported until acceptance test have been performed). |
| 6 | DEXLib Help section | Progress has been made last period, but in total the activity is behind schedule, approximately 6 weeks. Main reason is lack of access to resources. |
| 7 | Develop, review and update templates | Progress on completing templates for review has been made the last period. There has also been made progress in the review activity. According to plan, this activity should have been completed 1st July 07. The activity is approximately 7 weeks behind schedule. |
| 8 | Develop, review and update capabilities | No progress last period. According to plan, this activity should have been completed 1st July 07. The activity is approximately 6 weeks behind schedule. |
| 9 | Develop and harmonize DEXs | This activity runs according to plan. |
| 10 | Review and update DEXs | This activity runs according to plan. |
| 11 | Preparations for establishing Implementers Forum | This activity has not started. |
| 12 | Final report | This activity has not started. |

Comments to Progress

# Used Hours and direct costs

This chapter will report used hours and direct cost when input is received from the Steering Group.

According to agreement the Project Manager shall report status and progress. The Steering Group is responsible for the overview of used hours and direct costs.