DEX Publication Project

Status Report

28 October 2007

| Date of first issue: | Project No: |  |
| --- | --- | --- |
| 15.11.2007 |  |  |
| Prepared by: | Organisational unit: |  |
| Trine Hansen |  |  |
| Approved by: Tor Arne Irgens |  |  |
| Client: | Client ref.: |  |
| Steering Group for ‘DEX Publication Project’ |  |  |
| Summary: |
| This report covers the progress for the project “DEX Publication Project” for the period 24 August 07 to 28 October 07. The report refers to Project Plan version 20070423. The project has made less progress than planned last period. The commitments of resources are critical for several activities. There is still a need for re-commitment as requested last month. The project has made less progress that planned the last period, mainly because of the un-clear funding situation and access to committed resources. Because of the resource situation the last period, it looks unrealistic to meet the first December milestone. A phasing of the deliverables has been concluded the last period. Capabilities will be postponed to a later phase. To prohibit further delay it is crucial to have all requested resources available for the project. Progress In total the project is estimated to be approximately 10 weeks behind schedule. Without any further delay and sufficient access to resources the project may be completed this year. The main reason are Late access to committed resources Un-clear financial situation for a long time Resource situation There is an urgent need to have a final commitment from all contributors of the projects with respect to requested tasks and resources. Phasing deliverables Phasing of deliverables was concluded last period: Completion of capabilities will be postponed to a later phase. How to reduce/stop the delay Access to committed resources |
| Report No: | Subject Group: | Date of this revision: | Revision No: | Number of pages: |
|  |  | 26.11.2007 | 01 | 3+11 |
| Report title: |
| DEX Publication Project - Status Report October 2007 |

Table of Contents	Page

1	Project plan	1

2	Status	2

2.1	Management	2

2.2	Core Team Activities	2

2.3	TOG Support Management	2

2.4	Check lists and Processes	2

2.5	DEXLib infrastructure	3

2.5.1	Sub-activity ‘Templates’	3

2.5.2	Sub-activity ‘Acceptance test plan’	3

2.5.3	Sub-activity ‘Long form generation’	3

2.5.4	Sub-activity ‘Part 28 generation’	3

2.5.5	Sub-activity ‘Business DEX’	3

2.5.6	Sub-activity ‘Business Objects’	3

2.5.7	Sub-activity ‘Release environment’	3

2.5.8	Sub-activity ‘Usage reporting tool’	3

2.5.9	Sub-activity ‘General maintenance’	3

2.5.10	Sub-activity ‘Configuration change management’	4

2.5.11	Sub-activity ‘Configuration management of reference data’	4

2.5.12	Sub-activity ‘Publication as standard’	4

2.5.13	Sub-activity ‘Normalized form of OWL’	4

2.5.14	Sub-activity ‘Graphical Express’	4

2.5.15	Sub-activity ‘Graphical Instance’	4

2.5.16	Sub-activity ‘Test data’	4

2.6	DEXlib Help section	4

2.7	Develop, review and update templates	4

2.8	Develop, review and update capabilities	4

2.9	Develop and harmonize DEXs	4

2.10	Review and update DEXs	4

2.11	Preparations for establishing Implementers Forum	5

2.12	Final report	5

3	Progress	6

3.1	Estimated progress per 28 October 07	6

3.2	Comments to Progress	7

4	Used Hours and direct costs	8

# Project plan

Reference should be made to detailed project plan ‘DEX_Publication_Project_Plan_version_20070423.doc’.

The Figure below shows the project activities and schedule.

# Status

This status report refers to the period 24 August 07 to 28 October 07.

The project has made less progress that planned the last period, mainly because of the un-clear funding situation and access to committed resources.

Because of the resource situation the last period, it looks unrealistic to meet the first December milestone.

A phasing of the deliverables has been concluded the last period. Capabilities will be postponed to a later phase.

To prohibit further delay it is crucial to have all requested resources available for the project.

## Management

In this period the focus has been on

- Day-to-day management of the project

- Propose phasing the deliverables (first phase delivers Task DEX, Aviation Maintenance DEX as a second phase) and reducing scope

- Arrange Core Team workshops and telecons

- Reports to Steering Group (total 3 Steering Group meetings in the period)

The following ‘events’ have been performed in the period:

- 27 August 07: Steering Group telecon (Status)

- 30 August 07: OASIS TC telecon

- 7 September 07: Telecon. Agenda: Phasing deliverables.

- 11 September 07: Steering Group telecon (Proposing phasing of deliverables)

- 14 September 07: Core team telecom

- 27 September 07: Steering Group telecon

- 1 October: Face-to-face TC meeting in Oslo

- 2-3 October: Task DEX harmonization workshop (Oslo).

- 12 October: Core Team telecom. Agenda: Status, with focus on Templates

- 15 October: Core Team Telecon. Agenda: DEXLib Help section

## Core Team Activities

This activity runs according to plan.

Several telecons have been arranged last period.

## TOG Support Management

Work on ‘Cover page’ is in the final phase.

This activity depends on activity for development of publication tool, see activity “DEXLib infrastructure”, sub-activities “Release Environment” and “Configuration Management”.

## Check lists and Processes

Review checklist for Templates

This activity is completed.

Review checklist for Capabilities

This activity will be postponed to a later phase.

Review checklist for Reference data

Status: On-going

Review checklist for DEXs

Status: On-going

Review checklist for DEXLib Help section

Status: Completed

Reference data process

Status: A process is agreed in the Core Team group but need to be revisited.

DEX publication process

On-going.

This activity depends on the Configuration Management activity.

## DEXLib infrastructure

### Sub-activity ‘Templates’

Status: Completed

### Sub-activity ‘Acceptance test plan’

Checklist for Acceptance test: on-going.

Acceptance test date is set to 26th November.

### Sub-activity ‘Long form generation’

Status: Completed.

### Sub-activity ‘Part 28 generation’

Status: Completed.

### Sub-activity ‘Business DEX’

Status: Completed.

The Business DEXs now have a similar structure to the DEXs. This means that a long form can be generated for a Business DEXs

### Sub-activity ‘Business Objects’

Status: On-going.

### Sub-activity ‘Release environment’

Status: On-going. First draft is available for review.

### Sub-activity ‘Usage reporting tool’

Status: On-going.

### Sub-activity ‘General maintenance’

Status: On-going.

### Sub-activity ‘Configuration change management’

Status: On-going. Requirements agreed and implementation on-going.

### Sub-activity ‘Configuration management of reference data’

Status: Requirements agreed. Implementation is on-going.

### Sub-activity ‘Publication as standard’

Good progress last period. 
Draft version of “Cover page” according to OASIS requirements has been established.

### Sub-activity ‘Normalized form of OWL’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Graphical Express’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Graphical Instance’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

### Sub-activity ‘Test data’

No funding for this activity is identified. For the time being this activity is defined as ‘out of scope.

## DEXlib Help section

Minor activities performed in September.

High activity in October.

## Develop, review and update templates

Development of templates is on-going, but progress is less than planned.

Review of templates is on-going, but progress is less than planned.

There is still a lack of commitments for update templates.

It seems unrealistic to have all templates reviewed and updated by 1st December 07.

## Develop, review and update capabilities

It was concluded in the OASIS TC meeting 1st October to postpone further development of capabilities to a later phase.

## Develop and harmonize DEXs

‘Harmonization’ between the two Task DEXs is some delayed since last workshop was cancelled because of illness. Next workshop is planned 21-23 November. This was originally ment to be the final workshop, but probably an additional early December is required.

DEX checklist is a delivery from this activity. The checklist is delayed due to the cancelled meeting.

## Review and update DEXs

Review of the Task DEXs is in progress as part of the activity ‘Develop and harmonize DEXs’.

Updates have not started.

Aviation Maintenance DEX is ready for review. Await checklist.

## Preparations for establishing Implementers Forum

This activity is not started.

## Final report

This activity is not started.

# Progress

## Estimated progress per 28 October 07

The Figure below illustrates the estimated completed progress per activity.

Estimated progress per activity per 28 October 07

## Comments to Progress

This chapter describes the work done in the period since the previous Status Report.

| # | Main activity | Comments to progress |
| --- | --- | --- |
| 1 | Management | This activity runs according to plan. |
| 2 | Core Team activities | Core team workshops and meetings have been arranged according to plan. |
| 3 | TOG support management | Sub-activity ‘Identify OASIS requirements for having the DEXs (and related concepts) through ballot’ This activity is almost completed. Cover page and test publication set to be accepted by OASIS remains. Sub-activity ‘Identify requirements for tool support of future TOG management activities’ This activity has started as part of other activities in this project. Sub-activity ‘Propose procedures for handling request for external support such as training and consultancy services’ This activity is not started. |
| 4 | Check lists and processes | This activity has made minor progress in the last period and is delayed according to plan. Main reason is lack of access to resources. The following checklists are not completed: Reference data, capabilities, DEX. |
| 5 | DEXLib infrastructure | This activity was started last period and makes progress according to plan. Several sub-activities are reported completed (98% completion is reported until acceptance test have been performed). |
| 6 | DEXLib Help section | Minor progress in September, but intensivated in October. The delay has increased from 6 to 9 weeks. Main reason is lack of access to resources. |
| 7 | Develop, review and update templates | Progress on completing templates for review has been made the last period. But less than planned. According to plan, this activity should have been completed 1st July 07. The activity is approximately 3 months behind schedule. |
| 8 | Develop, review and update capabilities | NA |
| 9 | Develop and harmonize DEXs | Progress made last period, but progress is behind schedule. Mainly because of access to key resources. |
| 10 | Review and update DEXs | Some progress made last period, but deliverables are still behind schedule. Review activities await checklist. |
| 11 | Preparations for establishing Implementers Forum | This activity has not started. Delayed according to plan. |
| 12 | Final report | This activity has not started. |

Comments to Progress

# Used Hours and direct costs

This chapter will report used hours and direct cost when input is received from the Steering Group.

According to agreement the Project Manager shall report status and progress. The Steering Group is responsible for the overview of used hours and direct costs.