## Goals
Overall Goal for the PLCS TC:
Improve quality of product data exchange, sharing and storage through life
Activities needed to reach the goal
Develop and standardize PLCS DEXs
Complete Task DEX and Aviation M DEX, which includes addressing ballot comments and complete the related capabilities
Have the two DEXs through an Implementers Forum
Develop Product Breakdown & Individual DEX
Develop and standardize web services to support PLCS

## Phase II activities
| Codes: | "From Phase I" means activities proposed for Phase I, but postponed to Phase II becasue of the funding situation
"DEX completion" points at deliverables required for completing the the two DEXs that are out for ballot (Task and Aviation Maintenance)
"For Impl. Forum" means activities with deliverables required by Implementers forum
"For new DEXs" points at activities with deliverables that have to be in place before new DEXs can be developed by "newcombers"
"NN" means that costs have not been estimated
# | Activity | Priority | Codes | Cost estimate (hours) | Cost estimate (hours) | Deliverables | Comments
1 | Program management | 1 | DEX completion | 800 | 800 |  | Coordinating external development, identify resources and prioritise internal projects, communicating and other management activities. Assume 2 days a week.
2 | Establish a funded project | 1 | DEX completion | 140 |  | Detailed project plan including budget and schedule | To be performed by project manager supported by the Steering Group of the project
2-1 | Identify project manager | 1 | DEX completion |  | 20
2-2 | Conclude on contributors | 1 | DEX completion |  | 40 |  | Preparations for establishing a Steering group
2-3 | Establish a detailed project plan | 1 | DEX completion |  | 80
3 | Project management (Phase II) | 1 | DEX completion | NN | NN | Status reports, minutes, presentations | 10% of total hours
4 | Address ballot issues | 1 | DEX completion | 940 |  | New ballot package for Task DEX and AM DEX. | Assume most comments are straight forward to address.
4-1 | Task DEX Templates | 1 | DEX completion |  | 80
4-2 | Task DEX Reference data | 1 | DEX completion |  | 130 |  | Core Team Reference data workshop: 4 participates, 4 days including travel ==> 4*4*8=128t
4-3 | Task DEX | 1 | DEX completion |  | 100
4-4 | AM DEX Templates | 1 | DEX completion |  | 80
4-5 | AM DEX Ref data | 1 | DEX completion |  | 130 |  | Core Team Reference data workshop: 4 participates, 4 days including travel ==> 4*4*8=128t
4-6 | AM DEX | 1 | DEX completion |  | 100
4-7 | Resolution workshops | 1 | DEX completion |  | 130 |  | Core Team Reference data workshop: 4 participates, 4 days including travel ==> 4*4*8=128t
4-8 | Address all Bugzilla issues | 1 | DEX completion |  | 150 |  | Review and address those relevenat for Task DEX and AM DEX
4-9 | New ballot packag | 1 | DEX completion |  | 40 |  | New ballot needed
5 | DEXLib infrastructure | 1 | DEX completion | 700 |  |  | Improve DEXLib to meet needs in Implementers Forum activities and ballot package requirements. Stepmod accessable in the ballot package. Functionality for communicating the "maturity" of PLCS.
5-1 | Access to Stepmod EXPRESS | 1 | DEX completion |  | 150 |  | OASIS requirement for the ballot package
5-2 | Status | 1 | DEX completion |  | 200 |  | Maturity of PLCS DEXs and templates. Agree method and implement it.
5-3 | Manage Test data | 2 | For Impl.Forum |  | 100 |  | Preparations for Implementers Forum activities. Proposal for how to handle test data in DEXLib. NO implementation.
5-4 | Class definitions show EXPRESS not OWL | 2 | For Impl.Forum |  | 50 |  | Functionality for showing the EXPRESS representation of reference data.
5-5 | Hyperlinking of diagrams | 2 | From Phase I |  | 200 |  | Functionality for hyperlinking from/to diagrams (Graphical Express). Add functionality to Graphical Express. Probably re-work all diagrams. May be under-sestimated.
6 | Management of "PLCS_resources" | 2 |  | 150 |  | Server up and running
6-1 | Managemenet of web site | 2 |  |  | 150 |  | Harware costs not included. Approx. 2 hours per week per year.
7 | Develop DEX Examples | 2 | For Impl.Forum | 850 |  | Specification for representation of DEX example data. DEX example data for Task DEX and AM DEX. | Develop example data: Examples of instantiations of the DEXs. Agree how to represent the example data. Should be in place prior to Implementers Forum (IF) activities. Contributes to test data activity of IF.
7-1 | Agree how to represent example data | 2 | For Impl.Forum |  | 150
7-2 | Examples for Task DEX | 2 | For Impl.Forum |  | 400
7-3 | Examples for AM DEX | 2 | For Impl.Forum |  | 300
8 | Reference data | 2 | For new DEXs | 300 |  | Specification for how to represent individuals and assigning codes. Agreed process for development of reference data. Reference data review checklist. Schema for normalized form for representing reference data.
8-1 | Technical issues | 2 | For new DEXs |  |  |  | Individuals, assigning codes. Part of the workshop
8-2 | Review process for development of ref data | 2 | For new DEXs |  | 160 |  | Core Team workshop. Assme 5 participants, 4 days including travel ==> 160
8-3 | Checklist | 2 | For new DEXs |  | 100
8-4 | Define schema for normalized form | 2 | For new DEXs |  | 40 |  | Establish a XML schema according to agreements.
9 | Information pages | 1 | From Phase I, For new DEXs | 500 |  | Documentation of: (1) How to use DEXLib, (2) user guidence for how to develop DEXs, capabilities, templates and reference data. Specification and implementation of extension of reference data with language construct | All these activities requires review and following discussions
9-1 | How to use DEXLib | 1 | From Phase I, For new DEXs |  | 150
9-2 | How to develop DEXs, templates, reference data | 1 | From Phase I, For new DEXs |  | 150 |  | Reuse deliveries from TLSS poject if possible
9-3 | Extension of ref data with language construct | 2 | From Phase I, For new DEXs |  | 100 |  | E.g. the Swedish version of reference data
9-4 | Review all Info pages and sort out | 2 | From Phase I |  | 100
10 | Capabilities | 2 | From Phase I, For Impl.Forum | 1950 |  | Reviewed capabilities for all templates related to Task DEX and AM DEX. Ready for ballot.Review checklist. Issues addressed. | User guidence for PLCS. Re-use existing documentation.Required by Implementers Forum
10-1 | Capabilities for Task DEX | 2 | From Phase I, For Impl.Forum |  | 600
10-2 | Capabilities for AM DEX | 2 | From Phase I, For Impl.Forum |  | 600
10-3 | Capability review checklist | 2 | From Phase I, For Impl.Forum |  | 150
10-4 | Review capabilities | 2 | From Phase I, For Impl.Forum |  | 300
10-5 | Address issues from review activities | 2 | From Phase I, For Impl.Forum |  | 300
11 | AP239 second edition | 2 |  | 1640 |  | Status report and analysis of what's needed to be done for next edition of AP239. Revise estimates in this plan if needed. Edition 2 of AP239 ready for ISO ballot. | Start when ballot issues are addressed. The estimates do not cover extended scope of AP239.
11-1 | Status review on the modules | 2 |  |  | 200 |  | Delivery: Estimate the work for edition 2.
11-2 | Compare ALL modules that are at a new form | 2 |  |  | 400 |  | May be over-estimated. Depends on status.
11-3 | Redo ARM | 2 |  |  | 100
11-4 | Update mapping tables | 2 |  |  | 300
11-5 | Update MIM | 2 |  |  | 300
11-6 | Rebuild longform | 2 |  |  | 40
11-7 | Ensure compatible with AP233 | 2 |  |  | 200
11-8 | Build ballot package and submit to ISO | 2 |  |  | 100
12 | Update Checklists | 2 | For new DEXs | 200 |  | Version 2 of review checklists for templates and DEXs.
12-1 | Template review checklist | 2 | For new DEXs |  | 100
12-2 | DEX review checklist | 2 | For new DEXs |  | 100
13 | Implementers Forum | 2 |  | NN | NN | Implementers forum
14 | Marketing | 2 |  | NN | NN | Marketing material. Participation in seminars etc. | Add PLCS AAM, White papers, success stories, manage external communication
15 | Harmonization with other standards/guidelines | 2 |  | NN | NN | Establish a policy / strategy for how to harmonize with other standards. | S1000D, 3000L, MIMOSA, OAGIS 9, SCORM etc.
16 | Develop and standardise Web Services | 2 |  | NN | NN
17 | Develop new DEXs | 3 |  | 5000 |  | 2 DEXs ready for ballot. | Re-use of existing templates and ref data. Harmonization activities are included, and are expected to take lot of time (based on experience). Recommendation from Core Team: Use Core Team resources as part of the development team
17-1 | Product Breakdown for support | 3 |  |  | 2500
17-2 | Product as individual | 3 |  |  | 2500
18 | Capabilities for new DEXs | 3 |  | 1250 |  | Capabilities specific for the 2 new DEXs ready for ballot. | 3 capabilities
18-1 | Capabilities for Product breakdown & Individual DEX | 3 |  |  | 500
18-2 | Capability review checklist | 3 |  |  | 150
18-3 | Review capabilities | 3 |  |  | 300
18-4 | Address issues from review activities | 3 |  |  | 300
19 | Extensions to the Template language | 3 |  | 750 |  | UML representation of AP239 and templates | Objective: Simplify use of PLCS
19-1 | AP239 as UML class diagram | 3 |  |  | 150
19-2 | Templates as UML class diagrams | 3 |  |  | 300
19-3 | Use of QVT/OCL as mapping language | 3 |  |  | 300
| SUM |  |  | 15170 | 15170
NOTE: Not all activities have estimated hours!