## Sheet1
Aggregate RLTC Schedule
2002-07-09
# | Description | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May
General Body
1 | RLTC Launch | May: 21
2 | Subcommittee Structure Developed and Launched | May: 21
3 | General Body Meetings | 21,29 | 12,26 | 10,24 | 7,21 | 4,18 | 2,16,30 | 13,27 | 11,tbd | 8,22 | 5,19 | 5,19 | 2,16,30 | 14,28
4 | Face to Face Meetings | May: 21; Sept: ?12/13; Nov: TBD; Feb: TBD; May: TBD
Governance-Liaison SC
1 | Liaison Request SC Draft Approved | July: 3
2 | MPEG Liaison Request SC Draft Approved | July: 3
3 | Liaison Request and MPEG Liaison Request RLTC Approved | July: 10
Requirements SC
1 | Requirements Gathering Process | June: 19; Aug: 7
2 | Requirements Categorization Process | June: 26; Aug: 14
3 | Requirements Disposition Process | July: 3; Aug: 21
4 | Requirements SC Draft Released | Aug: 28
5 | RLTC Requirements SC Draft Approved | Sept: 4
Core and Standard Specification SC
1 | Change Management Process and Template SC Draft Released | June: 12
2 | Change Management Process and Template SC Approved | June: 19
3 | Change Management Process and Template RLTC Approved | June: 26
4 | Change Management Process | June: 26; Sept: 10
5 | Change Requests Dispositioned-Spec Written/Edited | Sept: 10; Oct: 15
6 | SC Draft Spec Released | Oct: 15
7 | RLTC Review | Oct: 15; Nov: 13
8 | RLTC Spec Approved | Nov: 13
9 | Package Submitted to OASIS | bar: Dec
10 | OASIS Member Review Process | Jan: 1; Mar: 31
11 | OASIS Member Voting | April: 1-30
12 | OASIS Spec Approved | bar: May
Examples SC
TBD
Profiles SC
TBD
Extensions and Process Models SC
TBD