## LCSC Issues
Request Number | Requester | Date of Request | Issue | Team/s Involved | Why Needed | Comments | Priority | Impact | Status | Outcome
Each issue logged needs comments, discussion and final outcome. Lisa Seaburg is keeping a master list, please send her email with any new issue or comment on current issues. The list sent out on the mailing list is for your information only.
1 | LCSC | 2002-01-22 | Clear definition of Property Name, Object Term, and Representation Term | NDR | For Naming Definition | This may be more of a schema debate. | High | High
2 | Lisa Seaburg | 2002-01-23 | Teams using different versions of spreadsheets | LCSC | without this we can not use scripts for processing the data. |  | High |  | Done | Have spent Face to face time to compile the spreadsheets together and worked out the column headers together as a group. LAS
3 | Tim | 2002-01-23 | Should our UID be UDEF? (This is done manually, so this is another issue) | LCSC | Need to understand the UBL ID numbering and what it will be used for. | We could use this as a way to cross reference and check for duplicates. | 1-2 weeks
4 | LCSC-Tim, Gunther | 2002-01-23 | Naming and Design needs to make a decision for Types (simple and complex) | NDR | XSD output | We are capturing this information in the spreadsheet already. So, is this really an issue?
5 | LCSC | 2002-01-23 | Code Lists - how to maintain and where they come from, how they will be put into the XSD Schema | LCSC | When we build our schema for transactions, what will we put in? | Two recommended paths, one is the CC path, one is the xCBL path. The default is the xCBL lists (when no other is available).
6 | Lisa Seaburg | 2002-01-23 | Get the Min and Max occurrence description from XSD for Template | LCSC | XSD output
7 | Gunther | 2002-01-25 | Debate over the Datetime and Date format. | LCSC |  | This may be more of a schema debate.
8 | LCSC | 2002-01-25 | By creating open elements like the References.Details, we are opening up for a very large differences in the list of contents dependng on context. | LCSC |  | We need to constraint outselves to the world of what we are working within. |  |  | Done | We deleted the Refernece
9 | Arofan | 2002-01-25 | ACTION ITEM: Peter write up proposal for tools committee for using NetMeeting. | LCSC | This will enable continuous work.
10 | LCSC | 2002-02-05 | The separation of dictionary from tag names and how we manage that. Currently this is not addressed.
11 | Arofan | 2002-02-05 | Construct of spreadsheet, there is no way to indicate the difference between a child element that may be repeatable, and the case where you want to have a "ListOf" container element. |  | XSD output
12
13
14
15
16
17
18
19
20
21
22
23

## UBL Issues
Request Number | Requester | Date of Request | Issue | Team/s Involved | Why Needed | Comments | Priority | Impact | Status | Outcome
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18