## Sheet1
Comment Resolution Log for CACAO 1.1 CSD01 (first public review)
Prepared: | 2021-11-19
Comment # | Public review | Date provided | Link to email | Commenter | Category | Comment provided / Issue raised | TC decision on resolution | Comments / Changes
1 | CSD01 | 2021-08-12 | Publication Process | OASIS Staff | Editorial | There were some broken links that needed to be fixed that were found during the publication process for CSD01 | Accepted |  | DONE
2 | CSD01 | 2021-08-14 | In Google Doc | Allan Thomson | Editorial | Minor non-material editorial fix to remove white space in section 3.1 and add industry sectors property to example | Accepted |  | DONE
3 | CSD01 | 2021-08-14 | In Google Doc | Allan Thomson | Material | Section 3.1 change MUST to SHOULD for industry sector vocabulary use | Accepted | We will changes these to SHOULDs throughout the document | DONE
4 | CSD01 | 2021-08-14 | In Google Doc | Allan Thomson | Editorial | Example need to be updated and placeholder UUIDs need to be change to real UUIDs in sections 3.1, 4.4, 4.6, 4.7, 4.8, 7.1, 7.2, 8.2, 8.3, Appendix | Accepted | These changes have been made everywhere. | DONE
5 | CSD01 | 2021-08-14 | In Google Doc | Allan Thomson | Material | Section 6.12.1 is missing the new vocab entries | Accepted | These were added. | DONE
6 | CSD01 | 2021-08-14 | In Google Doc | Allan Thomson | Material | Conformance section needs to be updated to 1.1 | Accepted | Updated to 1.1 and added statements to support version interoperability | DONE
7 | CSD01 | 2021-08-14 | In Google Doc | Allan Thomson | Editorial | Update IANA considerations | Accepted | Made minor changes to reflect version 1.1 | DONE
8 | CSD01 | 2021-11-04 | Direct email to editors | Vaman Kini | Future | Add an enrichement playbook type | Review in future version | We will look at this in a future version of the specification | Future
9 | CSD01 | 2021-11-04 | Direct email to editors | Vaman Kini | Future | Add a Guardrail / Safety playbook type | Review in future version | We will look at this in a future version of the specification | Future
10 | CSD01 | 2021-11-04 | Direct email to editors | Vaman Kini | Future | Add users role to the identity in section 6 | Review in future version | We will look at this in a future version of the specification | Future
11 | CSD01 | 2021-11-24 | Direct Slack message to secretary | Vaughan Shanks | Material | Add spec_version and id properties in Data Marking Definition (section 8.1) | Accepted with changes | We added the spec_version and ID properties to the marking defintion common properties sections. | DONE
12 | CSD01 | 2021-11-24 | In Google Doc | Vasileios Mavroeidis | Editorial | Update text and examples with "1.1" for the version of spec used. See for example the "spec_version" proeprty in 3.1 | Accepted | In addition to examples, we need to update the descriptions for the property on the playbook object and the signature object. | DONE