## Sheet1
Comment Resolution Log for CACAO 1.1 CSD02 (second public review)
Prepared: | 2022-04-05
Comment # | Public review | Date provided | Link to email | Commenter | Category | Comment provided / Issue raised | TC decision on resolution | Comments / Changes
1 | CSD02 | 2022-03-09 | Publication Process | OASIS Staff | Editorial | There were some broken links that needed to be fixed that were found during the publication process for CSD01 | Accepted |  | DONE
2 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL | N/A | 2.3 - Question on best practices | Rejected | The TC discussed this on 2022-04-19 and decided to do nothing with this as it is implementation specific. | DONE
3 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL | Editorial | 3.0 - Add a should statement for UUIDv4 | Accepted | The TC discussed this on 2022-04-19 and decided to add a sentence at the top of the table that says that all data types are defined in section 9. | DONE
4 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | 6.2 - Questions about using Kali | Accepted | We will make some changes | DONE
5 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | 6.2 - Questions about using Caldera | Accepted | We will make some changes | DONE
6 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL | Minor | 6.11 - Question on passwords | Accepted | Added some text | DONE
7 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL | Minor | 6.11 - Question on private keys | Accepted | Added some text | DONE
8 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | 6.12.1 - Add or change entries in the vocab | Accepted | We will make some changes | DONE
9 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | 6.13 - More concerns about Kali and Caldera | Duplicate | Same as question in 6.2 | DUPLICATE
10 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | 6.15 - More concerns about Caldera | Duplicate | Same as question in 6.2 | DUPLICATE
11 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | 9.3 - Additional contact types | Not at this time | We may do this in the future. | REJECTED
12 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00008.html | JHU APL |  | A.1 - Add meta data to generate diagrams | Not at this time | Suggest submitter create a proposal or extension | REJECTED
12 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA |  | 2.1 - Asking about required steps for each playbook type | Accepted | The TC discussed this on 2022-04-19 and Marlon will provide an example of what he would like this to look like. | DONE
13 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Editorial | 2.3 - Derived from not defined | Accepted | Editorial fix | DONE
14 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Editorial | 3.0 - Spec_version formating | Accepted | Editorial fix | DONE
15 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 3.0 - Question about industry sectors | Accepted | The TC discussed this on 2022-04-19 and decided to add a statement here to capture the roll up | DONE
16 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 3.0 - Question about external_references | Accepted | The TC discussed this on 2022-04-19 and decided to do the same as industry sectors | DONE
17 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Material | 3.0 - Question about features | Accepted | The TC discussed this on 2022-04-19 and decided to add a normative statement and fix the description. Additional entries were add to the features vocabulary. | DONE
18 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Editorial | 3.0 - Question about playbook variables | Accepted | The TC discussed this on 2022-04-19 and decided to add some text in the description that talks about the scope of the variable and that these are like global variables for the entire playbook | DONE
19 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Material | 3.0 - Question about workflow_start | Accepted | The TC discussed this on 2022-04-19 and decided to fix description to say that the start record needs to be in the workflow itself so it is not referencing and make this property required and add a MUST statement that says you need at least a START, END, and one other step. | DONE
20 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Material | 3.0 - Question about workflow_exception | Accepted | The TC discussed this on 2022-04-19 and decided to fix description to ensure that it is part of the workflow. | DONE
21 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Material | 3.0 - Question about workflow | Accepted | The TC discussed this on 2022-04-19 and decided to make this required if it is not a template. | DONE
22 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 3.0 - Question about targets | Accepted | Added text like we did elsewhere to address similar comments | DONE
23 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 3.0 - Question about extension definitions | Accepted | Added text like we did elsewhere to address similar comments | DONE
24 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 3.0 - Question about data marking defintiions | Accepted | Added text like we did elsewhere to address similar comments | DONE
25 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Editorial | 3.0 - Question about example not formatted right | Accepted | Added spaces as needed | DONE
26 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 4.5 - Question about out_args | Accepted | Added text to in_args and out_args to address | DONE
27 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Minor | 4.6 - Question about multiple outputs | Accepted | Added text to in_args and out_args to address | DONE
28 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Editorial | 5.2 - Question about defanging | Accepted | Added text to explain this. | DONE
29 | CSD02 | 2022-03-24 | https://www.oasis-open.org/apps/org/workgroup/cacao/email/archives/202203/msg00009.html | CISA | Editorial | D.1 - Wrong reference for STIX 2.1 | Accepted | Fixed. Also fixed a few other references where the links were not hyperlinked | DONE
30 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 1.3 Difference between executable and template | Accepted | Added some proposed text to 1.3 | DONE
31 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.3 Some content is duplicative from 2.2 | Accepted | Added a reference to section 2.3 in section 2.2 to make it clear that is more info | DONE
32 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.4 Content seems out of place | Accepted | We will look into restructuring the section | DONE
33 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.5 Move to section 9.10 | Accepted | Moved the requirements to section 9.10 | DONE
34 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.5.1 Need descriptions for algorithms | Accepted | These entries were removed and changes made to 9.10.1 | DONE
35 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.5.1 Give example of explicit name | Accepted | Done, as part of the move to 9.10.1 | DONE
36 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.5.1 typo | Accepted | Done | DONE
37 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 2.5.1 change plural systems to system | Accepted | Done | DONE
38 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 Rq is too abbreviated | Accepted | Changed this to how we did it in STIX, needed to be done everywhere | DONE
39 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 id row, modified needs to be bold | Accepted | Done | DONE
40 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 optional rows are not marked as "N" | Accepted | Changed this to how we did it in STIX, needed to be done everywhere | DONE
41 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 created/modified row, change precise to given | Accepted | Done | DONE
42 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 revoked row, false needs to be bolded and blue | Accepted | Done | DONE
43 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 priority row, zero is not a possitive integer | Accepted | Changed to "number (W - whole number)". Also in severity and impact rows | DONE
44 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 priority, severity, and impact have different views of 100 | Accepted | Added some text | DONE
45 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 severity row, question about what "its" is referring to | Accepted | Added clarrifying text | DONE
46 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 severity row, are incidents and threats the only two | Accepted | Added "or a response to something else" | DONE
47 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 impact row, change 1st or first | Accepted | Done | DONE
48 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 markings row, plurality issue in normative statement | Accepted | Changed from "The IDs" to "Each ID" | DONE
49 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 3.0 targets row, represent data differently than stix | N/A | Nothing to do. | NOTHING TO DO
50 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 3.0 extension_definitions row, why not use STIX objects | N/A | Nothing to do. | NOTHING TO DO
51 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 example, include the steps that are used | Accepted | Made a note to add these | DONE
52 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.0 example, add "..." to signify some missing content | Accepted | Done | DONE
53 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.2 add some examples for each playbook type | Accepted | Added a note to add an example of each in 2.1 | DONE
54 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 3.3 add "n/a" in empty cell | Accepted | Done | DONE
55 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.1 replace value with integer | Accepted | Will rewrite / rephrase | DONE
56 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.1 add normative statements to on_failure and such | Accepted | Added normative statements that are just inverse of what is already there for the on_completion property, so it is not a material change as the statements already exist. | DONE
57 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 4.2 purpose of a start step | Accepted | Added some text in 4.3 to help explain this, that is was done on purpose. | DONE
58 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 4.3 purpose of a stop step | Accepted | Added some text in 4.4 to help explain this, and that it was done on purpose. | DONE
59 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Minor | 4.5 change name to "Commands Step" | Rejected |  | REJECTED
60 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.5 delete "one at a time" | Accepted | Done | DONE
61 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Material | 4.5 Explain why this is called a "single" action step | Accepted | This was renamed to be just "Action Step" | DONE
62 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Material | 4.5 target property should be targets. | Accepted | Renamed and added text. This was a problem in 4.7 as well | DONE
63 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.5 example does not have commands property | Accepted | Done | DONE
64 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.6 Where is the target type defined? | Accepted | Added reference to section 6 and a note in section 6 | DONE
65 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.6 Where is the playbook that is referenced? | Accepted | Added a note to address | DONE
66 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.7 Replace can not with cannot | Accepted | Done | DONE
67 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Material | 4.8 Dollar signs are not valid in STIX grammar | Accepted | Need to update our definitions, have made a note | DONE
68 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 4.10 description has match_probs but should be cases | Accepted | Done | DONE
69 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 5 what does stringified JSON mean? | Accepted | Added text. | DONE
70 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 5.2 fix example header for example 5.4 | Accepted | Done | DONE
71 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 5.2 fix example header for example 5.4 | Accepted | Done | DONE
72 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 5.2 fix example header for example 5.5 | Accepted | Done | DONE
73 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 6 Is there a way to capture infrastructure or software affected by the commands / steps? | N/A | That would be part of the STIX Incident object | NOTHING TO DO
74 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 6.3 Need examples for each of the targets | Accepted | Added note to do this. | DONE
75 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 6.10/1 sort vocab in alphabetical order | Accepted | Done | DONE
76 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 6.12 Where is the target type defined? | Accepted | Added note in section 6 to address | DONE
77 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 6.12.1Kali is both a target type and orchestration system type does that make sense? | Accepted | We will make some changes | DONE
78 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 6.12.1 example 6.5 add descriptive text | Accepted | We will make some changes | DONE
79 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 6.12 delete spaces in example | Accepted | Done | DONE
80 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 6.15 sort section in the order of the target-type-ov | Accepted | Add a note to do this. | DONE
81 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 7.1 extension definision example is not unique | Accepted | Done | DONE
82 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 7.1 another extension definision example is not unique | Accepted | Done | DONE
83 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 8.1 Why have the modified property? | N/A | To make things consistent and easier to code. | NOTHING TO DO
84 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Material | 8.4 consider using constant IDs like in STIX | Accepted | We made this change | DONE
85 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 8.4 typo | Accepted | Done | DONE
86 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Material | 9.4 Dictionaries have IDs and thus have a dash | Accepted | Done | DONE
87 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 9.7 Why do we have features? | N/A | Added a note to add some text. | DONE
88 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 9.10 revoked row, fixed style for "false" | Accepted | Done | DONE
89 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Question | 9.10 signee row, should this be a STIX identity? | Accepted | Added some text to help explain. | DONE
90 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 9.10 move references to names in RFCs to bottom of cell | Accepted | Done. Fixed in a few cells | DONE
91 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Editorial | 9.10 two different uses of b64url.encoded | Accepted | Fixed so we only use one. | DONE
92 | CSD02 | 2022-03-24 | https://lists.oasis-open.org/archives/cacao-comment/202203/msg00014.html | MITRE | Material | A.1 We are not consistent with step-- or start-- | Accepted | This was fixed, all steps and targets now use object-type--uuid | DONE
93 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | UUIDv5 generation for steps | Accepted | Made it clear to use UUIDv4 in most cases and only UUIDv5 for the playbook | DONE
94 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | Variable names in dictionaries have incorrect rules | Accepted | Fixed. Changed to be 200 characters | DONE
95 | CSD02 | 2022-05-03 | Slack | SAPPAN | Minor | Switch step case property dictionary problems | Accepted | Changed normative rule to allow keys to start with numbers | DONE
96 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | Target dictionary does not allow hyphens | Accepted | Already fixed | DONE
97 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | Workflow dictionary does not allow hyphens | Accepted | Already fixed | DONE
98 | CSD02 | 2022-05-03 | Slack | SAPPAN | Minor | Extend variable type vocabulary to allow float and bool | Accepted | Added float and bool | DONE
99 | CSD02 | 2022-05-03 | Slack | SAPPAN | Minor | Playbook and Playbook Steps have the same type value | Accepted | Playbook steps were renamed to "playbook-action" | DONE
100 | CSD02 | 2022-05-03 | Slack | SAPPAN |  | Merging of parallel steps | Accepted | Need to add text to watch for this. | DONE
101 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | 4.1 timeout property needs normative rule to say greater than or equal to zero | Accepted | Added rule similar to elsewhere | DONE
102 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | on_success and on_failure need rule to say if specified than on_completion must not be used | Accepted | Already fixed | DONE
103 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | targets and target_ids needs rule to say only one can be used. | Accepted | Already fixed | DONE
104 | CSD02 | 2022-05-03 | Slack | SAPPAN |  | playbook features types does not define behavior for undefined property | Accepted | Already fixed | DONE
105 | CSD02 | 2022-05-03 | Slack | SAPPAN |  | Parallel steps needs clarrification on waiting for steps to finish | Accepted | It must wait on the completeion of all sub steps and all branches that they launch | DONE
106 | CSD02 | 2022-05-03 | Slack | SAPPAN | Material | If and Switch steps should remote list of steps since that is already provided by the single and parallel steps | Accepted | Fixed in If, Switch, and While steps | DONE
107 | CSD02 | 2022-05-03 | Slack | SAPPAN |  | Allow data markings on steps | Rejected | The TC talked about this on 2022-05-17 and we decided to not do this at this time due to complexity issues. | REJECTED
108 | CSD02 | 2022-05-03 | Slack | SAPPAN |  | Problem with start and end steps | Rejected | Most modeling tools have ecplicit start and end indicators. These were added to CACAO to follow existing best practices. | REJECTED