## Tabelle1
Planned DSS-X Testing Activities 2013
Topic | Description | Schedule | Fixed Costs (in €) | Person days
Conformance Test Suite
Definition of conformance test suite | Assembling a useful test set of requests to ensure at least core compliance | January |  | 3
TAML assertions from Spec | Deriving the assertions from the core document. | February |  | 10
Review of DSS schema restrictions | Ensure that assertions expressed in the schema language match the requiremts exactly. Add TAML assertions when required. | February |  | 5
Conformance check facility | Setup an online or offline facility to perform the conformance checks on components. | January-April
- domain setup | Setup a special domain to host the conformance check facility. Costs estimated for one year. | January-February | 500 | 3
- server check | Apply the given set of requests against a DSS server 'under test' and validate the response. | March |  | 10
- client check (validating stub) | Accept incoming requests and validate their conformance. Return responses of a predefined set to test client's handling of valid responses. | April |  | 10
- reporting functionality | Give a summary of performed tests and their outcome. | April |  | 8
TEST SUITE DEFINITION | Define the scope of the events. This includes: - Decide profiles to be tested - For each spec identify the test cases |  |  | 20
DOCUMENTS TO BE GENERATED FOR THE PORTAL
Conducting Plugtests | Introduction, types of tests, before starting the plugtest, scope of the plugtest (what parts of the core, what parts of what profiles), conducting Signature Generation protocol tests, conducting Signature Validation protocol tests |  |  | 2
Interactions with the Portal | Figures of the powerpoint presentation discussed and agreed in their definitive form. Some explanatory text. |  |  | 1
Downloading material | Test cases and naming convetions. Organization of the material. It will provide details on how the material is stored within the portal…this includes requests, responses, and reports generated by the participants, which will help to build up the interoperability matrixes |  |  | 2
Testing Signature Generation Protocols | This document will provide full details on how to conduct the interoperability tests on the signature generation protocol, including interactions with the portal, naming conventions, instructions for uploading the material to the portal, etc |  |  | 3
Testing Signature Validation Protocols | As above but this time for the Signature Validation protocols. |  |  | 2
Cryptographic Material | High level overview of the PKI provided by the portal. Use optional. |  |  | 1
Document explaining test definitions language (OPTIONAL) | This document provides details of a XML language that describes the details of a test case. In this way, each test case can be defined using a XML file. Applications may parse this file and generate the corresponding DSS request….although this feature is optional, for other interoperability events has been present and helped to participants, which, on the other hand, had to develop software for parsing and processing this kind of files. |  |  | 10
XML files with details of the test cases (OPTIONAL) | XML files that describe the details of what parts of the protocol is tested in each test case |  |  | 4
Test cases document | HTML document that explains with text and tables the different test cases. |  |  | 4
UPDATE SCRIPTS FOR AUTOMATIC REGENERATION OF INTEROPERABILITY MATRIXES, AND TABLES WITHIN TESTS DOCUMENTS | This includes: . Scripts for uploading/downloading material . Scripts for automatic update of interoperability matrixes . Scripts for automatic computation of tables of the HTML document explaining the test cases, from the XML test definition files. |  |  | 15
DEFINING AND SETTING UP THE PKI AT THE PORTAL | The ETSI Portal incorporates a PKI that includes several trust frameworks with different roots, Cas, OCSP responders, CRLs, and Time-stamp Authorities. |  |  | 5
ETSI / OASIS InterOp
Coordination meeting |  | January | 1000
Getting public attention |  | April – June |  | 5
Non-public dry run
Support during the event | .This could be roughly estimated by 0,5 man per event's day…this asumes that there will be an organized event where participants and organizers will perform tests… |  |  | 0,5 x number of event's days
Rough Summing up (est. 450 € / Person day) |  |  | 1500 | 57600
(and planning for 10 event days i.e. 2 weeks)
Total |  |  |  | 59100