## README
NIEM F2F ¦ 2018 Fall Meeting Action Tracker |  | Version: v10 (12/7/18)
About
This workbook contains Action Items and Reminders (see Tabs below) captured
from the NIEM Face-To-Face (F2F) 2018 Fall Meeting.
Instructions
1) Review each tab (Action Items and Reminders) below.
2) FOR NIEM MO Only - For Action Items (Column E), provide an estimated level
of effort (LOE). If necessary, use Comments (Column N) to clarify scope of work.
3) FOR NBAC & NTAC Only - Use the Comments (Column M or N) on each worksheet
to provide any feedback.
ACTION ITEMS | REMINDERS
↓ | ↓

## Action Items
NIEM F2F ACTION ITEMS ¦ FALL MEETING 2018
| NBAC & NTAC |  |  | Last Updated: |  | 2018-12-07 |  |  | Next Meeting: |  | TBD
# | ACTION ITEM | PRIORITY | LOE | OWNER | AO POC | SUBJECT | TYPE | DONE | STATUS | SUSPENSE | NOTES | COMMENTS
AI-1 | Kamran provide Internet of Things (IoT) requirements guidance to the Emerging Technologies Tiger Team to define operational requirements (body wear device signaling capabilities, handheld devices, DNA systems, device-to-exchange environment, etc.) for NTAC technical architecture development including JSON | MEDIUM | 1st Qtr | Kamran Atri | Ralph O'Connell | Enterprise Standards Approach | NBAC |  | Not Started |  | Lain McNeill and Ajmal Aziz Emerging Technologies Tiger Team co-chairs
AI-2 | Onboard Grants as a NIEM Domain for long term preservation of Grant Data | MEDIUM | High | Kamran Atri Ryan Schultz | Heather Grace | Grants Data Management | NIEM MO |  | Not Started
AI-3 | Health Domain COI POC to provide HIPAA-compliant & PHI use case(s) with data model attributes and schema to determine NIEM support requirements, approach, and estimated level of effort (LOE) - Brian Handspicker provided PHI privacy markup schema 11/14/18 | HIGH | 4 weeks | Cait Ryan | Mark Dotson | Health Community | NBAC |  | Not Started |  | Other domains (Biometrics, MilOps, Human Services, etc.) have similar data safeguarding requirement; Include Chris Traver, Ryan Schultz, Kamran Atri involve in effort. Cait Ryan will be transitioning within the next ~3-4 months.
AI-4 | Support transition of NIEM Health COI leadership, FHA closing in September 2019 | MEDIUM |  | Ryan Schultz | Heather Grace | Health Community | NBAC |  | Not Started
AI-5 | Implement a NIEM IEPD Registry initial operating capability - Develop an execution plan - Define threshold and objective requirements | MEDIUM | 1st Qtr | Heather Grace Kamran Atri | Chuck Chipman | IEPD Registry | NBAC |  | Not Started
AI-6 | NIEM ESC Meeting Topic: NIEM International Data Strategy - Obtain ESC approval - Update NIEM.gov and other communication/documentation with approved language | MEDIUM | 2019-05-30 | Heather Grace | Mark Dotson | International | NBAC |  | Not Started
AI-7 | Support NIEM data model translations of into other languages | MEDIUM |  | International Tiger Team |  | International | NTAC |  | Not Started
AI-8 | Kamran provide JSON microservices examples that were developed by FEMA; provide to NTAC for review | MEDIUM | Low | Kamran Atri | Ralph O'Connell | JSON | NTAC |  | Not Started
AI-9 | Develop a plan for presenting the value of NIEM to senior leaders (SES level) within each domain and C-Suite level (e.g. CTO, COO, CFO) decision makers across agencies for NIEM adoption - Discuss during NBAC monthly teleconferences - Update Value of NIEM briefing materials - Coordinate with NBAC and domain stewards - Schedule engagements | HIGH | 1st Qtr | Ryan Shultz Kamran Atri | Heather Grace | NIEM Adoption | NIEM MO |  | Not Started
AI-10 | Develop a plan for presenting the value of NIEM to program managers (GS-15 level) within each domain for their support to conduct technical 'deep dives' | HIGH |  | Ryan Shultz Kamran Atri | Heather Grace | NIEM Adoption | NIEM MO |  | Not Started
AI-11 | Conduct technical 'deep dives' with data modelers and software developers within each domain to advance the implementation of NIEM conformant solutions | HIGH |  | Ralph O'Connell | Webb Roberts | NIEM Adoption | NIEM MO |  | Not Started |  | Conduct multi-day sessions to review schemas, engage domains over time with co-chairs & LNO leads; work through solutions to obstacles and challenges
AI-12 | Advance OMB as a NIEM policy champion | MEDIUM |  | Ryan Schultz | Heather Grace | NIEM Adoption | NIEM MO |  | Not Started
AI-13 | Engage agencies to get NIEM integrated into their data strategy and environments | MEDIUM |  | Heather Grace | Shunda Woodhouse | NIEM Adoption | NIEM Reuse |  | Not Started
AI-14 | Onboard Statistics domain (US Census Bureau) | MEDIUM |  | Ryan Schultz | Heather Grace | NIEM Adoption | NIEM MO |  | Not Started
AI-15 | Coordinate with Christina Bapst to understand PAO guidance on NIEM outreach communication (e.g. email, social media, etc) | HIGH | Low | Heather Grace | Shunda Woodhouse | NIEM Communications | NIEM MO |  | Not Started
AI-16 | Explore podcast and video communications strategy on NIEM.gov | MEDIUM |  | Heather Grace |  | NIEM Communications | NIEM MO |  | Not Started |  | Kamran can provide support for video.
AI-17 | Rename NIEM PMO to NIEM MO on NIEM.gov and other web sites, resources, and deliverables | MEDIUM |  | Heather Grace | Aubrey Beach | NIEM Communications | NIEM MO |  |  |  | Will need to look across web applications and update (both NIEM.gov and NEM.io)
AI-18 | Incorporate CDC data model content into NIEM for reuse (Nikoli) | MEDIUM |  | Kamran Atri | Ralph O'Connell | NIEM Data Model | NBAC |  | Not Started
AI-19 | Monthly Telecon Topic: Leverage NIEM domain configuration management best practices | MEDIUM |  | Heather Grace | Christina Medlin | NIEM Data Model | NBAC |  | Not Started
AI-20 | Incorporate Statistics data model content into NIEM 4.2 | MEDIUM |  | Heather Grace | Christina Medlin | NIEM Data Model | NBAC
AI-21 | Develop NIEM contract requirements language that can be plugged into a Statement of Work (SOW); use standard language (for government, commercial); include specific criteria and what NIEM conformance means | MEDIUM |  | NBAC |  | NIEM Expansion | NIEM MO |  | Not Started |  | Procurement integrity rules apply
AI-22 | Develop a formal requirements development and handoff process between NBAC and NTAC; NTAC will provide feedback, and progress will be tracked/reviewed routinely - NBAC/NTAC requests/requirements repository set up on GitHub | HIGH |  | Ralph O'Connell | Webb Roberts | NIEM Requirements | NIEM MO |  | 25% |  | https://github.com/NIEM/NBAC-NTAC-collaboration/issues
AI-23 | Provide Architectural requirements for NIEM 5.0 to the NTAC | MEDIUM |  | NBAC |  | NIEM Requirements | NBAC |  | Not Started
AI-24 | Monthly Telecon Topic: Update NIEM Vision statement, coordinate with NBAC | MEDIUM |  | Heather Grace | Ralph O'Connell | NIEM Strategic Planning | NIEM MO |  | Not Started
AI-25 | Monthly Telecon Topic: NIEM 2019 Strategic Goals - NIEM 20110/2019 Strategy posted to GitHub - Align with Federal Data Strategy (Dr. Carrino provided copy) - Coordinate with NBAC - Obtain ESC approval | MEDIUM | 1st Qtr | Heather Grace | Ralph O'Connell | NIEM Strategic Planning | NIEM MO |  | 25% |  | Leverage the 2010 NIEM Strategic Goals approved by ESC. Proceed with review of Federal Data Strategy Artifacts, NDAA Language, and CIO Council Recommendations. Looking to provide an update to NBAC in January with measures and metrics for FY19 assessment towards NIEM Advancement (Data) Strategy.
AI-26 | Update the NIEM Tools User Agreement (UA) and post to NIEM.Gov | HIGH | Low | James Cabral | Aubrey Beach | NIEM Tools | NIEM MO |  | Not Started |  | James noted 3 specific concerns; (1) reference to production capability (these are vendor references); (2) use of the word "NIEM" in the name/title of the tool; (3) do not let people rate tool publicly
AI-27 | Improve SSGT want list error message processing | MEDIUM |  | James Cabral | Dave Hardy | NIEM Tools | NTAC |  | Not Started
AI-28 | Produce a 3-5 page whitepaper on NIEM Tools that identifies critical gaps, proposed architecture, and a rationale for why they are needed; goal is to arm NIEM MO with artifact to obtain funding to support further tool development | MEDIUM |  | NTAC | Dave Hardy | NIEM Tools | NTAC |  | 25%
AI-29 | Develop ICAM/IDAM information exchange requirements and use cases | MEDIUM |  | Ralph O'Connell | Mark Dotson |  | NBAC |  | Not Started

## Reminders
NIEM F2F REMINDERS ¦ FALL MEETING 2018
| NBAC & NTAC |  | Last Updated: |  | 2018-12-07 |  |  | Next Meeting: |  | TBD
# | REMINDER | PRIORITY | OWNER | AO POC | SUBJECT | TYPE | DONE | STATUS | SUSPENSE | NOTES | COMMENTS
R-1 | Review Health 201 documentation to be provided by Cait Ryan; provide assistance with Health Domain COI prior to publication on GitHub repository | MEDIUM | Cait Ryan |  | Health Domain |  |  | Not Started |  | Brian Handspicker noted on 11/14 that he will "post the NIEM Health 201 document once [he has] finished rewriting it. Webb requested a draft copy if possible.
R-2 | Investigate Coast Guard IEPD use case to see where it can be leveraged in Health Domain; Dr. Apple to provide POC | MEDIUM | Cait Ryan |  | Heath Domain | ADMIN |  | Not Started
R-3 | Based on Kamran's proposal to provide 1 FTE as a resource to developing an IEPD Registry MVP, but contigent upon a Jan 1, 2019 launch date and Jan 15, 2019 IEPD upload by each domain, Heather will provide a response within 1 week after internal discussions and assessment of scope of effort. | MEDIUM | Heather Grace |  | IEPD Registry |  |  | Not Started
R-4 | Provide POC's to Ryan to facilitate DoD discussions (see AI-15) | MEDIUM | Jerry Christman |  | IEPD Registry |  |  | Not Started
R-5 | Share Counterterrorism use case with Dr. Apple to see where it can be leveraged in Maritime Domain | MEDIUM | Heather Grace | Shunda Woodhouse | Maritime Domain | ADMIN |  | Not Started
R-6 | Christina Bapst to provide Ryan with information on how to handle NIEM conferences | MEDIUM | Christina Bapst |  | NIEM Governance | ADMIN |  | Not Started
R-7 | Share any past NIEM marketing/outreach campaign deliverables and lessons learned with Heather | MEDIUM | Christina Bapst |  | NIEM Strategic Planning | ADMIN |  | Not Started
R-8 | Each domain will provide input into broadening the current Executive Steering Committee (ESC); Identify person within organization that will champion NIEM and commit resources | MEDIUM | ALL |  | NIEM Strategic Planning |  |  | Not Started
R-9 | Ralph to update slides based on feedback provided from participants and obtain approval of revisions prior to NBAC/NTAC Strategic Planning meeting | MEDIUM | Ralph O'Connell |  | NIEM Strategic Planning |  |  | 100%
R-10 | Share security protocols for IoT Devices with Kate Silhol | MEDIUM | Kamran Atri |  |  | ADMIN |  | Not Started
R-11 | Ryan to have a sidebar with Chris Traver re: insight into adoption of pieces of NIEM (NATO Use Case) | MEDIUM | Ryan Schultz |  |  | DEVELOPMENT |  | Not Started
R-12 | Research requirements and procedures of the Defense Innovation Data Day, sponsored by Defense Innovation Board (DIB) | MEDIUM | Heather Grace |  |  |  |  | Not Started
R-13 | Provide Dr. Guha with MilOps list of organizations | MEDIUM | Ralph O'Connell, Ryan Schultz |  |  | ADMIN |  | Not Started
R-14 | Provide Ryan Schultz with Lain's slides (e.g. "89 JSON standards, choose one!") from NTAC brief for future marketing purposes | HIGH | Dave Hardy |  |  | NIEM Marketing | NTAC
R-15 | Send NIEM JSON slides to Thomas Freed | MEDIUM | Mark Dodson |  |  | Biometrics Domain | NIEM MO | Not Started |  | Mark self-assigned task on 11/13