## Sheet1
Type	JIRA	Summary	Source	Severity	New Severity	Target	Notes
New Feature	OFFICE-212	Integrate "Intelligence Community Information Security Markings" with ODF?	comment-form@oasis-open.org Original date: 23 May 2005 22:10:33 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200505/msg00003.html	Minor	Major	?	404 for link in email. Try: http://www.dni.gov/index.php/about/organization/chief-information-officer/information-security-marking-metadata Could this be adapted to our RDF metadata? Worth contacting the government to see if they will contribute work cycles.
Task	OFFICE-260	Broken link on PDF page 2	comment-form@oasis-open.org Original date: 19 Oct 2005 05:21:00 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200510/msg00021.html	Minor	Minor	close	Close as we verify all links for drafts.
New Feature	OFFICE-286	Proposal to allow multiple markups within an ODF document	comment-form@oasis-open.org Original date: 27 Feb 2006 16:49:09 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200602/msg00000.html	Major	Major	1.3?	Embedding non-ODF markup/code for processing by non-ODF applications. Interest from implementers?
New Feature	OFFICE-228	Font Embedding	comment-form@oasis-open.org Original date: 30 Aug 2005 03:58:05 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200508/msg00003.html	Major	Major	1.3?	Q: Are any implementers interested in embedding of fonts as a new feature?
Improvement	OFFICE-298	Seeks formal content model of ODF	Bryce Nordgren Original date: 28 Apr 2006 18:14:49 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200604/msg00004.html	Minor	Major	1.3?	Requests a formal data model (UML, etc.) - Would help with the change tracking but also a lot of work. Quite old, 2006.
Task	OFFICE-220	Annotating the RelaxNG schema of ODF	comment-form@oasis-open.org Original date: 14 Jun 2005 08:04:18 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200506/msg00003.html	Major	Minor	?	The proposed annotation returns 404. Unless someone on the TC wants to annotate a separate version of the schema. Changed to new feature.
Task	OFFICE-296	Would like ODF to allow "semantic markup at smaller granularities than at the document level"	Melanie Kendell Original date: 21 Apr 2006 02:18:50 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200604/msg00002.html	Major	Minor	N/A	Updated to be a new feature and one that is satisfied by our current RDF support. Suggest close.
New Feature	OFFICE-638	office-formula: FFT functions?	"Steven G. Johnson" <stevenj@fftw.org> Original date: 28 Jan 2008 22:58:34 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200801/msg00050.html	Minor	Minor	close	Duplicate of Office-657 and Office-659, close, point to Office-659
New Feature	OFFICE-645	Allow saving a comment additionally to a defined name	"Leonard Mada" <discoleo@gmx.net> Original date: 11 Feb 2008 22:07:43 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200802/msg00006.html	Minor	Minor	close	Wants to “allow saving a comment in addition to a name” Isn't this covered by RDF metadata?
Bug	OFFICE-652	[office-formula] predraft 8 of 2007-12-28, section 6.9.6, function days360 comment	Roel <oasis@prsystems.be> Original date: 13 Feb 2008 21:30:42 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200802/msg00013.html	Minor	Minor	close	Error in test case, which no longer appears in the standard
New Feature	OFFICE-653	Additional Directives to Functions to Trigger Special Behaviour	"Leonard Mada" <discoleo@gmx.net> Original date: 13 Feb 2008 22:39:42 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200802/msg00014.html	Minor	Major	close	Wants global IGNORE_ERR (ignore cell with error and evaluate function without considering that cell) – Don't we have that with Part 2, 4.6 Error and specific language for functions where errors can be ignored? Also wants interpret text as number, Part 2, 6.3.5 Conversion to Number defines this conversion as implementation dependent
New Feature	OFFICE-657	Add FFT() to formula spec?	"David A. Wheeler" <dwheeler@dwheeler.com> Original date: 16 Feb 2008 18:52:43 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200802/msg00018.html	Minor	Minor	close	Duplicate of Office-638 and Office-659, close, point to Office-659
New Feature	OFFICE-659	FFT() and IFFT to formula spec?	"Leonard Mada" <discoleo@gmx.net> Original date: 20 Feb 2008 00:49:19 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200802/msg00020.html	Minor	Minor	ODF1.3	In email, Rob Weir suggests FFT() Andreas Guelzow suggests he can write up the proposal. You can see all the emails on this issue at: http://markmail.org/search/?q=FFT%28%29&q=list%3Aorg.oasis-open.lists.office-comment
Improvement	OFFICE-669	Proposes different data structures for indexing	"Timothy S. Nelson" <wayland@wayland.id.au> Original date: 25 Apr 2008 05:49:57 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200804/msg00008.html	Major	Major	ODF-Next?	You can see the full proposal here: http://computerstuff.jdarx.info/content/how-improve-openofficeorg-writer-indexing - I agree it would be a vast improvement but it would require significant changes to make it happen. Perhaps if we consolidate all the empty element mechanisms in ODF-Next, this would be far easier. Thoughts?
Bug	OFFICE-674	Re: [office-comment] ODFF: list of suggestions	Leonard Mada <discoleo@gmx.net> Original date: 2 May 2008 19:39:46 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200805/msg00001.html	Minor	Major	?	I think Dennis makes a strong argument on the dispositon of this one. Since we are past ODF 1.2, is this even fixable? Email traffic on this issue: http://markmail.org/search/?q=%22list+of+suggestions%22&q=list%3Aorg.oasis-open.lists.office-comment#query:%22list%20of%20suggestions%22%20list%3Aorg.oasis-open.lists.office-comment%20order%3Adate-forward+page:3+state:facets not all posts are relevant to this issue, sorry.
Bug	OFFICE-688	Remaining issue: Alternative to XSD datatypes?	"Alex Brown" <alexb@griffinbrown.co.uk> Original date: 10 May 2008 06:03:50 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200805/msg00015.html	Major	Major	ODF-Next	The original issue is resolved, question is whether the TC wants to investigate alternatives to XSD datatypes? If yes, then close this issue and open up a task with that description.
Bug	OFFICE-704	Should elements/attribute names in titles be followed by short translatable text?	"Dennis E. Hamilton" <dennis.hamilton@acm.org> Original date: 18 May 2008 07:45:09 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200805/msg00031.html	Minor	Major	ODF-Next?	I marked this as major simply because of the amount of time required to produce and proof the requested text. But it does strike me as a good idea.
Task	OFFICE-730	XML declarations required for ODF when encoding other than UTF-16 or UTF-8 is used.	"Dennis E. Hamilton" <dennis.hamilton@acm.org> Original date: 30 May 2008 16:58:06 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200805/msg00057.html	Minor	Minor	close	XML 1.0 (4th edition) provides: “it is also a fatal error if an XML entity contains no encoding declaration and its content is not legal UTF-8 or UTF-16.” Would be an invalid XML document. To complete the circle, ODF 1.2, part 2, 2.2.1 B1 OpenDocument Document provides: “The files shall be well formed XML documents with respect to XML 1.0 [XML 1.0] specification.” I am assuming that well-formed means a lack of fatal errors, although XML 1.0 doesn't explicitly say that.
New Feature	OFFICE-734	Statistical SUMMARY() function	Leonard Mada <discoleo@gmx.net> Original date: 2 Jun 2008 22:27:09 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00003.html	Major	Major	close?	Are there any implementations with this function? See Wheeler's comment.
Bug	OFFICE-737	Name change for attribute, ODF 1.2, part 3, 4.8.3 manifest:checksum-type	"Hanssens Bart" <Bart.Hanssens@fedict.be> Original date: 3 Jun 2008 12:46:28 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00006.html	Minor	Minor	close?	Agree that manifest:checksum-name would be a better name for this attribute but since it appears in 1.2, do we want to change it in ODF 1.3?
New Feature	OFFICE-740	Redefining NA? To aline with R?	Leonard Mada <discoleo@gmx.net> Original date: 3 Jun 2008 18:42:03 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00009.html	Blocker	Minor	close	In light of part2, 6.13.27 NA, is there any reason to keep this issue open?
Improvement	OFFICE-742	Extending the PERCENTILE() Function	Leonard Mada <discoleo@gmx.net> Original date: 3 Jun 2008 20:34:14 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00011.html	Minor	Minor	ODF 1.3	Check ODF Part 2, 6.18.57 PERCENTILE to see if we need to extend PERCENTILE. The proposed extension: Syntax: PERCENTILE( NumberSequence Data ; NumberSequence x )
New Feature	OFFICE-747	Email discussion that relates to OFFICE-740	Leonard Mada <discoleo@gmx.net> Original date: 3 Jun 2008 22:27:05 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00016.html	Trivial	Trivial	close	Point back to Office-740
New Feature	OFFICE-752	Statistical SUMMARY() function	Sheldon Britton <sab_orion@verizon.net> Original date: 4 Jun 2008 15:16:16 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00021.html	Minor	Major	close	Point to Office-734
New Feature	OFFICE-758	Request for Economic Rate of Return function	Sheldon Britton <sab_orion@verizon.net> Original date: 4 Jun 2008 19:34:57 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00027.html	Minor	Minor	ODF 1.3?	See the attachement to: https://lists.oasis-open.org/archives/office-comment/200806/msg00027.html to evaluate this issue.
New Feature	OFFICE-765	Extending the PERCENTILE() Function	Leonard Mada <discoleo@gmx.net> Original date: 6 Jun 2008 22:37:32 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00034.html	Minor	Minor	close	Point to Office-742
Bug	OFFICE-779	Border styles on style:columns and style:column elements	Sander Marechal <sander.marechal@tribal-im.com> Original date: 17 Jun 2008 09:38:24 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200806/msg00048.html	Major	Minor	ODF 1.3	fo:border-*, fo:margin-*, fo:padding-* on style:columns and style:column elements
Bug	OFFICE-898	odf 1.1 validity error, example for 4.2	"Dave Pawson" <dave.pawson@gmail.com> Original date: 16 Jul 2008 10:05:29 -0000 Original URL: http://lists.oasis-open.org/archives/office-comment/200807/msg00094.html	Minor	Minor	close	Examples no longer appear in ODF and we are unlikely to produce another errata for ODF 1.0