## Plans (status 2004-10-19)
Schedule for completion of PLCS IS |  |  | Total hours: | 1100 | Contigency: | 80 | Hours remaining
| Task |  | Responsible | Remaining hrs | Status | Comment
T1 | Project management |  | Rob Bodington | 20
T2 | Issue management
|  | Baseline issue logs | Rob Bodington | 8 | 70%
|  | Ballot comment resolution workshop | Nigel Shaw Tim King | - | 100% | Held in St Asaph + Seattle.
|  | Raise SEDS for all issues | Rob Bodington | 0 | 100% | Assuming that we need to do this. We understand that we do not
T3 | Publication issues
|  | Addition of French titles | Darla Nettles | 2 | 100% | Completed - but needs checking. See T4.4
|  | ISO boilerplate changes | Rob Bodington | 0 | 90% | Believe complete - need confirmation from ISO | Effort recently funded by Eurostep
|  | Separating out the abstract for publication | Rob Bodington | 4 | 90% | Believe complete - need confirmation from ISO | Effort recently funded by Eurostep
T4 | XSL issues
T4.1 |  | Boilerplate changes / bug fixes | Rob Bodington | 8 | 90% |  | Effort recently funded by Eurostep
T4.2 |  | AP Index - modify display | Nigel Shaw | 8 | 40%
T4.3 |  | Technical discussion Annex | Rob Bodington | 8 | 0% | Modify XSL to handle clauses and update table of contents
T4.4 |  | ISO cover pages | Rob Bodington Tom Hendrix | 4 | 90% | Need to add a check that French titles have been added Need to modify all build processes to ensure that cover is created | Effort recently funded by Eurostep
T5 | AP document
|  | Introduction | Nigel Shaw | 8 | 0%
|  | Scope | Rob Bodington | 8 | 0%
|  | Implementation Annex C | Nigel Shaw | 8 | 0%
|  | PICS form Annex D | Rob Bodington | 8 | 0%
|  | AAM corrections | Tim King | - | 75% | Some changes still to be made / discussed
|  | AAM conversion to XML | Nik Barron | - | 0%
|  | Annex H: Technical discussion | Nigel Shaw | 32 | 0%
T6 | AP validation report |  | Rob Bodington | 0 | 100% | assume no action is required
T7 | PDM Modules major issues to be addressed
|  | Document | Tom Hendrix | -
|  | Representation | Tom Hendrix | -
|  | For each module: | Tom Hendrix Rob Bodington | 8 | 60% | 9 issues remaining. Effort required to coordinate check that issues have been addressed
|  | Address issue | Tom Hendrix | -
|  | Ant check | Tom Hendrix | -
|  | QC check | Tom Hendrix | -
|  | Publish | Tom Hendrix | -
T8 | PLCS Modules major issues to be addressed |  | PLCS modellers |  |  | Effort can not be estimated until the ballot comment resolution workshop. For each module: Address Issue, Redraw EXPRESS-G, generate Express, redo mapping, add WG numbers, run ANT checks, do QC check, Publish
T8.1 |  | Global rules |  | 20 | 0% | We need to refer to the mapping rules in the XSL - the mapping rules will not be developed However, we need to develop some global rules based on the Capabilities
|  | alias_identification |  | 2 |  | Extend select and Explain in Annex H
T8.2 |  | attachment_slot | Tim King | - | 0%
T8.3 |  | attribute_classification | Rob Bodington | - | 0%
T8.4 |  | classification_assignment | Rob Bodington Tom Hendrix | 1 | 0%
T8.5 |  | condition | Rob Bodington | 4 | 0%
T8.6 |  | condition_evaluation | Rob Bodington | 4 | 0%
T8.7 |  | interface | Rob Bodington | 80 | 0% | There is a risk that we may have to make significant changes and produce new modules in order to harmonize with AP210,212
T8.8 |  | location | Mike Ward | 8 | 0%
T8.9 |  | location_assignment_characterized | Mike Ward | 4 | 0%
T8.10 |  | multi_linguism | Rob Bodington | 1 | 0% | Chase up resolution with AP236
T8.11 |  | name_assignment | Rob Bodington | 1 | 0% | This impacts on external class
T8.12 |  | observation | Rob Bodington Sean Barker | 1 | 0% | Need to update Annex H
T8.13 |  | product_as_individual | Rob Bodington | 20 | 0%
T8.14 |  | product_breakdown | Rob Bodington | 16 | 0%
T8.15 |  | product_group | Mike Ward | 8 | 0%
T8.16 |  | required_resource | Leif Gylstrom | - | 0%
T8.17 |  | resource_as_realized | Leif Gylstrom | - | 0%
T8.18 |  | resource_item | Leif Gylstrom | - | 0%
T8.19 |  | resource_management | Leif Gylstrom | - | 0%
T8.20 |  | resource_management_characterized | Leif Gylstrom | - | 0%
T8.21 |  | state_characterized | Mike Ward | 4 | 0%
T8.22 |  | state_definition | Mike Ward | 4 | 0%
T8.23 |  | state_observed | Mike Ward | 4 | 0%
T8.24 |  | system_breakdown | Rob Bodington | 16 | 0%
T8.25 |  | task_specification | Sean Barker | - | 0% | We need to harmonize work_output, actvity, task, scheme.
T8.26 |  | work_output | Leif Gylstrom | - | 0%
T8.27 |  | ap239_activity_recording | Sean Barker | - | 0%
T8.28 |  | ap239_document_management | Rob Bodington | 16 | 0%
T8.29 |  | ap239_management_resource_information | Rob Bodington | 16 | 0%
T8.30 |  | ap239_part_definition_information | Rob Bodington | 16 | 0%
T8.31 |  | ap239_product_definition_information | Rob Bodington | 16 | 0%
T8.32 |  | ap239_product_life_cycle_support | Rob Bodington | 16 | 0%
T8.33 |  | ap239_product_status_recording | Sean Barker | - | 0%
T8.34 |  | ap239_task_specification_resourced | Sean Barker | - | 0%
T8.35 |  | ap239_work_definition | Sean Barker | - | 0%
T10 | PLCS AP module
T10.1 |  | Select extension checks | Rob Bodington | 16 | 0% | We need to check that all necessary selects are extended, then extend the implementation modules in T8(ap239_**)
T10.2 |  | Mapping corrections | Rob Bodington | 16 | 0% | A number of mapping errors have been identified during ballot comments that need to fixed
T10.3 |  | Check all selects | Rob Bodington | 16 |  | check then modify implementation modules
T10.4 |  | Check all mappings | Rob Bodington | 16 |  | check then modify implementation modules
T10.5 |  | Long form generation | Rob Bodington | 16 |  | check then modify implementation modules
|  | HTML validation | Rob Bodington | 16 |  | This is an ongoing process that occurs during the development
T11 | Common resources
T11.1 |  | Part 41 "Fundamentals" IS publication | Mike Ward | 0 | 99% | Already funded by UK MOD + Eurostep
T11.2 |  | Part 56 "State" IS publiction | Tom Hendrix | - | 90%
T11.3 |  | Part 54 "Classification" IS publication | Tom Hendrix | - | 90%
IS0 publication
T13 | Divide modules into publication packages |  |  |  |  | The release of module to ISO will be iterative. The following tasks will be repeated for each publication
T14 | Issue report
T15 |  | XSL to collect ballot issues | Rob Bodington | 0 | 100% |  | Effort funded by Eurostep
T16 |  | Generation of issue report | Rob Bodington | 2 | 90% |  | Effort recently funded by Eurostep
T17 | Regenerate modules HTML |  | Rob Bodington |  |  | PLCS should only be responsible for PLCS modules
T18 | QC checks |  | Tim Turner | -
T19 | Project leader checks |  | Rob Bodington | 8
T20 | Send to convener |  | Rob Bodington | 8
T21 | ISO publication |  | Rob Bodington | 8
T22 | ISO editorial response |  | Rob Bodington | 16 |  | ISO may well require some changes
550
Note on G1: Rob Bodington: This is a contingency as the estimated hours is based on the assumption that everything goes to plan and each change does not have a knock on affect. We have tried to reduce the estimate to an absolute minimum
Note on F2: Nigel Shaw: As of 19 October 2004

## Module issue summary
Part | Number | Total issues | Open issues | Project leader | Editor | Developer
1047 | activity | 4 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1259 | activity_as_realized | 4 | 0 | John Dunford | Sean Barker | Sean Barker
1272 | activity_characterized | 3 | 0 | John Dunford | Tom Hendrix | Tom Hendrix
1049 | activity_method | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1249 | activity_method_assignment | 1 | 0 | John Dunford | Nigel Shaw | Nigel Shaw
1298 | activity_method_characterized | 1 | 0 | John Dunford | Tom Hendrix | Tom Hendrix
1261 | activity_method_implementation | 1 | 0 | John Dunford | Nigel Shaw | Nigel Shaw
1025 | alias_identification | 2 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1287 | ap239_activity_recording | 12 | 3 | John Dunford | Sean Barker | Sean Barker
1297 | ap239_document_management | 19 | 2 | John Dunford | Rob Bodington | Rob Bodington
1289 | ap239_management_resource_information | 26 | 1 | John Dunford | Rob Bodington | Rob Bodington
1293 | ap239_part_definition_information | 51 | 9 | John Dunford | Rob Bodington | Rob Bodington
1292 | ap239_product_definition_information | 55 | 1 | John Dunford | Rob Bodington | Rob Bodington
439 | ap239_product_life_cycle_support | 44 | 11 | John Dunford | Nigel Shaw | Rob Bodington
1304 | ap239_product_status_recording | 6 | 1 | John Dunford | Albert Leyson | Albert Leyson
1295 | ap239_properties | 15 | 0 | John Dunford | Tom Hendrix | Tom Hendrix
1306 | ap239_task_specification_resourced | 29 | 5 | John Dunford | Nigel Shaw | Sean Barker
1307 | ap239_work_definition | 19 | 5 | John Dunford | Nigel Shaw | Sean Barker
1012 | approval | 3 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1026 | assembly_structure | 4 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1250 | attachment_slot | 12 | 2 | John Dunford | Tim King | Rob Bodington
1246 | attribute_classification | 11 | 1 | John Dunford | Rob Bodington | Rob Bodington
1044 | certification | 3 | 1 | Simon Frechette | Darla Nettles | Simon Frechette
1070 | class | 1 | 0 | John Dunford | David Leal | Rob Bodington
1114 | classification_assignment | 3 | 1 | Ricardo Gonçalves | Maria José Núñez Ariño | Simon Frechette
1253 | condition | 17 | 3 | John Dunford | Leif Gyllström | Leif Gyllström
1257 | condition_characterized | 2 | 0 | John Dunford | Leif Gyllström | Leif Gyllström
1254 | condition_evaluation | 6 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1296 | condition_evaluation_characterized | 2 | 0 | John Dunford | Leif Gyllström | Leif Gyllström
1058 | configuration_effectivity | 3 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1056 | configuration_item | 2 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1027 | contextual_shape_positioning | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1062 | contract | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1010 | date_time | 2 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1014 | date_time_assignment | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1121 | document_and_version_identification | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1122 | document_assignment | 5 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1123 | document_definition | 5 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1290 | document_management | 2 | 0 | John Dunford | Rob Bodington | Rob Bodington
1126 | document_properties | 5 | 3 | Simon Frechette | Darla Nettles | Simon Frechette
1124 | document_structure | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1057 | effectivity | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1059 | effectivity_application | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1004 | elemental_geometric_shape | 2 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1265 | envelope | 12 | 0 | John Dunford | Sean Barker | Sean Barker
1064 | event | 4 | 0 | Simon Frechette | Darla Nettles | Tom Hendrix
1364 | event_assignment | 1 | 0 | Simon Frechette | Darla Nettles | Tom Hendrix
1243 | experience | 7 | 0 | John Dunford | John Spencer | Mike Ward
1106 | extended_measure_representation | 16 | 1 | John Dunford | Tom Hendrix | Tom Hendrix
1275 | external_class | 6 | 0 | John Dunford | Rob Bodington | Rob Bodington
1128 | external_item_identification_assignment | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1033 | external_model | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1127 | file_identification | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1006 | foundation_representation | 3 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1216 | functional_breakdown | 2 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1113 | group | 6 | 0 | Ricardo Gonçalves | Maria José Núñez Ariño | Maria José Núñez Ariño
1218 | hybrid_breakdown | 2 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1021 | identification_assignment | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1036 | independent_property | 1 | 1 | Simon Frechette | Darla Nettles | Simon Frechette
1038 | independent_property_representation | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1241 | information_rights | 9 | 0 | John Dunford | Sean Barker | Sean Barker
1251 | interface | 22 | 7 | John Dunford | Tim King | Mike Ward
1294 | interface_lifecycle | 7 | 0 | John Dunford | Tim King | Ian Bailey
1263 | justification | 10 | 1 | John Dunford | Kalle Serén | Kalle Serén
1276 | location | 15 | 6 | John Dunford | Erik Rieger | Mike Ward
1277 | location_assignment | 1 | 0 | John Dunford | Erik Rieger | Mike Ward
1358 | location_assignment_characterized | 4 | 1 | John Dunford | Erik Rieger | Mike Ward
1288 | management_resource_information | 14 | 0 | John Dunford | Rob Bodington | Rob Bodington
1118 | measure_representation | 5 | 1 | Simon Frechette | Darla Nettles | Simon Frechette
1270 | message | 14 | 0 | John Dunford | Sean Barker | Sean Barker
1105 | multi_linguism | 5 | 1 | Ricardo Gonçalves | Maria José Núñez Ariño | Maria José Núñez Ariño
1340 | name_assignment | 1 | 1 | John Dunford | Rob Bodington | Rob Bodington
1258 | observation | 5 | 1 | John Dunford | Sean Barker | Sean Barker
1240 | organization_type | 2 | 0 | John Dunford | John Spencer | Mike Ward
1022 | part_and_version_identification | 8 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1055 | part_definition_relationship | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1023 | part_view_definition | 4 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1011 | person_organization | 5 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1013 | person_organization_assignment | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1215 | physical_breakdown | 1 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1242 | position_in_organization | 14 | 0 | John Dunford | John Spencer | Mike Ward
1252 | probability | 22 | 0 | John Dunford | Sean Barker | Sean Barker
1274 | probability_distribution | 12 | 0 | John Dunford | Sean Barker | Sean Barker
1040 | process_property_assignment | 1 | 0 | Simon Frechette | Darla Nettles | Tom Hendrix
1164 | product_as_individual | 5 | 2 | John Dunford | Rob Bodington | Rob Bodington
1248 | product_breakdown | 14 | 4 | John Dunford | Tim King | Mike Ward
1016 | product_categorization | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1060 | product_concept_identification | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1278 | product_group | 16 | 1 | John Dunford | Erik Rieger | Rob Bodington
1017 | product_identification | 5 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1024 | product_relationship | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1046 | product_replacement | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1134 | product_structure | 8 | 0 | Bill Anderson | Darla Nettles | Simon Frechette
1018 | product_version | 3 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1020 | product_version_relationship | 3 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1019 | product_view_definition | 4 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1034 | product_view_definition_properties | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1041 | product_view_definition_relationship | 1 | 0 | Simon Frechette | Simon Frechette | Simon Frechette
1061 | project | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1030 | property_assignment | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1244 | qualifications | 4 | 0 | John Dunford | John Spencer | Mike Ward
1267 | required_resource | 4 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1280 | required_resource_characterized | 3 | 0 | John Dunford | Leif Gyllström | Leif Gyllström
1233 | requirement_assignment | 4 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1140 | requirement_identification_and_version | 4 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1348 | requirement_management | 1 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1141 | requirement_view_definition | 3 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1142 | requirement_view_definition_relationship | 3 | 0 | Jim U'Ren | Ian Bailey | Mike Ward
1269 | resource_as_realized | 4 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1283 | resource_as_realized_characterized | 4 | 0 | John Dunford | Leif Gyllström | Leif Gyllström
1268 | resource_item | 3 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1281 | resource_item_characterized | 2 | 0 | John Dunford | Leif Gyllström | Leif Gyllström
1266 | resource_management | 7 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1282 | resource_management_characterized | 5 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1273 | resource_property_assignment | 1 | 0 | John Dunford | Tom Hendrix | Tom Hendrix
1260 | scheme | 2 | 0 | John Dunford | Nigel Shaw | Nigel Shaw
1015 | security_classification | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1357 | selected_item | 0 | 0 | John Dunford | Rob Bodington | Rob Bodington
1210 | set_theory | 9 | 0 | John Dunford | David Leal | Rob Bodington
1032 | shape_property_assignment | 1 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1133 | single_part_representation | 9 | 0 | Ricardo Gonçalves | Maria José Núñez Ariño | Simon Frechette
1271 | state_characterized | 10 | 2 | John Dunford | Albert Leyson | Albert Leyson
1255 | state_definition | 26 | 1 | John Dunford | Albert Leyson | Albert Leyson
1256 | state_observed | 10 | 1 | John Dunford | Albert Leyson | Albert Leyson
1214 | system_breakdown | 3 | 1 | Jim U'Ren | Ian Bailey | Mike Ward
1262 | task_specification | 13 | 1 | John Dunford | Nigel Shaw | Sean Barker
1065 | time_interval | 2 | 0 | Simon Frechette | Darla Nettles | Tom Hendrix
1365 | time_interval_assignment | 0 | 0 | Simon Frechette | Darla Nettles | Tom Hendrix
1245 | type_of_person | 5 | 0 | John Dunford | John Spencer | Mike Ward
1054 | value_with_unit | 2 | 1 | Simon Frechette | Darla Nettles | Simon Frechette
1043 | work_order | 6 | 0 | Simon Frechette | Darla Nettles | Rob Bodington
1286 | work_order_characterized | 2 | 0 | John Dunford | Tom Hendrix | Rob Bodington
1300 | work_output | 4 | 1 | John Dunford | Leif Gyllström | Leif Gyllström
1301 | work_output_characterized | 1 | 0 | John Dunford | Leif Gyllström | Leif Gyllström
1042 | work_request | 0 | 0 | Simon Frechette | Darla Nettles | Simon Frechette
1285 | work_request_characterized | 4 | 0 | John Dunford | Tom Hendrix | Tom Hendrix
1217 | zonal_breakdown | 9 | 0 | Jim U'Ren | Ian Bailey | Mike Ward