## Ark1
Agree
Purpose
Specify
Develop
Test
activety number | type of activety | active partners | lead | sequence | % completion | level
[5 empty] | 100% | Issue AP239 as an IS
| Agree | [5 empty] | Agree resolution of DIS ballot comments
Prepare resolution programme
Implement change programme
Submit to ISO for publication
Issue as IS
[5 empty] | 70% | Extend DEXLIB tool set
User friendly front end
Develop terminology dictionary
Develop indexing method from terminology dictionary to DEXLIB
Interface to reference data
Allow publication of DEXs
Allow publication of Ref. Data
[5 empty] | 55% | Develop DEXLIB Documentation
Develop a documentation infrastructure
Develop a DEXLIB introduction
Develop the DEXLIB architecture and a framework explanation
Develop Implementation options
Develop guidelines for creating business domain extensions to Ref Data
Develop guidelines for developing capabilities
Develop mapping guidelines
Develop DEXs for business implementation
| Agree |  |  | 1 |  |  | Agree a common development method for DEXs (outcome of DEX Synchronisation meetings)
| Agree |  |  | 1 |  |  | Agree common content for DEXs (outcome of DEX Synchronisation meetings)
Develop a ‘core’ capability set
|  |  |  | 1 |  |  | Develop a DEX template (OASIS TC meeting 11 action item 2)
| Agree |  |  | 2 |  |  | Agree a common usage guidance method for DEXs
Specify a representation of a thesaurus of business concepts reflecting business terms *
Specify an indexing mechanism from the Business concepts to Dex capabilities *
Re-develop initial set of DEXs i.a.w. common agreements
|  |  |  | 0 |  |  | Incorporate the recommendations from the series of DEX Sync Workshops
Develop future DEXs
Identify potential future DEXs
Produce a DEX development programme
Decide how DEXs are to be published as OASIS standards
Develop a DEX publication mechanism
Publish DEXs as OASIS standard
Technical - Capabilities
Develop new capabilities as required
Incorporate new Ref Data
Enable representation of instantiation capabilities
Set up a review structure for capabilities
Technical - Ref Data *
Consolidate existing Ref Data files to establish baseline core
Establish a better development environment for consolidation and management
Technical - DEXs *
Develop an exchange agreement (specialisation of DEX)
Enable specialisation pruning of DEXs
Provide a mechanism for converting existing part 28 file to part 21 (OASIS TC meeting 11 action item 4)
Technical - Publication *
Continue to maintain DEXLIB on Sourceforge
Maintain an HTML mirror of DEXLIB for non developers
Allow an XML view facility in browsers (other than I Explorer)
Extend DEXLIB to allow TML publications
Extend DEXLIB to allow individual (or sets of) DEXs to be published as a standalone package electronically and on paper
Estabish a PLCS web server
Publish OWL files on the PLCS Web server
Establish PLCS RDL server accessed via APIs from translators
Develop Reference Data for DEX implementation
| Agree | [5 empty] | Agree how Ref. Data is to be published as a standard and how it will be maintained
Define reference data architecture
Develop pilot RDL service
| Agree | [5 empty] | Agree and standardised RDL services
Develop industrial strength RDL services
Define management of RDL services
Populate RDL services
Propose reference data from pilot sources
Instantiate reference data
Link with other standards
Develop a standard publication mechanism
Submit Ref. Data for ballot
Develop a programme to monitor the resolution of ballot comments
Publish Ref. Data as standard (OASIS TC meeting 11 action item 7)
Input recommendations from the synchronisation workshops
Develop Usage Guidance for business implementation
Modeller / Developer guidance
Business user guidance
Software implementer guidance
Contract managers guidance
Harmonisation with SC4 standards
10303 STEP APs
13584 PLIB
15926 Oil & Gas
Harmonisation with other standards
00-60
SCORM (OASIS TC meeting 11 action item 6)
1000D
2000M
OAGIS 9
W3C
OMG
MIP
SIMBASE
Develop AP239 edition 2
Risk
Test DEXs
Run Pilot projects for assurance of AP239
Identify pilot business areas
Modify DEXs based on pilot input
Share results of pilots
Review Framework for quality (OASIS TC meeting 11 action item 4)
Develop a method for viewing test data (OASIS TC meeting 11 action item 5)
Establish Implementers Forum
Define test data
Develop test tools
Run test rallies
Define Conformance requirements *
Establish implementers forum *
Establish tools to develop / view the test data
Establish tools to validate the test results
Formalise OASIS Role
Agreed programme of work
Agreed allocation of programme tasks
Rules for approval of methods
Agreed DEX development processes
Agreed Reference Data processes
Establish resource requirement *
Establishment of an Implementation Plan *
| Agree | [5 empty] | Agree process for review / ballot / update / maintenance of ref data *
Infrastructure of RDL Server
Infrastructure of DEXLIB publication environment
Establish API for PLCS
E:\Product Data Standards\009 - Introduce PD Standards\OASIS\Draft proposed OASIS plan V04.doc
Note on D8: Organisation that lead the activety and reports progress at TC. Lead include have the funding.
Note on C8: Organisations that fully involved with the lead, might include funding
Note on E8: The order in which the activies should be carried out.
Note on A8: 3-level number 1.9.9
Note on B2: A vote within OASIS TC documented in the minutes
Note on B3: Purposal for work to be added to the program
Note on B4: Detail the work to be done
Note on B5: Do the work
Note on B6: Check the work
Note on B8: Pick one from the list in the cell