PLEASE NOTE:  THIS TIMELINE REFERENCES THE V3 ENHANCEMENTS FOR CORE COMPONENTS, NOT THE V2 “RETROFIT” REQUIREMENTS.  THE V2 RETROFIT REQUIREMENTS WILL BE INCLUDED IN A SEPARATE TIMELINE.

| Activity # | Activity | Begin | End | Duration | Notes |
| --- | --- | --- | --- | --- | --- |
| [1] | Create strawman for V3 Core Components documents | Now | Release of new CC Spec | TBD | “V3 Core Components documents” refers to 2 documents: The document that describes V3 enhancements for Core Components (will be incorporated into V3 Registry specifications) The document that describes those Core Components requirements that are already covered by Registry functionality |
| [2] | Update Functional Points Mapping document based on new CC Spec | Release of new CC Spec | Release of new CC Spec + 2 weeks | 2 weeks |  |
| [3] | Update CC Metadata Summary and Discussion Points documents | End of [2] | End of [2] + 3 weeks | 3 weeks |  |
| [4] | Review documents from [2] and [3] with UN/CEFACT CC group | End of [3] | End of [3] + 3 weeks | 3 weeks | Allows UN/CEFACT CC group to review at their F2F meeting if they would like |
| [5] | Create V3 Core Components documents | End of [3] | End of [3] + 4 weeks | 4 weeks | Can be done in parallel with [4] - begins at completion of [3] Includes one week for updates based on discussion with UN/CEFACT CC group Also includes review by CC Review subcommittee (no particular time duration specified for this) |
| [6] | Send V3 Core Components documents to Registry TC for review | End of [5] | End of [5] | N/A | This is a milestone - therefore, the start/end dates are the same and there is no duration |
| [7] | TC review of V3 Core Components documents | End of [6] | End of [6] + 4 days | 4 days | TC reviews/approves at F2F |
| [8] | Incorporate documents into V3 specifications | End of [7] | End of [7] | N/A | This is a milestone - therefore, the start/end dates are the same and there is no duration |

THE FOLLOWING EXAMPLE ASSUMES A RELEASE DATE OF 7/19/02 FOR THE NEW CC SPEC (FINAL DATE IS 10/25/02):

| Activity # | Activity | Begin | End | Duration | Notes |
| --- | --- | --- | --- | --- | --- |
| [1] | Create strawman for V3 Core Components documents | 6/26/02 | 7/19/02 | 3 weeks | “V3 Core Components documents” refers to 2 documents: The document that describes V3 enhancements for Core Components (will be incorporated into V3 Registry specifications) The document that describes those Core Components requirements that are already covered by Registry functionality |
| [2] | Update Functional Points Mapping document based on new CC Spec | 7/19/02 | 8/2/02 | 2 weeks |  |
| [3] | Update CC Metadata Summary and Discussion Points documents | 8/2/02 | 8/23/02 | 3 weeks |  |
| [4] | Review documents from [2] and [3] with UN/CEFACT CC group | 8/23/02 | 9/13/02 | 3 weeks | Allows UN/CEFACT CC group to review at their F2F meeting if they would like |
| [5] | Create V3 Core Components documents | 8/23/02 | 9/20/02 | 4 weeks | Can be done in parallel with [4] - begins at completion of [3] Includes one week for updates based on discussion with UN/CEFACT CC group Also includes review by CC Review subcommittee (no particular time duration specified for this) |
| [6] | Send V3 Core Components documents to Registry TC for review | 9/20/02 | 9/20/02 | N/A | This is a milestone - therefore, the start/end dates are the same and there is no duration |
| [7] | TC review of V3 Core Components documents | 9/20/02 | 9/25/02 | 4 days | TC reviews/approves at F2F |
| [8] | Incorporate documents into V3 specifications | 9/20/02 | 9/20/02 | N/A | This is a milestone - therefore, the start/end dates are the same and there is no duration |