## Sheet1
RLTC General Body Action Items
2002-06-25
# | Date | Description | Assigned to | Due | Status
1 | 2002-05-21 | Provide "English Language" description of the OASIS IPR policy | B. Glushko | 2002-05-29 | Done
2 | 2002-05-21 | Clarify policy and procedures for email voting | H. Reddy | 2002-05-29 | Done
3 | 2002-05-21 | Check with Karl on ongoing status of the TC | H. Reddy | 2002-05-29 | Done
4 | 2002-05-21 | Change wording to estimated times in the Phase Dev process | H. Reddy | 2002-05-29 | Done
5 | 2002-05-21 | Draft Governance Document | B Gandee/P Schirling | 2002-05-29 | Done
6 | 2002-05-21 | Sign up for SCs | ALL | 2002-05-29 | Done
7 | 2002-05-21 | Research possible IPR holders that are relevant to this work | ALL | Ongoing | Ongoing
8 | 2002-05-21 | Post updates to the Charter on the RLTC website | H. Reddy | 2002-05-29 | Done
9 | 2002-05-21 | SC Work Plans Submitted to Hari | SC Chairs | 2002-06-07 | In Process
10 | 2002-05-21 | Integrated RLTC Workplan Developed | H. Reddy | 2002-06-11 | Done
11 | 2002-05-21 | Governance Proposal delivered to MPEG | B Gandee/P Schirling | 2002-07-15
12 | 2002-05-29 | Provide definition of "Liaison" from ISO | B Gandee/P Schirling | 2002-06-12 | In Process
13 | 2002-05-29 | Establish Email lists for the SCs | H. Reddy | 2002-06-12 | Done
14 | 2002-05-29 | Send template to develop work plan | H. Reddy | 2002-06-06 | Done
15 | 2002-06-12 | Provide input re: Sw tools to facilitate meetings/document sharing | All | 2002-06-19 | Done
16 | 2002-06-12 | Provide summary of JC discussion to the Rights List | H. Reddy | 2002-06-14 | Done
17 | 2002-06-12 | Submit Initial SC Work Plans | SC Chairs | 2002-06-19 | In Process
18 | 2002-06-12 | Provide Integrated Work Plan | H. Reddy | 2002-06-22 | Done
19 | 2002-06-12 | Provide sources for Profile Requirements to Profiles SC Chair (T. DeMartini) | ALL | Ongoing | Ongoing
20 | 2002-06-26 | Provide SC Web Site Needs to Hari | SC Chairs | 2002-07-10
21 | 2002-06-26 | Initiate Voting for the Minutes approval (5/29/02 and 6/12/02) and the Core and Standard Specification SC Change Management Process | H. Reddy | 2002-06-28