## Sheet1
SOA-RAF Punch list
Section | Item | Comment | Responsible party | Date closed
all sections | PR2_issues_2010-08-11: open issues identified as All, Editors, or Committee | need each editor to review their sections and enter specific items in punch list | each editor
general | UML models to be updated (specific needs should be entered below) | Jeff: Create all UML diagrams from scratch in a new MagicDraw project, organized around views. These will be packages in MD. | Jeff
general | PR2_issues_2010-08-11 issue 2: The capitalization of sections is not consistent. Compare, e.g., 1.1.4 and 1.4.1. | Partial Accept. All titles have significant words capitilized (Title Caps). Verify all titles captilize significant words.
general | PR2_issues_2010-08-11 issue 3: Some of the diagrams seem very fuzzy. And if they were produced by a tool, the tool should be noted. | Accept. When the final document comes out, we will make sure all the diagrams are clear. Magic Draw is used to generate the document, however, that will not be specified in the document.
general | PR2_issues_2010-08-11 issue 4: Semicolons appear to be frequently used where commas are more appropriate. Some specific examples are noted. (see also line 216) | When the editors reread/update the document the editors will try not to overuse semicolons.
general | PR2_issues_2010-08-11 issue 5: The large number of emboldened terms defined and used is confusing;a separate (non-normative) glossary and index would make the document more useful. | Use of a Glossary is rejected. However, identify the term has a definition in the RAF. Suggestion to use italics or a reference link. Will take representative paragraphs and update as an example before updating the document. Make every definition a book mark and link to the book mark,
general | PR2_issues_2010-08-11 issue 6: Capitalization is not consistent between the normative and non-normative references and their use in the document. Needs general editorial correction. | See paragraph starting at 2720. References should be all caps in document.
general | PR2_issues_2010-08-11 issue 7: A "typographical conventions" note under section 1.5 would make the document more useful and readable. Lee comments for line 314. | Accept, explain bold/capitilization in section 1.5.1.
general | PR2_issues_2010-08-11 issue 8: Many sections that should start on an odd page boundary do so only by accident. E.g. p24 as the start of a major section, the table of contents on page 4. This is difficult to read when printed double-sided. | Accept. Update major headings so that sections start on an odd page boundary.
title page | update dates, links, etc. |  | Ken
title page | who are final editors? |  | Ken
T of C | regenerate |  | Ken
T of Figures | regenerate |  | Ken
1.2.1 | insert Services in the Ecosystem |  | Ken
2.1 | Figure 2 needs final update
2.1 | PR2_issues_2010-08-11 issue 36: Is there a refernce for Critical Success Factors and "Critical Factors Analysis? Include one. Note that you use CFA as an abbreviation, but repeated indicate abbreviations for other terms in the doc -- refs if I have time. | Accept - But no agreed reference.
2.1.1 | PR2_issues_2010-08-11 issue 37: The goals are very abstract; the modeling is somewhat obscure (but I liked it eventually). There are more forward reference; the definition of Critical Success Factors on Line 417 follows its first use on 377. Please pay attention to forward references--they're jarring and make the document less accessible. YOU know what they mean, the reader does not. | Accept - Add a formal definition for Critical Factors Analysis at the beginning of the section. The diagram needs to be updated to be in synch with the sections.
3 | in work; remaining open issues as may still be applicable |  | Peter & Chris
3.1.4 | Much of Policy material originated by Danny but moved here. Any changes need to be considered in conjunction with what remains in section 4.4. |  | Danny, Peter & Chris
4 | PR2_issues_2010-08-11 issue 81: The label [figure caption] should be reworded, perhaps to "Model Elements Described in Realizing a Service Oriented Architecture View" (eliminate "the" before "Realizing") | 1. Keep "the" 2. change caption to match title in line 1367 | Ken
4.1.1.1 | PR2_issues_2010-08-11 issue 83: What do I do with this [figure]? What is its utility? Please explain in the text. | - This diagram was moved from later in the PR1 draft. Check with the PR1 surrounding text to see if some of that also needs to be moved. - Change line 1448 to read "Description, as shown in Figure 25, ..." - change line 1447 just to General Description - diagram spread out and might be better to be more compact so text is bigger. | Ken
4.1.1.3.1 | PR2_issues_2010-08-11 issue 84: From Joint Action to "exchange of messages". Which way to describe? | [make sure these connections still exist] reject, there is already a connection - line 43 says primarily through exchange of messages - line 770 precisely connects - section 3 will clearly show message exchange as an example of joint action | Ken, Peter & Chris
4.3 | recent input from Michael Poulin | Michael and Jeff to resolve | Jeff
5.3 | management section | Rex: Explanation for why we don't have a Management Model in the RAF. I would appreciate it very much if this explanation was as brief as possible.
5.4 | appropriate models and definitions need to be added |  | Ken, Michael
5.4.2 | editor's notes need to be removed |  | Ken, Michael